# United Nations Development Group Iraq Trust Fund

# Project #:B1-01

# Date and Quarter Updated: 22nd June 2008 (2nd Quarter)

# Operationally Complete

| Participating UN Organisation: UNESCO | Cluster: B |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Education – Baghdad, Iraq |

# Programme/Project Number:

| Title | REvitalization of TechNical and Vocational Education and Training |
| --- | --- |
| Location | Baghdad (Karkh and Resafa), Ninewa (Mosul) and Al-Muthanna (Samawah) |
| Project Cost | US $ 2,758,274 |
| Duration | 8 July 2004 to 31 December 2005 (extended three times: First until 31st Aug. 2006, Second until 30th September 2006 and Third until 31st December 2006). |
| Approval Date (SC) | 3 May 2004 | Starting Date | Sept. 2004 | Completion Date | 31st Dec. 2006 |
| Project Description | Procurement of IT and vocational workshop equipment to 11 TVET schools in Baghdad, Mosul and Samawah. Installation of all equipment in the 11 TVET schools. Training of IT MOE staff on installation of IT equipment. |

# Development Goal and Immediate Objectives

Provide essential and basic workshop equipment, computers and training materials for high priority disciplines; Provide computers for improving IT skills for teaching staff; Prepare the recipient institutions for future networking with the proposed national internet link as well as the international links.

# Outputs, Key activities and Procurement

| Outputs | Eleven (11) technical and vocational institutions in Baghdad, Mosul and Samawah fully equipped with workshops and a network of computer centres; Improved quality of teaching and training for students in the 11 institutions in Baghdad, Mosul and Samawah through the acquisition of IT skills; and Improved IT facilities for the teaching staff at the 11 institutions in Baghdad, Mosul and Samawah. |
| --- | --- |
| Activities | Procurement of IT and vocational workshop equipment to 11 TVET schools in Baghdad, Mosul and Samawah. Installation of all equipment in the 11 TVET schools. Training of IT MOE staff on installation of IT equipment. |
| Procurement (major items) | Vocational Workshop equipment Computer Labs. |

# Part Two: Situation as of 22nd June 2008

| Funds Committed | $2,757,198 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | $2,757,198 | % of approved | 100% |
| Forecast final date |  | Delay (months) |  |

# Quantitative achievements against objectives and results

| Procurement of vocational workshop equipment | All Achieved | % of planned | 100 % Achieved |
| --- | --- | --- | --- |
| Procurement of IT and Computer Labs | All Achieved | % of planned | 100 % Achieved |
| Training of IT personnel on Installation | All Achieved | % of planned | 100 % Achieved |

# Qualitative achievements against objectives and results

The project has been successfully implemented in line with the planned strategy. Delivery of equipment is completed to the selected 11 TVET schools. Eleven (11) TVET schools are fully equipped with the most up to date vocational training equipment which will enhance the training delivery process. MOE capacity of IT staff is enhanced through the training of 28 IT persons on installation and networking which was undertaken in Amman during 11 – 30 March 2006. The provided new IT Labs and IT workshop equipment during the academic year (2005-2006) is contributing to the improvement of quality IT education within these 11 TVET schools. Equipment is fully operational with high rate of utilization by MOE staff and students. The direct impact of the project is that 11 technical and vocational institutions in Baghdad, Mosul and Samawah have started the scholastic year 2005-2006 with newly equipped workshops and computer labs for electrical and mechanical engineering as well as for carpentry and commerce programmes. This will enable those institutions to improve the quality of education delivered with a higher emphasis on practical training.