# FINAL

# United Nations Development Group Iraq Trust Fund

# Project #:B1-09

# Date and Quarter Updated: 30 September 2008, 3rd. Quarter

# Part One: Summary

| Participating UN Organisation: UN-HABITAT | Sector: Education SOT |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education; Ministry of Higher Education & Scientific Research |

| Title | Education Facility Rehabilitation |
| --- | --- |
| Geographic Location | Baghdad, Basrah, Samawa and Nassiriya |
| Project Cost | US$ 17,580,663 |
| Duration | 12 months |
| Approval Date (SC) | 8th July 2004 | Starting Date | August 2004 | Completion Date | September 2008 |
| Project Description | Rehabilitation of educational facilities (Schools, vocational schools, Institutes, & universities), Supply of equipment tools, and instruments to technical institutes, technical capacity building and employment generation. |

# Development Goal and Immediate Objectives

To rehabilitate kindergarten, primary, secondary, technical and university educational facilities damaged by war and looting in the current areas operation. To upgrade the capacity of the workshops & laboratories of the technical institutes. To develop skills of construction workers and young professionals in construction, mechanical and electrical engineering To provide employment opportunities in the construction sector and income generation at local level for skilled and unskilled workers

# Outputs, Key activities and Procurement

| Outputs | Education activities resumed/enhanced in a total of 34 educational facilities in selected locations to provide improved education for about 30,000 student at different levels . Skills developed of construction workers and young engineering professionals involved in the rehabilitation activities Construction workers employed through local contractors selected in the area of the specific interventions |
| --- | --- |
| Activities | Rehabilitation/ construction of 16 kindergartens; 12 primary/ secondary schools, 7 vocational facilities, 3 technical education facilities and 2 universities in the selected locations. On the job training of young engineers and construction workers. |
| Procurement (major items) | Supply operational furniture to 26 schools and kindergartens and 4 vocational facilities. Supply IT equipment to one UNIVERSITY; supply laboratory & workshops equipment to three Technical Institutes |

# Part Two: 31/05/2008

| Funds Committed | $17,580,663 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | $17,580,663 | % of approved | 100% |
| Forecast final date | September 2008 | Delay (months) | 38 |

# Quantitative achievements against objectives and results

| Rehabilitation/construction of 15 kindergartens &11 school buildings in Baghdad. 2 school buildings in Samawa, 6 vocational training institutes , 5 l vocational workshops in Nassiriya, 7 workshops & 2 colleges in Basrah 3 technical institutes in Baghdad, Basrah and Samawa | Completed | % of planned | 100 % |
| --- | --- | --- | --- |
| Sanitation Facilities in 5 colleges and institutes were constructed | Completed | % of planned | 100 % |
| One Social care Institute for Deaf & Mute in Nassiriyah is constructed | Completed | % of planned | 100 % |
| One training clinic was constructed in medical college in Basrah University. | Completed | % of planned | 100 % |
| IT equipment supplied to the University of Technology in Baghdad | Completed | % of planned | 100 % |
| Furniture supplied to 25 schools & kindergartens in Baghdad and 4 vocational facilities in Samawa | Completed | % of planned | 100 % |
| Laboratories equipment Supplied to Basrah, Samawa and Baghdad/Zaafraniya Technical Institutes | While the main shipments have been received, some items need to be replaced and these will be delivered within the coming three months | % of planned | 100% |
| Employment of local workers. | A total of 372,361 persons –days | % of planned | 100% |

# Qualitative achievements against objectives and results

Educational facilities for 30,000 students has been restored and revitalised & a better learning environment is maintained Improved technical capacity was guaranteed for vocational schools specialized technical institutes in three governorates. Employment at a significant rate was generated for local workers and rehabilitation skills were developed for new engineers