Seventh Six-month progress report for project

# REPORT COVER PAGE

| ## Participating UN Organization: |  | ## Cluster: |
| --- | --- | --- |
| UN-HABITAT |  | B - Education and Culture |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| B1-09 Educational Facilities Rehabilitation Project |  | 7 |

| ## Reporting Period: |  | ## Project Budget: |
| --- | --- | --- |
| 1 July to 31 December 2007 |  | UNDG ITF: $17,580,663 |

| ## List Implementing Partners: |  | ## Project Coverage/Scope: |
| --- | --- | --- |
| - Ministry of Education; Ministry of Higher Education and Scientific Researches |  | Baghdad, Basrah, Samawa and Nassiriya |

| ## Abbreviations and acronyms: |  | ## Project Duration/Closed Project: |
| --- | --- | --- |
| MoE : Ministry of Education MoHE; Ministry of Higher Education DoE: Directorate of Education HQ: Head Quarter TVE: Technical and vocational education |  | - 47 months (August 2004 – June 2008). Ongoing - Report on budget revisions and extensions and provide the new dates. – is being processed Indicate if the project has been operationally closed during the reporting period.- NA |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Objectives:

The main objective of the project is to enhance access to education in Iraq at all levels.

Outputs:

The main outputs as per the approved project document are as follows:

- Rehabilitation of 34 educational facilities in the selected locations to provide improved education environment for about 30,000 students;

- Improved skills for construction workers and young engineering professionals involved in the rehabilitation activities;   and

- Employment generated for approximately 5000 construction workers per day through local contractors selected in the areas of specific interventions.

Outcomes:

Improved access to educational facilities at all levels.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq:

The project is an integral component of the Programme being implemented by the Education & Culture Cluster within the framework of the UN Assistance Strategy for Iraq, which, as one of its principal developmental goals for the education sector, seeks to increase participation and completion rates at all levels of education, strengthen service delivery and support and inform policy development.

- UN Millennium Development Goals:

- The project is expected to strengthen primary, technical and higher education as envisaged in the Millennium Development Goal on Education; and

- The project is contributing to the Millennium Development Goal "eradication of extreme poverty and hunger" by providing significant employment opportunities.

- Joint Needs Assessment:

The project responds to the medium term priorities of the 2003 UN-World Bank Joint Needs Assessments follows:

- Ensure minimum quality standards of teaching and learning and system management through strengthening basic training and providing an adequate supply of materials and equipment.

- Begin physical rehabilitation and reconstruction of primary and secondary schools, prioritising replacement of schools that are no longer serviceable.

- For TVE rehabilitate key buildings and replace essential equipment as needed in the short-term, and assist the TVE system before carrying out more extensive investment.

- Iraqi National Development Strategy:

The project responds to the NDS Goal 2, i.e. Achieve Primary Education for All

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

UN HABITAT is working closely with the following partners in the implementation of this project:

      - Representatives of the Directorates of Education (DoE) and representatives of Universities & Technical Institutes. During the reporting period, they participated in joint field visits along with UN-HABITAT consultant engineers in each governorate. The Ministry of Education via local Education Directorates and the Ministry of Higher Education & Scientific Research continue to be involved in all procedures relating to identification of educational facilities, needs assessment and detailing of specifications for technical equipment, bid opening, supervision of works, and final acceptance of the works and supplies.

      - Local contractors in order to maximize the employment impact of the project and enhance the capacity of local contractors

      - Local consultants/engineers, who are engaged in the technical assessments and preparation of scope of work, bidding documents, participate in the tenders opening process. They also participate effectively in the supervision, follow up & quality control of the rehabilitation works according to tender requirements including:  quality of work & compliance with technical specifications, quantities according to the approved BoQ, and timely completion of works.

      - International Suppliers of technical equipment, tools, and instruments.

- Human Resources

2.1 National Staff: Provide details on the number and type (operation/programme)

      - Two national operations staff

      - Four national programme staff, and

      - Ten national field engineers

2.2 International Staff: Provide details on the number and type (operation/programme)

- Programme Manager (part time)

- Rehabilitation Expert

- Programme Management Officer (part time)

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- UN-HABITAT national consultants, with the active participation of DoEs and representatives of Universities & Technical Institutes, carry out a detailed assessment of the facility to be rehabilitated. An assessment report is prepared based on the needs identified by the beneficiaries. Based on the technical assessment and identification of scope of works, detailed Bills of Quantities (BoQs) are prepared by the field personnel, including detailed specification, quantities and standards.

- The Bills of Quantities and the technical specifications are sent to UN-HABITAT Office in Amman for review by the Rehabilitation Team. Once approved, the Rehabilitation Expert authorizes the preparation of the tender documents. The rehabilitation works are packaged into small contracts - typically between $50,000 and $150,000 in size - that can be carried out by small Iraqi Contractors.

- UN-HABITAT maintains a register of - now over 1000 - Iraqi Contractors with different specialties and grades in the four targeted governorates. Bidders are selected from a comprehensive contractors’ database based on a selection criteria. Normally, between 10 and 20 Iraqi contractors are invited to tender for each rehabilitation contract depending on the estimated amount of each contract.

- Implementation supervision is carried out on a daily basis by UN-HABITAT field Consultant Engineers.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- The tender evaluation process incorporates a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team based in Erbil/Iraq prepares the Agency Estimate (estimated cost) for each contract, using a specifically designed database system, which generates priced Bills of Quantities using monthly updated market prices. Prices of materials and labour are regularly compared with that collected by other UN agencies.

- For contracts, which exceed $150,000 the tender evaluation report is subject to review and approval by the Local Contracts Committee of the United Nations Office in Nairobi (UNON). Contracts of $150,000 are locally reviewed and approved by the Programme Manager (PM) under the terms of a special delegation of authority.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

- Rehabilitation works are supervised and monitored by Iraqi national consultants. The progress of works monitored and approved through time-series photographs, daily briefings from the consultants, videos & telecommunication, laboratory test reports for quality control of construction materials. In addition, initial handing over certificate is issued upon completion & acceptance of the rehabilitated facility by the direct beneficiaries.

- Interim payments are only released to the contractor upon accepting the work progress and quality by the Senior Engineer and the Rehabilitation Expert in Amman Office, certified by the PMO and then approved by PM as a final stage before being sent to HQ for processing.

- During the maintenance period, constant monitoring of the implemented work is carried out by the field personnel in close coordination with the counterparts and beneficiaries to check the quality of works and request the remedy of defect if necessary.

- Before the rehabilitated facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the Local Authority, the beneficiaries, the relevant department of the government and UN-HABITAT field staff. The final payment will be then released after issuance of final acceptance by the Committee

  - Report on any assessments, evaluations or studies undertaken.

A third party evaluation of procurement practices was carried out during the reporting period.  The recommendations of the evaluation have since been implemented.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six-month reporting period.

During the reporting period, the following activities were implemented;

- The rehabilitation of the Electrical Department, Transformer Building and the sewage network for Zafaraniyah Technical Institute in Baghdad was 100% completed.

- The rehabilitation of the Secondary School in Samawa was 100% completed.

- The supply of equipment, tools and Instruments for the Basrah Institutes has reached 99 % during the reporting period while for Baghdad Technical Institute has reached 77%.

- The construction of the Deaf & Mute Institute was 100% completed.

- The supply of furniture to schools & kindergartens in Baghdad was 100% completed.

- The project generated 3,453 persons-days of local employment.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

- Increased the access to educational programmes at all levels (kindergartens, schools, vocational training, technical institutes & universities)

- Contributed widely to enhanced access to vocational schools in southern governorates for both genders, and also in significant reduction in girls drop out especially at the secondary school level.

- Contributed to the filling of skill gaps in the labour market through the rehabilitation of specialized technical workshops, institutes & university departments and supply of equipment, tools & instruments.

- Enhanced the environmental health and hygiene through the rehabilitation/upgrading of sanitary facilities.

  - Report on the key outputs achieved in the six month period including and nature of the activities (inputs), % of completion and beneficiaries.

Up to 31st. December 2007, the following completed and ongoing works have benefited around 29,000 students at various levels of education.  Progress on specific sub projects during the reporting period are as follows:

- The Supply of furniture to 25 schools & kindergartens has been 100% completed;

- Rehabilitation of one technical department, one secondary school, and one Deaf & Mute Institute has been completed; and

- The supply of equipment, tools and instruments to the Baghdad & Basrah Institutes has reached to a good progress (almost 92%).

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

The implementation of the various rehabilitation works has been delayed, largely due to security-conditions.  Furthermore, the supply of equipment by International companies has been affected by the delay in obtaining necessary customs clearances.

The implementation experience of this project has provided the following significant lessons:

Implementation Planning of Physical Works:  Most of the physical works and offshore procurement have taken longer than their planned duration due to security conditions and difficulties in obtaining customs clearances. This experience has helped to plan more realistically as well provide for contingencies, factoring in such unanticipated delays.

Market Price Fluctuations:  Market prices of both labour and materials have been extremely volatile, in turn affecting the scope of the project.  UN-HABITAT is now considering carrying out sensitivity analyse of different design and technology options, so as to mitigate the problems resulting of unexpected price variations.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project is being implemented in collaboration with the Directorate of Education in each governorate & the representatives of the technical institutes and university departments. These partners are involved in all stages of the project cycle, such as: selection and prioritisation of educational facilities for rehabilitation; procurement and contracting; implementation supervision; in addition to final approval of works and supplies.  This has helped to ensure transparency, and foster a greater sense of responsibility and commitment from amongst client departments.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including of short and/or long-term jobs created), and environment.

Security: Nothing substantive.  At the same time, despite security constraints and resultant delays, 96% of works were completed by the end of the reporting period.

Gender and Human Rights:  All rehabilitated institutes offered equal learning opportunities for both girls and boys, where applicable. Throughout the improvement of the teaching learning environment, the project has also contributed towards the basic human right through enhancing quality education.

Employment: The project has generated 372,361 persons–days of local employment.

Environment: Through improved sanitation facilities, the project has contributed directly to environmental improvement.  In addition the technologies and materials used in this project are environmentally benign.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

- The project is expected to be 100% completed during the next reporting period.   The supply of the final consignment of equipment, tools & instruments to Baghdad/ Zafaraniya Technical Institute is expected to be completed by end June 2008.  The replacement of the missing and damaged items for Basrah Technical Institute is also expected to be completed by end June 2008.  Activities will include facilitating supply and transportation including obtaining necessary Custom Clearances and formal handovers to the end beneficiaries.