- United Nations Development Group Iraq Trust Fund

- Project #:B1-17

- Date and Quarter Updated: 08Q4

- Part One: Summary

| Participating UN Organisation: UNESCWA | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Higher Education |  |

| Title | Iraqi Networking Academies Project – Phase II |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Baghdad, Basra, Mosul and Erbil, as well as other cities and towns in Iraq |  |  |  |  |
| Project Cost | $3,780,000 |  |  |  |  |
| Duration | 36 months |  |  |  |  |
| Approval Date (SC) | 22 July 2004 | Starting Date | 25 August 2004 | Completion Date | 30 June 2008 |
| Project Description | The main goal of the project is to provide Iraqis the opportunity to receive networking education and thus empower them to actively contribute to the development of a robust ICT education sector that will help towards the rebuilding of their country. |  |  |  |  |

- Development Goal and Immediate Objectives

Establishing 5 Regional and 39 Local Networking Academies in Baghdad, Mosul, Basra and Erbil to train Iraqi university students on the basic and advanced Cisco networking courses.

- Outputs, Key activities and Procurement

| Outputs | The project end date is 30 June 2008. Therefore, this project is complete. However, some activities have started prior to the end date but haven’t been completed yet. |
| --- | --- |
| Activities | - Study on the use of ICT in conflict: this study was started in June and will be completed by end of 2008; - Shipment of Cisco books: the goods are at the shipper’s location in the USA. However, due to budget limitations, this activity is pending a budget revision; - External project evaluation: ISG has completed the evaluation of the INA project, and has submitted two draft reports. The final report is being prepared and should be submitted in October; |
| Procurement (major items) | No procurement of goods and services was initiated in this period. |

- Part Two:

- Situation as of 31/12/2008

| Funds Committed | $ 3,642,996.46 | % of approved | 96% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 3,517,305.95 | % of approved | 93% |
| Forecast final date | 31 December 2008 | Delay (months) | 6 |

- Quantitative achievements against objectives and results

| Training of students | Up until end of June 2008, Cisco reports more than 1900 students and instructors trained in the Iraqi academies since the start of the implementation of the project. | % of planned | 100 % |
| --- | --- | --- | --- |
| Training of trainers | 3 training-of-trainer sessions were completed in 2004, 2006, and 2007. | % of planned | 100 % |
| Purchase of IT equipment | All necessary equipments to launch the academies have been purchased. | % of planned | 100 % |
| Shipment of IT equipment | The Cisco books are the only goods still left to be delivered. Delivery will take place in July. This delay is due to the unavailability of some books, which were published in May 2008, and the necessity to undertake a redeployment of funds. | % of planned | 95 % |

- Qualitative achievements against objectives and results

The project manager moderated a presentation about the INA project in the UN Regional Commissions Retreat in Turin, Italy, between 31 August and 2 September 2008. The project (concept, implementation, and sustainability) appealed to all participants, who praised the efforts of all project stakeholders in the commitment to the success of the project.