# United Nations Development Group Iraq Trust Fund

# Project #:B1-17

# Date and Quarter Updated: 08Q2

# Part One: Summary

| Participating UN Organisation: UNESCWA | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Higher Education |

| Title | Iraqi Networking Academies Project – Phase II |
| --- | --- |
| Geographic Location | Baghdad, Basra, Mosul and Erbil, as well as other cities and towns in Iraq |
| Project Cost | $3,780,000 |
| Duration | 36 months |
| Approval Date (SC) | 22 July 2004 | Starting Date | 25 August 2004 | Completion Date | 30 June 2008 |
| Project Description | The main goal of the project is to provide Iraqis the opportunity to receive networking education and thus empower them to actively contribute to the development of a robust ICT education sector that will help towards the rebuilding of their country. |

# Development Goal and Immediate Objectives

Establishing 5 Regional and 39 Local Networking Academies in Baghdad, Mosul, Basra and Erbil to train Iraqi university students on the basic and advanced Cisco networking courses.

# Outputs, Key activities and Procurement

| Outputs | Phase II of the project is being implemented. It involves the establishment of 1 Regional Networking Academy in Erbil and 33 Local Networking Academies throughout Iraq. This is part of the last stage of the implementation of this project: shipment of Cisco lab bundles have been delivery to Iraq and Cisco books under the process of being delivered. An end-of-project workshop was organized on 27-28 June in Beirut, which was part of the final project evaluation exercise. |
| --- | --- |
| Activities | Cisco Advanced Technologies lab bundles have been delivered during June 2008 to all the regional academies in Iraq. A contract has been awarded to International Solutions Group (ISG), to conduct a comprehensive substantive evaluation of the project. An end-of-project workshop has been organized in Beirut on 27-28 June 2008 to discuss the project implementation, its operation, problems faced and their solutions. This meeting gathered all project stakeholders: academy instructors and students, a representative of the MOHE, Cisco. Lebanese American University, Université Saint Joseph, ISG, and the Education Sector. A study on the use of ICT in conflict afflicted countries is being undertaken by a consultant. |
| Procurement (major items) | Purchase Order of Cisco books have been issued and currently in the process of the shipment. |

# Part Two:

| Funds Committed | 3,523,488.80 | % of approved | 93 |
| --- | --- | --- | --- |
| Funds Disbursed | 3,332,006.98 | % of approved | 88 |
| Forecast final date | 30 June 2008 | Delay (months) | 0 |

# Quantitative achievements against objectives and results

| Training of students | Up until end of June 2008, Cisco reports more than 1900 students and instructors trained in the Iraqi academies since the start of the implementation of the project. | % of planned | 100 |
| --- | --- | --- | --- |
| Training of trainers | 3 training-of-trainer sessions were completed in 2004, 2006, and 2007. | % of planned | 100 |
| Purchase of IT equipment | All necessary equipments to launch the academies have been purchased. | % of planned | 100 |
| Shipment of IT equipment | The Cisco books are the only goods still left to be delivered. Delivery will take place in July. This delay is due to the unavailability of some books, which were published in May 2008. | % of planned | 95 |

# Qualitative achievements against objectives and results

During the workshop, all stakeholders raised the importance of this project and the positive impact it had on the Iraqi university community. All participants expressed their views in filling feedback forms which will be reflected in the final project report.