# United Nations Development Group Iraq Trust Fund

# Project #:B1-18

# Date and Quarter Updated: 7 January 2008 (1st Quarter)

# Part One: Summary

| Participating UN Organisation: UNESCO | Sector: Education |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Education – Baghdad, Iraq |

| Title | Textbooks Quality Improvement Programme II |
| --- | --- |
| Location | All over Iraq (Nationwide) |
| Project Cost | US$ 7,100,000 |
| Duration | Sep. 2005 – 21st February 2006 (Extended four times: (1) Until 30 April 2006, (2) Until 20 June 2006, (3) Until 30 September 2006 and (4) 30 November 2006) |
| Approval Date (SC) | 29 September 2005 | Starting Date | 4th of Sep. 2005 | Completion Date | 30 Nov. 2006 |
| Project Description | The aim of this project was to provide immediate support to basic education in Iraq through the printing and distribution of primary and secondary textbooks to more than 6 million students of grades 1 – 12 and to strengthen the MOE capacity in formulating national textbook printing and distribution policy. |

# Development Goal and Immediate Objectives

Improving Quality Education of schools at primary, lower secondary and secondary level in Iraq..

# Outputs, Key activities and Procurement

| Outputs | The main outputs of the project are: 9 million school textbooks printed and distributed (39 Titles) to 14,000 primary and secondary schools in 18 governorates. Capacity of MoE built in the field of textbooks production and distribution. Establishing a pre-press center at the Directorate of curriculum. Establishing Textbooks and CD library at the Directorate of curriculum. A modern “National Textbooks Policy Document” formulated for Iraq. |
| --- | --- |
| Activities | Key Activities of this project are: Revision of textbooks content (39 Titles) and production of electronic versions (CDs) Printing 9 million school textbooks for primary and secondary schools at Iraqi and International printing presses. Distribution of 9 million textbooks to children in 18 governorates. Organizing a workshop for building the capacity of MOE textbooks designers. Organizing a workshop for building the capacity of MOE heads of writing committees. Establishing a pre-press center at the Directorate of curriculum. Establishing Textbooks and CD library at the Directorate of curriculum. Assisting MOE in formulating a modern “National Textbooks Policy Document”. |
| Procurement (major items) | Textbooks Printing: US$ 5,606,488.36 IT Equipment: US$ 128,110.00 |

# Part Two: Situation as of 31st December 2007

| Funds Committed | $6,643,720 | % of approved | 93.57% |
| --- | --- | --- | --- |
| Funds Disbursed | $6,599,683 | % of approved | 92.95% |
| Forecast final date |  | Delay (months) |  |

# Quantitative achievements against objectives and results

|  | Project Completed in Nov. 2006 | % of planned |  |
| --- | --- | --- | --- |
|  |  | % of planned |  |
|  |  | % of planned |  |
|  |  | % of planned |  |

# Qualitative achievements against objectives and results

Project Completed in Nov. 2006