# United Nations Development Group Iraq Trust Fund

# Project #:B1-22(a+b)

# Date and Quarter Updated: 30 June 2008, 2nd quarter

# Part One: Summary

| Participating UN Organisation: UNICEF and UN-HABITAT | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: |

| Title | School rehabilitation and capacity building for school maintenance |
| --- | --- |
| Geographic Location | Babel, Baghdad, Diyala, Dahuk, Erbil, Kerbala, Kirkuk, Muthanna, Najaf, Ninewa Qadissiya Salah Al-Din Sulaymaniyah & Wassit and as per the list attached. |
| Project Cost | UNICEF US$ 9, 029,119 and UN-HABITAT US$ 6, 631,818 |
| Duration | 24 months |
| Approval Date (SC) | 16 July 06 | Starting Date | 16/06/06 | Completion Date | [31/December/2008] |
| Project Description | The Programme will support the rehabilitation of 160 schools in 18 Iraqi Governorates and capacity building for school maintenance and School Sanitation and Hygiene Education. The Programme will be implemented in 2 phases. |

# Development Goal and Immediate Objectives

Goal: The main objective of the Program is to increase access to primary, intermediate and secondary education for school age children grade 1 to 12 with emphasis on rural areas and girls’ education, and enhance the capacity of DOEs on school maintenance and school sanitation and hygiene promotion. Objectives: 1. Improvement of physical environment of 160 schools in 18 governorates including water and sanitation facilities. 2. Enhance the capacity of DOE to undertake the maintenance of school and promote hygiene practices. 3-Reduce the number of shifts and reduce the number of students in crowded classrooms by adding new classrooms 4-Building capacity of local contractors under several categories and use local material which will improve the economical conditions of the local communities 5-Reduce the number of unemployment in local remote communities

# Outputs, Key activities and Procurement

| Outputs | Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children Train 55 DOE technical staff , 160 head teachers and 320 PTA representatives of the rehabilitated schools on best practices in school maintenance programme (including the use of public-private partnerships) and on the promotion of improved sanitation and hygiene practices. In the schools. Develop a manual on management of school building and maintenance and guidelines on school sanitation and hygiene practices. |
| --- | --- |
| Activities | Contracting about 100 local Iraqi contractors for implementing the comprehensive rehabilitation of 160 schools in 18 governorates. Hiring engineers /monitors to provide technical assistance and to undertake the monitoring of the rehabilitation activities. Engage International and Iraqi consultants to conduct training workshops and to work with UN and MOE/DOE staff in developing manuals and guidelines on school maintenance and school sanitation and hygiene practices, including an information dissemination programme to promote awareness among the students, parents and teachers on these practices |
| Procurement (major items) | None |

# Part Two:

# UNICEF

| Funds Committed | $9,019,023.51 | % of approved | 99% |
| --- | --- | --- | --- |
| Funds Disbursed | $8,370,723 | % of approved | 92% |
| Forecast final date | June 2008 | Delay (months) | 0 |

UN-HABITAT

| Funds Committed | $6,546,016 | % of approved | 98.7 % |
| --- | --- | --- | --- |
| Funds Disbursed | $6,051,954 | % of approved | 91 % |
| Forecast final date | June 2008 | Delay (months) | 0 |

# Quantitative achievements against objectives and results

| Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children Train 55 DOE technical staff , 160 head teachers and 320 PTA representatives of the rehabilitated | Comprehensive rehabilitation of 8 (6 UNICEF and 2 HABITAT) schools completed during the reporting period. This added to the 147 (77 UNICEF and 70 HABITAT) completed before the reporting period makes the total schools so far completed 147. Currently rehabilitation of 13 (UNICEF) schools is ongoing. Note: In addition to the original plan of rehabilitating 90 schools by UNICEF, savings made from this project enabled UNICEF to rehabilitate additional 13 schools (3 comprehensive in Wasit and 10 water and sanitation facilities in Kirkuk all of them are completed). Hence total schools in this project are 103 (UNICEF) schools. | % of planned | 92% |
| --- | --- | --- | --- |
| Train 55 DOE technical staff , 160 head teachers and 320 PTA representatives of the rehabilitated schools on best practices in school maintenance programme (including the use of public-private partnerships) and on the promotion of improved sanitation and hygiene practices. In the schools. . | Training of 452 teachers and Head masters on schools Hygiene and sanitation took place 12 -18 December in Wasit, Basra, Missan, Baghdad and Thiqar governorates. Reprinting of 5,000 School Sanitation and Hygiene manual and procurement of kits for the training is in progress. Training of 55 technical staff (Baghdad & KRG) on schools maintenance will take place as soon as the manual is finalized / approved by the Ministry of Education, hopefully second quarter of 2008. | % of planned | 95% |
| Develop a manual on management of school building and maintenance and guidelines on school sanitation and hygiene practices. | Following previous workshops held in the June, UNICEF and MOE officials held a meeting in Amman on October 16-18 and agreed that MOE will develop school maintenance manual with UNICEF financial support in 2008. | % of planned | 60% |

# Qualitative achievements against objectives and results

Post rehabilitation data collected from 24 schools (out of 56 completed in 2007) reveal that the improved environment is having a positive contribution towards the achievements of project objectives. The Construction of 80 new classrooms and 122 additional toilets for girls has helped in reducing the overcrowded classes and eased access to proper sanitation. Enrolment in these schools has increased from 11,481 to 13,023 for all (13%) for all students with 14% increase for girls. Attendance rates also jumped from 71.88% to 81.83%.

List of schools (Project B1-22 a)

| No | Governorate | District | Sub dis/village | School Name | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Al Muthana | Al Samawa | Al-Samawa | Al Kheer | Completed |
| 2 | Al Muthana | Al Samawa | Al-Samawa | Al Salam | Completed |
| 3 | Al Muthana | Al Rumaitha | Al-Rumaitha | Bilat Al Shuhadaa' | 55% |
| 4 | Al Muthana | Al Rumaitha | Al-Rumaitha | Muhammadia | 90% |
| 5 | Al Muthana | Al Rumaitha | Al-Rumaitha | Al Adala | 82% |
| 6 | Al Muthana | Al Rumaitha | Al-Rumaitha | Al Khansa' | 85% |
| 7 | Babil | Hilla | Hilla | Al Rasool | Completed |
| 8 | Babil | Hilla | Hilla | Al Tatbekat | Completed |
| 9 | Babil | Hilla | Hilla | Ma'rifa | Completed |
| 10 | Babil | Hilla | Hilla | Al Addil | 75% |
| 11 | Babil | Hilla | Hilla | Al Emam Al Husain | Completed |
| 12 | Babil | Hilla | Hilla | Al Qabas | Completed |
| 13 | Baghdad | Al Resafa | Al Resafa | Al Ardun | Completed |
| 14 | Baghdad | Al Resafa | Al Resafa | Al Aqoli | Completed |
| 15 | Baghdad | Al Resafa | Al Resafa | Al In Bi'aath | Completed |
| 16 | Baghdad | Al Resafa | Al Resafa | Darb Al Shahada' | Completed |
| 17 | Baghdad | Taji | Seder City | Muslim Bin A'qeel/ AL Thahi Al Arabi | Completed |
| 18 | Baghdad | Al Resafa | Al Resafa | Al Shaheed Adil Nasir/ Wadi Al Thahab | Completed |
| 19 | Baghdad | Taji | Karkh | Ahwaz | Completed |
| 20 | Baghdad | Taji | Karkh | Saeed Bn Al Museeb | Completed |
| 21 | Baghdad | Al Resafa | Al Resafa | Al Ihsan | Completed |
| 22 | Baghdad | Al Resafa | Al Resafa | Al Khalij Al Arabi | Completed |
| 23 | Baghdad | Al Resafa | Al Resafa | Al Talai | Completed |
| 24 | Baghdad | Al Resafa | Al Resafa | Al Nasriya | Completed |
| 25 | Baghdad | Al Resafa | Al Resafa | Al Rifa' | Completed |
| 26 | Diala | Ba'quba | Ba'quba | Al Qurna | Completed |
| 27 | Diala | Ba'quba | Ba'quba | Abu Al Ataheyah | Completed |
| 28 | Diala | Ba'quba | Ba'quba | Al Hera | Completed |
| 29 | Diala | Baladrooz | Baladrooz | Al Kifel | Completed |
| 30 | Diala | Khanaqeen | Khanaqin | Makarm Al Akhlaq | Completed |
| 31 | Dohuk | Dahuk | Dahuk | Beshbooreen(Payman) | Completed |
| 32 | Dohuk | Dahuk | Dahuk | Rezan | Completed |
| 33 | Dohuk | Dahuk | Deralok | Shiladze | Completed |
| 34 | Dohuk | Dahuk | Dahuk | Sararm | Completed |
| 35 | Dohuk | Sumel | Sumel | Sharva | Completed |
| 36 | Erbil | Koisanjaq | center | Kurdistan | Completed |
| 37 | Erbil | Koisanjaq | center | Nazanin | Completed |
| 38 | Erbil | Choman | Erbil | Qasrey | Completed |
| 39 | Erbil | Choman | Choman | Razan | Completed |
| 40 | Erbil | Choman | Erbil | Shirkwa | Completed |
| 41 | Erbil | Choman | Choman | Rostey | Completed |
| 42 | Erbil | Choman | Erbil | Smailawa | Completed |
| 43 | Erbil | Choman | Choman | Smilan | Completed |
| 44 | Kerbala | Al Hindiya | Al-Hindiya | Al Entisar | 93% |
| 45 | Kerbala | Al Hindiya | Al-Hindiya | Al Sayab | 96% |
| 46 | Kerbala | Karbala | Al-Hindiya | Um Al Kura | 96% |
| 47 | Kerbala | Karbala | Kerbala | Al Hadba'a | 95% |
| 48 | Kerbala | Karbala | Kerbala | Al Sayida Nafisa | 96% |
| 49 | Kerbala | Karbala | Kerbala | Al Ghranada | 95% |
| 50 | Tamim | Kirkuk | Kirkuk | Al Khalidya | Completed |
| 51 | Tamim | Kirkuk | Kirkuk | Al Ma'rifa' | Completed |
| 52 | Tamim | Kirkuk | Kirkuk | Al Mutawakel | Completed |
| 53 | Tamim | Kirkuk | Kirkuk | Jerdee Peroz | Completed |
| 54 | Tamim | Kirkuk | Kirkuk | Khabat | Completed |
| 55 | Tamim | Kirkuk | Kirkuk | Al Rezgaree | Completed |
| 56 | Tamim | Kirkuk | Al Waseti | Rouz Awah | Completed |
| 57 | Tamim | Kirkuk | Wahed huzairan | Al Nabi Younis | Completed |
| 58 | Tamim | Kirkuk | Wahed huzairan | Al Aqa’ad | Completed |
| 59 | Tamim | Kirkuk | Wahed huzairan | Al Shaheed Qasim Khadim | Completed |
| 60 | Tamim | Kirkuk | Sahat Al Umal | Mohammad Sadiq | Completed |
| 61 | Tamim | Kirkuk | Khasa | Al Watan | Completed |
| 62 | Tamim | Kirkuk | Khasa | Al Rafedeen | Completed |
| 63 | Tamim | Kirkuk | Sahat Al Tairan | Hure'at | Completed |
| 64 | Tamim | Kirkuk | Almas | Anstans Al Karmaly | Completed |
| 65 | Tamim | Kirkuk | Sahat Al Tairan | Mishkhel | Completed |
| 66 | Najaf | Najaf | Najaf | Al Shaimaa | Completed |
| 67 | Najaf | Najaf | Najaf | Al Taaef | Completed |
| 68 | Najaf | Najaf | Najaf | Saa’d bin jouber | Completed |
| 69 | Najaf | Najaf | Najaf | Al Ansaf | Completed |
| 70 | Najaf | Najaf | Najaf | Al Nahdha | Completed |
| 71 | Najaf | Kufa | Kufa | Al Ezdihar | Completed |
| 72 | Nenivah | Mosul | Mosul | Hafsah | Completed |
| 73 | Nenivah | Mosul | Mosul | Al Jomhoreyaih | Completed |
| 74 | Nenivah | Mosul | Mosul | Saqar Quraish | 50% |
| 75 | Nenivah | Mosul | Mosul | Al Waleed | Completed |
| 76 | Nenivah | Mosul | Mosul | Dar Al Salam | Completed |
| 77 | Nenivah | Mosul | Mosul | Al Hadi | 80% |
| 78 | Nenivah | Aqre | Akre | Devery | Completed |
| 79 | Qadisya | Al Shamiya | center | Manar | Completed |
| 80 | Qadisya | Al Shamiya | Al-Shamiya | Risafi | Completed |
| 81 | Qadisya | Al Shamiya | center | Shama'el | Completed |
| 82 | Qadisya | Dewania | Diwaniya | 14 Tamooz | Completed |
| 83 | Qadisya | Afaq | Afaq | Al Ukdah | Completed |
| 84 | Qadisya | Dewania | Al-Hawiga | Haifa | Completed |
| 85 | Salaheldin | Tooz | Tooz | Al Ghzali | Completed |
| 86 | Salaheldin | Tooz | Tooz | Al Shula'a | Completed |
| 87 | Salaheldin | Tooz | Tooz | Al Wathba | Completed |
| 88 | Salaheldin | Al Faris | center | Al Basma | Completed |
| 89 | Salaheldin | Al Faris | center | Al Bayraq | Completed |
| 90 | Salaheldin | Al Faris | center | Ja'far Al Sadiq | Completed |
| 91 | Sulaimaniyah | Halabja | Halabja | Harez | Completed |
| 92 | Sulaimaniyah | Sulaimania | Sulaymaniya | Kalakn | Completed |
| 93 | Sulaimaniyah | Sulaimania | Sulaymaniya | Waluba | Completed |
| 94 | Sulaimaniyah | Raniya | Rania | Titoka | Completed |
| 95 | Wasit | Al Nu'maniya | Al-Na'maniya | Al Dar Al Baydhaa | Completed |
| 96 | Wasit | Al Suwaira | Al-Suwaira | Al Qadsiya | Completed |
| 97 | Wasit | Al Nu'maniya | Al-Na'maniya | Sumar | Completed |
| 98 | Wasit | Kut | Kut | Al Bara'em | Completed |
| 99 | Wasit | Kut | Kut | Al Ifa | Completed |
| 100 | Wasit | Kut | Kut | Al Shumookh | Completed |
| 101 | Wasit | Kut | Kut | Al Farooq | Completed |
| 102 | Wasit | Kut | Kut | Ishtar | Completed |
| 103 | Wasit | Kut | Kut | Al Khalida | Completed |

List of schools (Project B1-22 b)

| No | Governorate | District | School | Status |
| --- | --- | --- | --- | --- |
| 1 | Basra | Al-Zubair center | Al-Tabaree (P) | completed |
| 2 | Basra | Al-Qurna Al-Sharsh | Al-Farazdaq (S) | completed |
| 3 | Basra | Al-Zubair Al-Shuiba | Ajnadeen (P) | completed |
| 4 | Basra | Basrah center Ashar | Al-Hadbaa (p) | completed |
| 5 | Basra | Al-Magel Qtr; Al-Hadi Hay | Al-Fettawa (I) | completed |
| 6 | Basra | Al-Magel Qtr; Al-Hadi Hay | Shuhadaa Al-Intifadaa Industrial (S) | completed |
| 7 | Basra | Al-Zubair; Al-Burjisiah Area; Al-Kartiat | Al-Furqan (P) | completed |
| 8 | Basra | Al-Zubair; Al-Burjisiah Area; Factories Region | Al-Burjisiah (P) | completed |
| 9 | Basra | Safwan; South Najemi Farms | Beni Hashim (P) | completed |
| 10 | Basra | Tewasah Hay | Al-Arqam (P) | completed |
| 11 | Basra | Al-Saai hay | Ibn Khaldoon (P) | completed |
| 12 | Basra | Zubair; Mahalt Al-Arab | Fatama Bint Al-Rasool (P) | completed |
| 13 | Basra | Basrah Center; Al-Hadi | Hutten (P) | completed |
| 14 | Basra | Al-Faw; Northern Faw | Al-Faw (S) | completed |
| 15 | Thiqar | Nassiriya; Thawra Hay | Maka Al-Mukarama (P) | completed |
| 16 | Thiqar | Al-Qal'a; Albo Ali Village | Al-Nahrawan (P) | completed |
| 17 | Thiqar | Nassiriya Ur Company Residential Complex | Al-Ghasasinah (P) | completed |
| 18 | Thiqar | Nassiriya Mouannis Village | Al-Adab (p) | completed |
| 19 | Thiqar | Al-Nassiriya ; Al-Saray Hay | Al-Talee'a (I) | completed |
| 20 | Thiqar | Al-Nassiriya; Sumir Hay | Amir Salim (K) | completed |
| 21 | Thiqar | Al-Nassiriya; Shuhadda Hay | Ghazwat Haneen (P) | completed |
| 22 | Thiqar | Al-Nassiriya; Shuhadda Hay | Abdulla Bin Khabab (P) | completed |
| 23 | Thiqar | Al-Nassiriya; Al-Tadhehiya Hay | Habib Bin Madhaher (P) | completed |
| 24 | Thiqar | Al-Nassiriya; Ur Hay | Al-Hikma (P) | completed |
| 25 | Thiqar | Al-Nassiriya; Ur Hay | Al-Meseera (P) | completed |
| 26 | Thiqar | Al-Nassiriya; Al-Sader Hay | Ibn Majed (P) | completed |
| 27 | Thiqar | Al-Nassiriya; Aredu Hay | Thi Al-Noon (P) | completed |
| 28 | Thiqar | Al-Nassiriya; Al-Sader Hay | Haber Al-Emmah (P) | completed |
| 29 | Thiqar | Al-Shatra; Al-Hawi Village. | Aswan (P) | completed |
| 30 | Thiqar | Al-Bat-ha'a | Al-Bat-Ha'a (S) | completed |
| 31 | Missan | Aummara; Jedada | Ibn Al-Nafees (P) | completed |
| 32 | Missan | Aummara; Al-Hussain Old Haee | Al-Fateh Al-Arabi (P) | completed |
| 33 | Missan | Aummara; Al-Risala Haee | Al-Warkaa (P) | completed |
| 34 | Missan | Aummara; Al-Askari Haee | Um Al-Baneen (P) | completed |
| 35 | Missan | Koumit | Al-Thaqeleen (P) | completed |
| 36 | Missan | Ali Al-Gharbi | Al-Hassaneen (P) | completed |
| 37 | Missan | Aummara; Al-Magharba Haee | Al-Yamama (P) | completed |
| 38 | Missan | Aummara; Al-Qadissiya Haee | Al-Beraq (P) | completed |
| 39 | Missan | Aummara; Al-Dibassat Haee | Asmaa (P) | completed |
| 40 | Missan | Aummara; Al-Moaalmeen New Haee | Bint Al-Hodaa (S) | completed |
| 41 | Missan | Aummara; Al-Amel Haee | Al-Emam Al-Sadeq (P) | completed |
| 42 | Missan | Aummara; Al-Jedada | Al-Tahreer (S) | completed |
| 43 | Missan | Aummara; Al-Magharba Haee | Al-Ghazali (P) | completed |
| 44 | Missan | Aummara; Al-Moaalmeen New Haee | Dejalah (S) | completed |
| 45 | Missan | Al-Mosherah | Al-Farooq (P) | completed |
| 46 | Missan | Aummara; Al-Rawaba Haee | Ghareeb Karbala (P) | completed |
| 47 | Missan | Al-Mamona; Al-Qodes | Al-Emam Mossa Al-Kadhem (P) | completed |
| 48 | Missan | Al-Mujer; Al-Qadissiya | Al-Naser (S) | completed |
| 49 | Missan | Aummara; Al-Qataa Haee | Janeen (P) | completed |
| 50 | Missan | Aummara; Al-Qataa Haee | Al-Ghosoon (P) | completed |
| 51 | Missan | Aummara; Al-Qahera Haee | Qahera (P) | completed |
| 52 | Missan | Aummara; Al-Thawra | Al-Hawraa (P) | completed |
| 53 | Missan | Aummara; Al-Qataa Haee | Al-Yamama (S) | completed |
| 54 | Missan | Aummara; Abo Rummanah Haee | Al-Shaheed Mohamed Baqer Al-Sader (P) | completed |
| 55 | Missan | Al-Mosherah | Al-Moshreh (S) | completed |
| 56 | Missan | Al-Mosherah | Al-Hadebaa (K) | completed |
| 57 | Missan | Aummara; Al-Zuzoot Haee | Al-Jawaheri (P) | completed |
| 58 | Missan | Al-Mamona; Al-Hussainiya | Al-Ameen (P) | completed |
| 59 | Missan | Aummara; Saad Haee | Yareb (P) | completed |
| 60 | Missan | Aummara; Al-Majediya | Al-Emam Al-Hussain (P) | completed |
| 61 | Missan | Aummara; Al-Thawra | Al-Zaheraa (P) | completed |
| 62 | Missan | Aummara; Al-Amarat | Ibraheem Al-Khaleel (P) | completed |
| 63 | Missan | Qalaat Saleh (S) | Qalaat Saleh (S) | Completed |
| 64 | Missan | Aummara; Baghdad Road | Al-Awali (P) | Completed |
| 65 | Missan | Aummara; Al-Askari Haee | Al-Rasool (S) | completed |
| 66 | Missan | Aummara; Al-Askari Haee | Al-Thagher (P) | completed |
| 67 | Missan | Qalaat Saleh Al-Ghadeer Haee | Al-Naaman (P) | completed |
| 68 | Missan | Qalaat Saleh | Al-Rayaheen (K) | completed |
| 69 | Missan | Koumit | Al-Shamael (K) | completed |
| 70 | Missan | Ali Al-Gharbi | Al-Maali (K) | completed |