# United Nations Development Group Iraq Trust Fund

# Project #:B1-22(a+b)

# Date and Quarter Updated: 30 September 2008 (3rd quarter)

# Part One: Summary

| Participating UN Organisation: UNICEF and UNHABITAT | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: |

| Title | School rehabilitation and capacity building for school maintenance |
| --- | --- |
| Geographic Location | 18 governorates (later Anbar was removed, therefore the geographic location became 17 governorates as per the list attached) |
| Project Cost | UNICEF US$ 9, 029,120 and UNHABITAT US$ 6, 631,818 |
| Duration | 24 months [1st extension: 29 months (approved)] |
| Approval Date (SC) | 16 Jul 2006 | Starting Date | 24 Jul 2006 | Completion Date | Original: 24 Jan 2008 1st Extension (approved): 30 June 2008 (2nd Extension till 31 Mar 2009 will be submitted soon) |
| Project Description | The project will support the rehabilitation of 160 schools in 18 Iraqi Governorates (90 schools in 15 governorates by UNICEF; 70 schools in 3 governorates by UNHABITAT), as well as capacity building for school maintenance and School Sanitation and Hygiene Education. The project will be implemented in 2 phases. |

# Development Goal and Immediate Objectives

Goal: The main objective of the project is to increase access to primary, intermediate and secondary education for school age children (grades 1 to 12) with emphasis on rural areas and girls’ education, and enhance the capacity of Directorates of Education (DoEs) on school maintenance and school sanitation and hygiene promotion. Objectives: 1. Improvement of physical environment of 160 schools in 18 governorates, including water and sanitation (WES) facilities. 2. Enhance the capacity of DoEs to undertake the maintenance of schools and promote hygiene practices. 3-Reduce the number of shifts as well as the number of students in crowded classrooms by adding new classrooms. 4-Building capacity of local contractors under several categories and using local material, which will improve economical conditions of local communities. 5-Reduce unemployment in local remote communities.

# Outputs, Key activities and Procurement

| Outputs | Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children Train 55 DoE technical staff, 160 head teachers and 320 Parent Teacher Association (PTA) representatives of the rehabilitated schools on best practices in school maintenance (including use of public-private partnerships) and on promotion of improved sanitation and hygiene practices in schools. Develop a manual on management of school building and maintenance and guidelines on school sanitation and hygiene practices. |
| --- | --- |
| Activities | Contracting about 100 local Iraqi contractors for implementing the comprehensive rehabilitation of 160 schools in 18 governorates. Hiring engineers/monitors to provide technical assistance and to undertake the monitoring of rehabilitation activities. Engage International and Iraqi consultants to conduct training workshops and to work with UN and Ministry of Education (MoE)/DoE staff in developing manuals and guidelines on school maintenance and school sanitation and hygiene practices, including an information dissemination programme to promote awareness among students, parents and teachers on these practices. |
| Procurement (major items) | None |

# Part Two:

# UNICEF

| Funds Committed | $ 9,008,134.5 | % of approved | 99.7 % |
| --- | --- | --- | --- |
| Funds Disbursed | $ 8,645,425.3 | % of approved | 95.7% |
| Forecast final date | March 2009 | Delay (months) | 9 months |

UN-HABITAT

| Funds Committed | $6,439,173 | % of approved | 97 % |
| --- | --- | --- | --- |
| Funds Disbursed | $6,177,735 | % of approved | 93 % |
| Forecast final date | June 2008 | Delay (months) | 0 |

# Quantitative achievements against objectives and results

| Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children. [The plan was changed as reported in the right] | The original plan was to rehabilitate 160 schools in the 18 governorates (90 schools in 15 governorates by UNICEF; 70 schools in 3 governorates by UNHABITAT). In October 2006, rehabilitation of the 6 schools in Anbar was shifted to 6 schools in Baghdad based on the request from the MoE due to insecurity in Anbar. Those schools were later included in the schools to be rehabilitated under another ITF project (B1-29). In December 2006, 2 schools in Ninevah near a US base were attacked by insurgents while rehabilitation was ongoing, and the rehabilitation work froze; despite several attempts made by all stakeholders to push the completion of the two schools, prevailing insecurity in the governorate prevented the contractor from resuming rehabilitation. Eventually, in January 2008, the DoE in Ninevah requested that the balance of funds planned for the comprehensive rehabilitation of the two schools be used for the construction of additional classrooms in other two schools covered by this project. In January 2008, the request for extension of the project (till 30 June 2008) was submitted, and was approved by the ITF in the same month. Meanwhile, rehabilitation of 13 schools (3 schools in Wasit for comprehensive rehabilitation; 10 schools in Kirkuk for WES rehabilitation) was additionally included in this project based on the requests from the DoEs of Kirkuk and Wasit. The changes mentioned above brought the number of schools to be rehabilitated by UNICEF from 90 (comprehensive) to 103 (93 comprehensive; 10 WES). By the end of June 2008, comprehensive rehabilitation of 157 (87 UNICEF and 70 UNHABITAT) schools and rehabilitation of WES facilities in 10 schools was completed. The project will benefit around 104,000 students and teachers (including guest schools using the buildings). During the reporting period, there was no school completed. | % of planned | 104% |
| --- | --- | --- | --- |
| Train 55 DoE technical staff, 160 head teachers and 320 PTA representatives of the rehabilitated schools on best practices in school maintenance (including use of public-private partnerships) and on the promotion of improved sanitation and hygiene practices in schools. | 459 teachers and head masters received training on school sanitation, Avian Influenza, HIV/AIDS and Cholera. Reprinting of 3,000 School Sanitation and Hygiene manuals in Kurdish was completed; 3,000 copies of the manual in Arabic will be printed soon. Training of 55 technical staff (Baghdad & KRG) on school maintenance will take place as soon as the manual is finalized / approved by the MoE, hopefully in the last quarter of 2008. | % of planned | 95% |
| Develop a manual on management of school building and maintenance and guidelines on school sanitation and hygiene practices. | Following previous workshops held in June 2007, UNICEF and MoE officials held a meeting in Amman in October 2007 and agreed that MoE would develop a school maintenance manual with UNICEF financial support in 2008. A draft manual was developed during the reporting period and is being translated from Arabic to English. | % of planned | 60% |

# Qualitative achievements against objectives and results

Post rehabilitation data collected from 24 schools (out of 56 completed in 2007) reveal that the improved environment is having a positive contribution towards the achievements of project objectives. The construction of 80 new classrooms and 122 additional toilets for girls has helped in reducing overcrowding in classrooms and improved access to proper sanitation. Enrolment in these schools has increased from 11,481 to 13,023 (13%) for all students, with 14% increase for girls. Attendance rates also jumped from 71.88% to 81.83%.

List of schools (Project B1-22 a)

| No | Governorate | District (HIC) | Sub dis-village | School Name | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Wasit | Al Nu'maniya | Al-Na'maniya | Al Dar Al Baydhaa | Completed |
| 2 | Wasit | Al Suwaira | Al-Suwaira | Al Qadsiya | Completed |
| 3 | Wasit | Al Nu'maniya | Al-Na'maniya | Sumar | Completed |
| 4 | Wasit | Kut | Kut | Al Bara'em | Completed |
| 5 | Wasit | Kut | Kut | Al Shumookh | Completed |
| 6 | Wasit | Kut | Kut | Al Ifa | Completed |
| 7 | Wasit | Kut | Kut | Al Farooq | Completed |
| 8 | Wasit | Kut | Kut | Ishtar | Completed |
| 9 | Wasit | Kut | Kut | Al Khalida | Completed |
| 10 | Kirkuk | Kirkuk | Kirkuk | Jerdee Peroz | Completed |
| 11 | Kirkuk | Kirkuk | Kirkuk | Khabat | Completed |
| 12 | Kirkuk | Kirkuk | Kirkuk | Al Rezgaree | Completed |
| 13 | Kirkuk | Kirkuk | Kirkuk | Al Khalidya | Completed |
| 14 | Kirkuk | Kirkuk | Kirkuk | Al Ma'rifa' | Completed |
| 15 | Kirkuk | Kirkuk | Kirkuk | Al Mutawakel | Completed |
| 16 | Kirkuk | Kirkuk | Al Waseti | Rouz Awah | Completed |
| 17 | Kirkuk | Kirkuk | Wahed huzairan | Al Nabi Younis | Completed |
| 18 | Kirkuk | Kirkuk | Wahed huzairan | Al Aqa’ad | Completed |
| 19 | Kirkuk | Kirkuk | Wahed huzairan | Al Shaheed Qasim Khadim | Completed |
| 20 | Kirkuk | Kirkuk | Sahat Al Umal | Mohammad Sadiq | Completed |
| 21 | Kirkuk | Kirkuk | Khasa | Al Watan | Completed |
| 22 | Kirkuk | Kirkuk | Khasa | Al Rafedeen | Completed |
| 23 | Kirkuk | Kirkuk | Sahat Al Tairan | Hure'at | Completed |
| 24 | Kirkuk | Kirkuk | Almas | Anstans Al Karmaly | Completed |
| 25 | Kirkuk | Kirkuk | Sahat Al Tairan | Mishkhel | Completed |
| 26 | Suleimaniyah | Koisanjaq | centre | Kurdistan | Completed |
| 27 | Suleimaniyah | Koisanjaq | centre | Nazanin | Completed |
| 28 | Suleimaniyah | Halabja | Halabja | Harez | Completed |
| 29 | Suleimaniyah | Sulaimania | Sulaymaniya | Kalakn | Completed |
| 30 | Suleimaniyah | Sulaimania | Sulaymaniya | Waluba | Completed |
| 31 | Suleimaniyah | Raniya | Rania | Titoka | Completed |
| 32 | Salaheldin | Tooz | Tooz | Al Ghzali | Completed |
| 33 | Salaheldin | Tooz | Tooz | Al Shula'a | Completed |
| 34 | Salaheldin | Tooz | Tooz | Al Wathba | Completed |
| 35 | Salaheldin | Al Faris | centre | Al Basma | Completed |
| 36 | Salaheldin | Al Faris | centre | Al Bayraq | Completed |
| 37 | Salaheldin | Al Faris | centre | Ja'far Al Sadiq | Completed |
| 38 | Qadissiyah | Al Shamiya | centre | Shama'el | Completed |
| 39 | Qadissiyah | Al Shamiya | centre | Manar | Completed |
| 40 | Qadissiyah | Al Shamiya | Al-Shamiya | Risafi | Completed |
| 41 | Qadissiyah | Dewania | Diwaniya | 14 Tamooz | Completed |
| 42 | Qadissiyah | Afaq | Afaq | Al Ukdah | Completed |
| 43 | Qadissiyah | Dewania | Al-Hawiga | Haifa | Completed |
| 44 | Ninevah | Mosul | Mosul | Dar Al Salam | Completed |
| 45 | Ninevah | Mosul | Mosul | Al Jomhoreyaih | Completed |
| 46 | Ninevah | Mosul | Mosul | Hafsah | Completed |
| 47 | Ninevah | Mosul | Mosul | Al Waleed | Completed |
| 48 | Ninevah | Mosul | Mosul | Saqar Quraish | 50% |
| 49 | Ninevah | Mosul | Mosul | Al Hadi | 80% |
| 50 | Najaf | Najaf | Najaf | Al Shaimaa | Completed |
| 51 | Najaf | Najaf | Najaf | Al Taaef | Completed |
| 52 | Najaf | Najaf | Najaf | Saa’d bin jouber | Completed |
| 53 | Najaf | Najaf | Najaf | Al Ansaf | Completed |
| 54 | Najaf | Najaf | Najaf | Al Nahdha | Completed |
| 55 | Najaf | Kufa | Kufa | Al Ezdihar | Completed |
| 56 | Kerbala | Al Hindiya | Al-Hindiya | Al Entisar | Completed |
| 57 | Kerbala | Al Hindiya | Al-Hindiya | Al Sayab | Completed |
| 58 | Kerbala | Karbala | Al-Hindiya | Um Al Kura | Completed |
| 59 | Kerbala | Karbala | Kerbala | Al Hadba'a | Completed |
| 60 | Kerbala | Karbala | Kerbala | Al Sayida Nafisa | Completed |
| 61 | Kerbala | Karbala | Kerbala | Al Ghranada | Completed |
| 62 | Erbil | Choman | Erbil | Smailawa | Completed |
| 63 | Erbil | Choman | Choman | Smilan | Completed |
| 64 | Erbil | Choman | Choman | Rostey | Completed |
| 65 | Erbil | Choman | Erbil | Qasrey | Completed |
| 66 | Erbil | Choman | Choman | Razan/Meehraban | Completed |
| 67 | Erbil | Choman | Erbil | Shirkwa | Completed |
| 68 | Dohuk | Dahuk | Dahuk | Beshbooreen(Payman) | Completed |
| 69 | Dohuk | Dahuk | Dahuk | Rezan | Completed |
| 70 | Dohuk | Dahuk | Deralok | Shiladze | Completed |
| 71 | Dohuk | Sumel | Sumel | Sharya | Completed |
| 72 | Dohuk | Aqre | Akre | Devery | Completed |
| 73 | Dohuk | Dahuk | Dahuk | Sararm | Completed |
| 74 | Diyala | Ba'quba | Ba'quba | Abu Al Ataheyah | Completed |
| 75 | Diyala | Ba'quba | Ba'quba | Al Hera | Completed |
| 76 | Diyala | Baladrooz | Baladrooz | Al Kifel | Completed |
| 77 | Diyala | Khanaqeen | Khanaqin | Makarm Al Akhlaq | Completed |
| 78 | Diyala | Ba'quba | Ba'quba | Al Qurna | Completed |
| 79 | Baghdad | Taji | Karkh 3 | Al Ahwaz | Completed |
| 80 | Baghdad | Taji | Karkh 3 | Saeed Bn Al Museeb | Completed |
| 81 | Baghdad | Al Resafa | Al Resafa 3 | Al In Bi'aath | Completed |
| 82 | Baghdad | Al Resafa | Al Resafa 3 | Darb Al Shahada' | Completed |
| 83 | Baghdad | Taji | Al Resafa 2 | Muslim Bin A'qeel- AL Thair Al Arabi | Completed |
| 84 | Baghdad | Al Resafa | Al Resafa 1 | Al Shaheed Adil Nasir- Wadi Al Thahab | Completed |
| 85 | Baghdad | Al Resafa | Al Resafa 1 | Al Aqoli | Completed |
| 86 | Baghdad | Al Resafa | Al Resafa 1 | Al Ardun | Completed |
| 87 | Baghdad | Al Resafa | Al Resafa 2 | Al Rifa' | Completed |
| 88 | Baghdad | Al Resafa | Al Resafa 2 | Al Ihsan | Completed |
| 89 | Baghdad | Al Resafa | Al Resafa 2 | Al Khalij Al Arabi | Completed |
| 90 | Baghdad | Al Resafa | Al Resafa 2 | Al Nasriya | Completed |
| 91 | Baghdad | Al Resafa | Al Resafa 2 | Al Talai | Completed |
| 92 | Babil | Hilla | Hilla | Al Rasool | Completed |
| 93 | Babil | Hilla | Hilla | Al Tatbekat | Completed |
| 94 | Babil | Hilla | Hilla | Ma'rifa | Completed |
| 95 | Babil | Hilla | Hilla | Al Addil | Completed |
| 96 | Babil | Hilla | Hilla | Al Emam Al Husain | Completed |
| 97 | Babil | Hilla | Hilla | Al Qabas | Completed |
| 98 | Al Muthanna | Al Samawa | Al-Samawa | Al Kheer | Completed |
| 99 | Al Muthanna | Al Samawa | Al-Samawa | Al Salam | Completed |
| 100 | Al Muthanna | Al Rumaitha | Al-Rumaitha | Bilat Al Shuhadaa' | 54% |
| 101 | Al Muthanna | Al Rumaitha | Al-Rumaitha | Muhammadia | 88% |
| 102 | Al Muthanna | Al Rumaitha | Al-Rumaitha | Al Adala | 83% |
| 103 | Al Muthanna | Al Rumaitha | Al-Rumaitha | Al Khansa' | 84% |

List of schools (Project B1-22 b)

| No | Governorate | District | School | Status |
| --- | --- | --- | --- | --- |
| 1 | Basra | Al-Zubair centre | Al-Tabaree (P) | Completed |
| 2 | Basra | Al-Qurna Al-Sharsh | Al-Farazdaq (S) | Completed |
| 3 | Basra | Al-Zubair Al-Shuiba | Ajnadeen (P) | Completed |
| 4 | Basra | Basrah centre Ashar | Al-Hadbaa (p) | Completed |
| 5 | Basra | Al-Magel Qtr; Al-Hadi Hay | Al-Fettawa (I) | Completed |
| 6 | Basra | Al-Magel Qtr; Al-Hadi Hay | Shuhadaa Al-Intifadaa Industrial (S) | Completed |
| 7 | Basra | Al-Zubair; Al-Burjisiah Area; Al-Kartiat | Al-Furqan (P) | Completed |
| 8 | Basra | Al-Zubair; Al-Burjisiah Area; Factories Region | Al-Burjisiah (P) | Completed |
| 9 | Basra | Safwan; South Najemi Farms | Beni Hashim (P) | Completed |
| 10 | Basra | Tewasah Hay | Al-Arqam (P) | Completed |
| 11 | Basra | Al-Saai hay | Ibn Khaldoon (P) | Completed |
| 12 | Basra | Zubair; Mahalt Al-Arab | Fatama Bint Al-Rasool (P) | Completed |
| 13 | Basra | Basrah Centre; Al-Hadi | Hutten (P) | Completed |
| 14 | Basra | Al-Faw; Northern Faw | Al-Faw (S) | Completed |
| 15 | Thiqar | Nassiriya; Thawra Hay | Maka Al-Mukarama (P) | Completed |
| 16 | Thiqar | Al-Qal'a; Albo Ali Village | Al-Nahrawan (P) | Completed |
| 17 | Thiqar | Nassiriya Ur Company Residential Complex | Al-Ghasasinah (P) | Completed |
| 18 | Thiqar | Nassiriya Mouannis Village | Al-Adab (p) | Completed |
| 19 | Thiqar | Al-Nassiriya ; Al-Saray Hay | Al-Talee'a (I) | Completed |
| 20 | Thiqar | Al-Nassiriya; Sumir Hay | Amir Salim (K) | Completed |
| 21 | Thiqar | Al-Nassiriya; Shuhadda Hay | Ghazwat Haneen (P) | Completed |
| 22 | Thiqar | Al-Nassiriya; Shuhadda Hay | Abdulla Bin Khabab (P) | Completed |
| 23 | Thiqar | Al-Nassiriya; Al-Tadhehiya Hay | Habib Bin Madhaher (P) | Completed |
| 24 | Thiqar | Al-Nassiriya; Ur Hay | Al-Hikma (P) | Completed |
| 25 | Thiqar | Al-Nassiriya; Ur Hay | Al-Meseera (P) | Completed |
| 26 | Thiqar | Al-Nassiriya; Al-Sader Hay | Ibn Majed (P) | Completed |
| 27 | Thiqar | Al-Nassiriya; Aredu Hay | Thi Al-Noon (P) | Completed |
| 28 | Thiqar | Al-Nassiriya; Al-Sader Hay | Haber Al-Emmah (P) | Completed |
| 29 | Thiqar | Al-Shatra; Al-Hawi Village. | Aswan (P) | Completed |
| 30 | Thiqar | Al-Bat-ha'a | Al-Bat-Ha'a (S) | Completed |
| 31 | Missan | Aummara; Jedada | Ibn Al-Nafees (P) | Completed |
| 32 | Missan | Aummara; Al-Hussain Old Haee | Al-Fateh Al-Arabi (P) | Completed |
| 33 | Missan | Aummara; Al-Risala Haee | Al-Warkaa (P) | Completed |
| 34 | Missan | Aummara; Al-Askari Haee | Um Al-Baneen (P) | Completed |
| 35 | Missan | Koumit | Al-Thaqeleen (P) | Completed |
| 36 | Missan | Ali Al-Gharbi | Al-Hassaneen (P) | Completed |
| 37 | Missan | Aummara; Al-Magharba Haee | Al-Yamama (P) | Completed |
| 38 | Missan | Aummara; Al-Qadissiya Haee | Al-Beraq (P) | Completed |
| 39 | Missan | Aummara; Al-Dibassat Haee | Asmaa (P) | Completed |
| 40 | Missan | Aummara; Al-Moaalmeen New Haee | Bint Al-Hodaa (S) | Completed |
| 41 | Missan | Aummara; Al-Amel Haee | Al-Emam Al-Sadeq (P) | Completed |
| 42 | Missan | Aummara; Al-Jedada | Al-Tahreer (S) | Completed |
| 43 | Missan | Aummara; Al-Magharba Haee | Al-Ghazali (P) | Completed |
| 44 | Missan | Aummara; Al-Moaalmeen New Haee | Dejalah (S) | Completed |
| 45 | Missan | Al-Mosherah | Al-Farooq (P) | Completed |
| 46 | Missan | Aummara; Al-Rawaba Haee | Ghareeb Karbala (P) | Completed |
| 47 | Missan | Al-Mamona; Al-Qodes | Al-Emam Mossa Al-Kadhem (P) | Completed |
| 48 | Missan | Al-Mujer; Al-Qadissiya | Al-Naser (S) | Completed |
| 49 | Missan | Aummara; Al-Qataa Haee | Janeen (P) | Completed |
| 50 | Missan | Aummara; Al-Qataa Haee | Al-Ghosoon (P) | Completed |
| 51 | Missan | Aummara; Al-Qahera Haee | Qahera (P) | Completed |
| 52 | Missan | Aummara; Al-Thawra | Al-Hawraa (P) | Completed |
| 53 | Missan | Aummara; Al-Qataa Haee | Al-Yamama (S) | Completed |
| 54 | Missan | Aummara; Abo Rummanah Haee | Al-Shaheed Mohamed Baqer Al-Sader (P) | Completed |
| 55 | Missan | Al-Mosherah | Al-Moshreh (S) | Completed |
| 56 | Missan | Al-Mosherah | Al-Hadebaa (K) | Completed |
| 57 | Missan | Aummara; Al-Zuzoot Haee | Al-Jawaheri (P) | Completed |
| 58 | Missan | Al-Mamona; Al-Hussainiya | Al-Ameen (P) | Completed |
| 59 | Missan | Aummara; Saad Haee | Yareb (P) | Completed |
| 60 | Missan | Aummara; Al-Majediya | Al-Emam Al-Hussain (P) | Completed |
| 61 | Missan | Aummara; Al-Thawra | Al-Zaheraa (P) | Completed |
| 62 | Missan | Aummara; Al-Amarat | Ibraheem Al-Khaleel (P) | Completed |
| 63 | Missan | Qalaat Saleh (S) | Qalaat Saleh (S) | Completed |
| 64 | Missan | Aummara; Baghdad Road | Al-Awali (P) | Completed |
| 65 | Missan | Aummara; Al-Askari Haee | Al-Rasool (S) | Completed |
| 66 | Missan | Aummara; Al-Askari Haee | Al-Thagher (P) | Completed |
| 67 | Missan | Qalaat Saleh Al-Ghadeer Haee | Al-Naaman (P) | Completed |
| 68 | Missan | Qalaat Saleh | Al-Rayaheen (K) | Completed |
| 69 | Missan | Koumit | Al-Shamael (K) | Completed |
| 70 | Missan | Ali Al-Gharbi | Al-Maali (K) | Completed |