# United Nations Development Group Iraq Trust Fund

# Project #: B1-25

# Date and Quarter Updated: 10 January 2009, 4th Quarter October- December 2008

| Participating UN Organisation: WHO | Sector: B-Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health |

| Title | Strengthening school health services at Primary School level through implementation of the Health Promoting Schools |
| --- | --- |
| Geographic Location | All governorates The School health screening component only in 8 governorates |
| Project Cost | US$ 1,757,280 |
| Duration | 12 months |
| Approval Date (SC) | 27th February 2007 | Starting Date | April 2007 | Completion Date | -First Extension till 31 September 2008 - 2nd extension till 31 March 2009 |
| Project Description | The aim of the project is to assist the Ministries of Health and Education/ Iraq to strengthen the school health services at primary level through updating the health education concepts into school curriculum, school health screening for students for visual and hearing problems and detection of musclo-skeletal abnormalities; and to adopt school health policies which aim to create a healthy physical and psychosocial environment for all students and staff, and to make the school a model of best practice for the whole community. This proposal will build on previous achievements of WHO in this area through its core budget and under the Integrated Basic Project funded under the UNDG ITF and support the Focusing Resources Effective School Health (FRESH) initiative launched by UN partners. |

# Development Goal and Immediate Objectives

Key immediate objectives: 1- Health promoting schools programme (life skills education and psychological first aid) implemented in 46 schools in 18 governorates (2 schools in each governorate except for Baghdad governorate 12 schools in Karch and Rasafa). 2- Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children as part of the Strengthening Primary Health Care system and improve the health of students. 3- Raise awareness among communities on Health Promoting Schools initiative and the role of parent teachers’ association (PTA) meetings strengthened 4- Hearing aids and eyeglasses provided for needy students and those with musclo-skeletal abnormalities referred to specialists. 5-Effective partnerships between all stakeholders including the community to build public awareness and strengthen demand for the school health services.

# Outputs, Key activities and Procurement

| Outputs | 100 teachers and school staff trained on health promoting school initiative in 46 schools in all governorates. School health including psychological first aid services strengthened and maintained at all levels through successful coordination approaches between schools and primary health care centres. MoH officials informed about health promoting school initiative. 50 MoH health professionals trained on school health screening activities. 100 Community leaders trained on health promoting schools initiative. Health screening of randomly selected students in the 150 schools at 8 governorates completed (screening for visual, hearing problems and musclo-skeletal abnormalities). 300 teachers trained on detection of visual, hearing defects and musclo-skeletal abnormalities in 150 schools in 8 governorates involved in Health screening. Provision of eyeglasses and hearing aids to school children with visual and hearing difficulties and those with musclo skeletal abnormalities referred to specialists completed. Community committees established to build public awareness in demanding for school health services. |
| --- | --- |
| Activities | Support MoH and Ministry of Education in the implementation of the health promoting schools initiative through conducting orientation workshops for head masters, training of health professionals, teachers and health workers. Provided skill-based health education that focuses on the development of knowledge, attitude, values and life skills needed to make and act on the most appropriate and positive decision concerning health. Training of (200) teachers and health personnel working at primary health care centres on providing first aid psychological and basic mental health care for children with psychosocial problems. Minor rehabilitation for 46 PHCs close to the school sites to cater for mental health services and psychological first aid services for children and adolescents. Advocacy and communication meetings for MoH/ MoE officials and local communities on health promoting schools initiative. Training of 50 MoH health professionals on school health screening. Increasing the coordination between all sectors and establishing systems for monitoring and evaluation of HPS initiative. Training of community leaders on health promoting school initiative. Capacity building of national trainers from MoH and MOE (school health programme managers, health workers and teachers) to improve their skills on early detection of eye and ear problems, and musclo-skeletal abnormalities. 10. Training of teachers on examination of visual acuity and detection of visual errors, hearing difficulties and musclo- skeletal abnormalities. 11.Provision of supplies and equipments as audiometers, ophthalmoscopes and Snell’s charts for health screening activities at schools. Provision of eyeglasses and hearing aids to students in need. Advocacy among community and religious leaders through training and distribution of educational materials and strengthening the Parent Teachers Association (PTA) meeting |
| Procurement (major items) | Procurement of informatics delivered to MoH/School health unit for distribution to all school health units at Directorate of health at all governorates |

# Situation as of 31/12/2008

| Funds Committed | US$ 730,236.00 | % of approved | 42% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 518.545.00 | % of approved | 30% |
| Forecast final date | March 2009 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Objective (1) | Health promoting schools programme (life skills education and psychological first aid) implemented in 46 schools in 18 governorates (2 schools in each governorate except for Baghdad governorate 12 schools in (Karch and Rasafa). | 90 % of planned |  |
| --- | --- | --- | --- |
| Objective (2) | Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children as part of the Strengthening Primary Health Care system. | 80 % of planned |  |
| Objective (3) | Raise awareness among community on Health Promoting Schools initiative and the role of parent teachers association (PTA) meetings | 95 % of planned |  |
| Objective (4) | Hearing aids and eyeglasses provided for needy students and those with musclo- skeletal abnormalities referred to specialists. | 40 % of planned |  |
| Objective (5) | Effective partnerships between all stakeholders including the community to build public awareness and strengthen demand for the school health services. | 78 % of planned |  |

# Qualitative achievements against objectives and results

Training of 80 doctors and 50 teachers on health promoting school initiatives and health education. 18 national training courses for 450 doctors, technicians and teachers on examination of visual acuity to detect visual errors among students screened detection of hearing difficulties by using audiometers and examination of musclo skeletal problems. 18 national training activities were successfully for 162 doctors and 20 teachers on psychosocial support was conducted to update their knowledge on health education and key health massages, communication skills and psychological first aid services. Assessment of the environmental health situation at the 46 schools implementing the health promoting schools initiative was conducted followed by editing and data entry. Data analysis is in process. Data editing and entry of the school health screening was completed. Data analysis and report writing are in process. Three technical meeting of the members of the steering committee to review the results of the school health screening. Procurement of equipments to School health unit in each directorate of health with a total cost of USD 15,000 12 advocacy meeting for 1010 community leaders, teachers and parent teachers association were held at governorates in collaboration with DoH and DoE to raise awareness of the community on health and hygiene and the importance of participating in making the school environment a health and friendly one, 10 supervisory visits by six members of the steering committee to primary schools in Baghdad, Basrah, Theeqar, Wasit, Muthana, Mosul and Suliamaniya to follow up the implementation of the project. Monthly evaluation report is submitted by the project focal points on the progress of the implementation of the projects at governorate level besides the daily communication with MoH and MoE focal point to provide technical assistance and solutions for most of the difficulties facing the implementation process.