- United Nations Development Group Iraq Trust Fund

- Project #: B1-29 (a+b)

- Date and Quarter Updated: April - June 2009 (2nd Quarter)

| Participating UN Organisation: UNICEF (Lead Agency) and UNHABITAT | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Directorates of Education in selected governorates in close collaboration with Ministries of Education in Baghdad and Erbil |  |

| Title | School Rehabilitation and Capacity Development for Enhanced Access and Retention in Primary Education |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Governorates: Muthanna, Dohuk, Kirkuk, Missan and Najaf (Ministry of Education (MoE) letter 13146 dated 21/04/2008 requested to transfer 10 schools from Kirkuk’s share to Anbar, as per attached list) Districts: Akrey, Dohuk centre, Kirkuk centre, Daqooq, Imam Qasim, Arafa, Bikler, Al Rumatha , Al Warka, Al Siwair, Al Samawa, Al Khidher, Najaf centre , Kufa, Omara, Rumadi, Al Najmi, Kumet, Al Mymona, Dubis, Shwan, and Al Manathera. |  |  |  |  |
| Project Cost | US $11,325,596 (UNICEF US$ 7,312,914 UNHABITAT US$ 4,012,682) |  |  |  |  |
| Duration | Original: 4/Jul/07 – 4/Jul/08 (12 months) 1st Extension: 4/Jul/08 – 31/Dec/08 (18 months) 2nd Extension: 31/Dec/08 – 31/Mar/09 (21 months) 3rd Extension: 31/Mar/09 – 30/Jun/09 (24 months) 4th Extension: 30/Jun/09 – 30/Sep/09 (27 months) |  |  |  |  |
| Approval Date (SC) | 28/Jun/07 | Starting Date | 4/Jul/07 | Completion Date | Original: 4/Jul/08 1st Extension: 31/Dec/08 2nd Extension: 31/Mar/09 3rd Extension: 30/Jun/09 4th Extension: 30/Sep/09 |
| Project Description | The project aims at increasing enrolment, completion and retention in primary education, especially for girls through: rehabilitation of Water and Sanitation (WES) facilities in schools; basic rehabilitation of school buildings; provision of educational supplies; on-the-job training in classroom and school-based management for education staff through exposure to best practices in the region; increase community participation and parents' support to learning in school through reactivation of Parent–Teacher Associations (PTAs); teacher training in gender-sensitive and child-centred methods; and health and hygiene education. |  |  |  |  |

- Development Goal and Immediate Objectives

The developmental goal of the project is to demonstrably improve access to and quality of primary education and intermediate levels of education, with particular focus on girls, girls’ schools and mixed schools in 200 disadvantaged rural schools throughout Iraq. Immediate Objectives are: To upgrade 200 mixed and girls’ schools to child-friendly status; to create awareness among community and religious leaders on the importance of girls’ education and gender issues; to equip teachers with innovative teaching methods, and promote gender-sensitive attitudes; to equip principals and educational supervisors with supervisory and leadership skills; to increase parent participation through strengthening of PTAs; and to include health and hygiene activities in the school curriculum.

| - Outputs, Key activities and Procurement |  |
| --- | --- |
| Outputs | - 200 schools will be rehabilitated in 5 governorates; - 200 schools in 5 governorates will be equipped with appropriate furniture, learning materials, sanitary kits, playgrounds and safe WES facilities; - 25 education staff will be trained on multipurpose schools; - Principals of the 200 selected schools and educational supervisors will be trained in school and classroom-based management, and leadership skills and strategies; - 4 meetings of each PTA will be conducted at the 200 selected schools, e.g. addressing issues of safety and privacy of girls in schools and on their way to school; - Teachers and students will be equipped with skills to take care of their personal health and hygiene, as well as maintain a healthy school environment. |
| Activities | - Rehabilitation of WES facilities in 200 schools and repair of school buildings; - Upgrading of 200 schools through: procurement and distribution of school furniture and recreational materials; establishment of safe recreational areas; on-the-job training for 25 education staff of multipurpose schools in the Region; - Improving teaching methods, child-centred learning and gender sensitivity through: study tour and training for 25 educational staff; upgrading 5 schools to multipurpose schools; elaboration of training manuals; elaboration and printing of teaching learning materials; and exposing 200 teachers to innovative teaching methods; - Improving supervisory, management and leadership skills of principals; - Establishing and printing guidelines for PTAs and supporting the preparation and implementation of 4 meetings for each PTA; - Including health and hygiene activities in the school curriculum; procurement and distribution of sanitation kits to all selected schools; and reprinting 200 manuals for rehabilitated schools. |
| Procurement | Furniture, teaching/learning materials, sanitation kits, and recreational materials |

- UNICEF

| Funds Committed | $ 7,307,040.35 | % of approved | 99.9% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 7,049,353.15 | % of approved | 96.3% |
| Forecast final date | 30 September 2009 | Delay (months) | 15 months |

- UNHABITAT

| Funds Committed | $ 4,001,688 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 3,232,506 | % of approved | 81% |
| Forecast final date | 30 June 2009 | Delay (months) | 12 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men |  |  |
| Women |  |  |
| Children | 60,000 school children | 167.5% |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries | 200 principals; 600 teachers | 76.4% |
| Employment generation (men/women) | 100,000 man-days labours | 153% |

| - Quantitative achievements against objectives and results |  |  |  |
| --- | --- | --- | --- |
| Rehabilitation of WES facilities in 200 schools and minor repair of school buildings and playgrounds | - As of 30 June 2009, rehabilitation works for 192 schools (100 by UNHABITAT and 92 by UNICEF) were completed, providing an improved school environment to around 100,500 students (62% girls). - During the reporting period, UNHABITAT completed the rehabilitation of 23 schools, while the rehabilitation of the remaining 8 schools by UNICEF has reached 90% progress. | % of planned | 95% |
| To create awareness among community and religious leaders on the importance of girls’ education, modern teaching methodology and gender issues | - 24 staff representing MoE Baghdad and the Kurdistan Region (KR) visited Egypt and received the subject training. | % of planned | 100% |
| To equip teachers with innovative teaching methods, and promote gender-sensitive attitudes | - For 167 schools in centre/south, 441 teachers were trained on child-centred and gender-sensitive teaching methods. - For 33 schools in the KR, 16 teachers were trained on the same subject. | % of planned | 100% |
| To equip the principals and educational supervisors with supervisory and leadership skills | - 154 headmasters in centre/south and 4 in the KR were trained on the subject. | % of planned | 100% |
| Equip 200 schools with school furniture, recreational materials, sanitation kits | - The distribution of desks was completed during the reporting period. A total of 43,844 school desks have been distributed to 200 schools. | % of planned | 100% |
| Provision of teaching / learning materials to students and teachers | - 100 schools received sanitation kits, and the other 100 schools will receive the kits at the beginning of the coming school year; - 167 schools received recreational kits and the remaining 33 schools will receive the kits at the beginning of the coming school year; - The distribution of teaching / learning materials has commenced. | % of planned | 50% |
| To increase parent participation through strengthening PTAs | - Meetings were held with school administration and teachers as well as community members involved in school matters. - Partnership was established with the International Rescue Committee (IRC) to establish PTAs in 10 schools in Erbil and provide technical support to the MoE for the development of PTA guidelines and training of 100 PTA members. | % of planned | 50% |

- Qualitative achievements against objectives and results

Qualitative achievements will be assessed once the project is completed.

- Main implementation constrains & challenges (2-3 sentences)

No constraints occurred during the reporting period.

UNICEF: Summary of school rehabilitation by governorate

| Governorate | # of schools completed | Ongoing | Under bidding |
| --- | --- | --- | --- |
| Al Muthanna | 34 |  |  |
| Dohuk | 33 |  |  |
| Anbar | 10 |  |  |
| Kirkuk | 15 | 8 |  |
| Najaf | 50 |  |  |
| Missan | 50 |  |  |
| Total | 192 | 8 | 0 |

Annex 1. Names & Locations of schools (B1-29a)

| No | Governorate | District (HIC) | School Name | Status |
| --- | --- | --- | --- | --- |
| 1 | Al Muthanna | Al Rumaithah | Al Kifah | 100% |
| 2 | Al Muthanna | Al Rumaithah | Al Futowa | 100% |
| 3 | Al Muthanna | Rumaithah | Palistine | 100% |
| 4 | Al Muthanna | Al Rumaithah | Al Tahtheeb | 100% |
| 5 | Al Muthanna | Al Rumaithah | Al A'aridhiat | 100% |
| 6 | Al Muthanna | Al Samawa | Al Akha' | 100% |
| 7 | Al Muthanna | Al Samawa | Al Razi | 100% |
| 8 | Al Muthanna | Al Samawa | Al Tadhamun | 100% |
| 9 | Al Muthanna | Al Samawa | Al Numoothaj | 100% |
| 10 | Al Muthanna | Al Samawa | Haifa | 100% |
| 11 | Al Muthanna | Al Rumaithah | Al Mustansiria | 100% |
| 12 | Al Muthanna | Al Samawa | Al Sahab | 100% |
| 13 | Al Muthanna | Al Rumaithah | Al Koofa | 100% |
| 14 | Al Muthanna | Al Khidhr | Al Zawra' | 100% |
| 15 | Anbar | Ramadi | Kinda | 100% |
| 16 | Anbar | Ramadi | Al Qaba' | 100% |
| 17 | Anbar | Ramadi | Al-Bara'a Bn Malik | 100% |
| 18 | Anbar | Ramadi | Qubat Al-Sakhra | 100% |
| 19 | Anbar | Ramadi | Ukadh | 100% |
| 20 | Anbar | Ramadi | Al-Rasheed | 100% |
| 21 | Anbar | Ramadi | Al-Afah | 100% |
| 22 | Anbar | Ramadi | Al-Amjad | 100% |
| 23 | Anbar | Ramadi | IbnAl-Atheer | 100% |
| 24 | Anbar | Ramadi | Al-Junid Al-Baghdadi | 100% |
| 25 | Dohuk | Akre | Dogondan Gawre | 100% |
| 26 | Dohuk | Akre | Dogondan Bijuk | 100% |
| 27 | Dohuk | Akre | Morilan | 100% |
| 28 | Dohuk | Akre | Qaranaz | 100% |
| 29 | Dohuk | Dahuk | 11 Aylul | 100% |
| 30 | Dohuk | Dahuk | Jihan | 100% |
| 31 | Dohuk | Dahuk | Halgurd | 100% |
| 32 | Dohuk | Dahuk | Shakhke | 100% |
| 33 | Dohuk | Dahuk | Salaidin | 100% |
| 34 | Dohuk | Sumel | Davar | 100% |
| 35 | Dohuk | Sumel | Kany Arab | 100% |
| 36 | Dohuk | Zakho | Runahi | 100% |
| 37 | Dohuk | Zakho | Karez | 100% |
| 38 | Dohuk | Zakho | Halo | 100% |
| 39 | Dohuk | Dahuk | Kurdayatee | 100% |
| 40 | Dohuk | Dahuk | Halat | 100% |
| 41 | Dohuk | Dahuk | Brushky | 100% |
| 42 | Dohuk | Shekhan | Beedol | 100% |
| 43 | Dohuk | Shekhan | Balata | 100% |
| 44 | Dohuk | Akre | Bakirman | 100% |
| 45 | Dohuk | Akre | Sarderian | 100% |
| 46 | Dohuk | Akre | Zeelka Fakher | 100% |
| 47 | Dohuk | Akre | Sheekhanok | 100% |
| 48 | Dohuk | Amadiya | Kaladimdim | 100% |
| 49 | Dohuk | Amadiya | Kurezhar | 100% |
| 50 | Dohuk | Dahuk | Etot | 100% |
| 51 | Dohuk | Dahuk | 14 Adar | 100% |
| 52 | Dohuk | Dahuk | Ararat | 100% |
| 53 | Dohuk | Dahuk | Kaverke/ Parlaman/ | 100% |
| 54 | Dohuk | Dahuk | Zozik | 100% |
| 55 | Dohuk | Dahuk | Malta Zhery | 100% |
| 56 | Dohuk | Dahuk | Malta Zhory | 100% |
| 57 | Dohuk | Mangeshek | Bajid Kandal | 100% |
| 58 | Missan | Amara | Al Ahid Al-Jadeed | 100% |
| 59 | Missan | Amara | Al Sayida Zainab | 100% |
| 60 | Missan | Amara | Falistine | 100% |
| 61 | Missan | Amara | Utba Bin Ghazwan | 100% |
| 62 | Missan | Amara | Um Salama | 100% |
| 63 | Missan | Amara | Babil | 100% |
| 64 | Missan | Amara | Tarablus | 100% |
| 65 | Missan | Amara | Al Ahrar | 100% |
| 66 | Missan | Amara | Al Tahira | 100% |
| 67 | Missan | Amara | Asia | 100% |
| 68 | Missan | Amara | Al Manar | 100% |
| 69 | Missan | Amara | Abu Al Fadhil Al Abas | 100% |
| 70 | Missan | Amara | Ausama Bin Zaid | 100% |
| 71 | Missan | Amara | Missan | 100% |
| 72 | Missan | Amara | Al Hashmiya | 100% |
| 73 | Najaf | Kufa | Al Hakma | 100% |
| 74 | Najaf | Najaf | Al Efa'a | 100% |
| 75 | Najaf | Kufa | Um Salma-Um Salam | 100% |
| 76 | Najaf | Najaf | Al Muhajreen | 100% |
| 77 | Najaf | Najaf | Al Makaseb | 100% |
| 78 | Najaf | Kufa | Al Kameliya | 100% |
| 79 | Najaf | Kufa | Al Hayat | 100% |
| 80 | Najaf | Njaf | Al Maqassed | 100% |
| 81 | Najaf | Kufa | Urafat | 100% |
| 82 | Najaf | Kufa | Al Rarenjiya | 100% |
| 83 | Najaf | Kufa | Nusaiba Al Ansareya | 100% |
| 84 | Najaf | Kufa | Al Bayt Al Ateeq | 100% |
| 85 | Najaf | Kufa | That Al Nitaqayn | 100% |
| 86 | Najaf | Kufa | Al Afrah | 100% |
| 87 | Kirkuk | Kirkuk | Kal Sedrah | 100% |
| 88 | Kirkuk | Kirkuk | Naghda | 100% |
| 89 | Kirkuk | Kirkuk | Tafka | 100% |
| 90 | Kirkuk | Kirkuk | Shaheed | 100% |
| 91 | Kirkuk | Kirkuk | Bent Al Huda | 100% |
| 92 | Najaf | Najaf | Al Ferdous | 100% |
| 93 | Kirkuk | Kirkuk | Bahra | Ongoing 90% |
| 94 | Kirkuk | Kirkuk | Chirdaghlu | Ongoing 90% |
| 95 | Kirkuk | Daquq | Amir Al Mumneen | Ongoing 90% |
| 96 | Kirkuk | Kirkuk | Mukhtar Oghlo | Ongoing 90% |
| 97 | Kirkuk | Daquq | Zaen Al Abdeen | Ongoing 90% |
| 98 | Kirkuk | Daquq | Fatima | Ongoing 90% |
| 99 | Kirkuk | Kirkuk | Sara | Ongoing 90% |
| 100 | Kirkuk | Kirkuk | Al Bikler | Ongoing 90% |

Names and Locations of schools (B1-29b)

| No | Governorate | District | School | Progress |
| --- | --- | --- | --- | --- |
| 1 | Al Muthanna | Samawa / Al Suwalim | Al Mujahid | 100% |
| 2 | Al Muthanna | Samawa / Centre | Al Jumhorya | 100% |
| 3 | Al Muthanna | Samawa/ Hay Al Shaheed Al Sadir | Al Ghadeer | 100% |
| 4 | Al Muthanna | Samawa | Al Nazaha | 100% |
| 5 | Al Muthanna | Samawa | Al Zuhoor / Secondary | 100% |
| 6 | Al Muthanna | Samawa / Mamlaha | Tabarek | 100% |
| 7 | Al Muthanna | Samawa/ Al Qushla | Bint Al Huda | 100% |
| 8 | Al Muthanna | Rumaithah / Al Khawam | Toa'a | 100% |
| 9 | Al Muthanna | Rumaithah / Al Abou Hassan | Al Shatte' | 100% |
| 10 | Al Muthanna | Rumaithah/ Al Tabo | Al Qabas | 100% |
| 11 | Al Muthanna | Al Khidhr / Al Bdairy | Ali Al Akbar/ Intermediate | 100% |
| 12 | Al Muthanna | Al Khidhr/ Qatyat Al Sabia | Al Ayat | 100% |
| 13 | Al Muthanna | Al Warka'a | Al Salman | 100% |
| 14 | Al Muthanna | Al Warka'a/ Al Jirabe | Al Noor | 100% |
| 15 | Al Muthanna | Al Warka'a/ Bani Zraje | Al Dhifer/Halima | 100% |
| 16 | Al Muthanna | Al Warka'a/ Bani Zraje | Haleema Al-Sadeya | 100% |
| 17 | Al Muthanna | Al Majed | Al Majed/ Secondary | 100% |
| 18 | Al Muthanna | Al Majed | Al Dyar | 100% |
| 19 | Al Muthanna | Al Salman | Jawad Al-Aema | 100% |
| 20 | Al Muthanna | Al Suwear | Al Khaleej Al Arabi/ Secondary | 100% |
| 21 | Kirkuk | Debass/ Al Malha | Barda Qaraman | 100% |
| 22 | Kirkuk | Debass/ Mshearfa' | Goran | 100% |
| 23 | Kirkuk | Debass/ Balkana | Sarkawtn | 100% |
| 24 | Kirkuk | Kirkuk Centre/ Taba | Kalwar | 100% |
| 25 | Kirkuk | Kirkuk Centre/ Raheem Awa | Sarchinar | 100% |
| 26 | Kirkuk | Kirkuk Centre/ Raheem Awa | Sonaboly | 100% |
| 27 | Kirkuk | Kirkuk Centre/ Raheem Awa | Dubizni | 100% |
| 28 | Kirkuk | Kirkuk Centre/ Raheem Awa | Al Khazrajea | 100% |
| 29 | Kirkuk | Al Toon Kopri/ Centre | Zarqaa Yamama | 100% |
| 30 | Kirkuk | Al Toon Kopri/ Cloor | Daraman | 100% |
| 31 | Missan | Nahr Saad | Al Emam Ali | 100% |
| 32 | Missan | Nahr Saad | Abu Al Qasim Al Shabi | 100% |
| 33 | Missan | Al Huda | Al Safa' / Secondary | 100% |
| 34 | Missan | Nahr Saad | Al Imam Al Jawad | 100% |
| 35 | Missan | Kumate | Sukaina Bint Elhusain | 100% |
| 36 | Missan | Ali Al Shaqi | Al-Mustafa | 100% |
| 37 | Missan | Ali Al Gharbi | Al-Haboobi | 100% |
| 38 | Missan | Ali Al Gharbi | Ghareeb Karbala | 100% |
| 39 | Missan | Ali Al Shaqi | Um Ammar | 100% |
| 40 | Missan | Al Umara | Al-Huda | 100% |
| 41 | Missan | Al Umara | Al-Mutanabi | 100% |
| 42 | Missan | Al Umara/ Awasha | Al Khansa | 100% |
| 43 | Missan | Al Umara/ Awasha | Al-Kawthar | 100% |
| 44 | Missan | Al Umara/ Al Wahda | Ali Alsharqi | 100% |
| 45 | Missan | Al Umara/ Al Wahda | Mesr Al-Arabia | 100% |
| 46 | Missan | Al Umara/ Al Qadsiya | Al-Shohob | 100% |
| 47 | Missan | Al Umara/ Al Qatta' | Al-Hidaya | 100% |
| 48 | Missan | Al Umara/ Al Al Rawaba' | Um Albaneen | 100% |
| 49 | Missan | Al Umara/ Dbeasat | Al-Qibla | 100% |
| 50 | Missan | Al Umara/ Al Musharah Way | Ali Algarbi | 100% |
| 51 | Missan | Al Umara/ Al Musharah Way | Balqees | 100% |
| 52 | Missan | Al Umara/ Al Musharah Way | Heteen | 100% |
| 53 | Missan | Al Umara/ Al Musharah Way | Al-Farouk | 100% |
| 54 | Missan | Al Umara/ Al Askari | Al-Shaheed Hazah | 100% |
| 55 | Missan | Al Umara/ Al Askari | Al-Musharah | 100% |
| 56 | Missan | Al Umara/ Al Kahla' Way | Al-Baraem | 100% |
| 57 | Missan | Al Umara/ Al Mugharba | Sebaa | 100% |
| 58 | Missan | Al Umara/ Al Mugharba | Gubat Al-Sagra | 100% |
| 59 | Missan | Al Umara/Al Maimona /Al Hussainya | Al Amin | 100% |
| 60 | Missan | Al Umara/Al Maimona /Al Tubar | Al Rahman | 100% |
| 61 | Missan | Al Umara/Al Maimona /Abu Saba' | Al Suroor | 100% |
| 62 | Missan | Al Umara/ Al Areas | Al Khaleej Al Arabi | 100% |
| 63 | Missan | Al Umara/ Al Iza' | Al Iza' | 100% |
| 64 | Missan | Al Umara/ Basateen Saniya | Al Imam Al Hassan | 100% |
| 65 | Missan | To be inditified | Replacement for Al-Yarmouk school | 100% |
| 66 | Najaf | Kufa | Al-Esra | 100% |
| 67 | Najaf | Al-Manathira | AL_-Botolah | 100% |
| 68 | Najaf | Al-Manathira | AL_Thahab | 100% |
| 69 | Najaf | AL_Haidariah | Al-Thowar | 100% |
| 70 | Najaf | AL_Haidariah | Al-Aqsa | 100% |
| 71 | Najaf | Al-Manathira | Heteen/Quresh | 100% |
| 72 | Najaf | Kufa | Zaid Ben Ali | 100% |
| 73 | Najaf | Kufa | Abi Firas | 100% |
| 74 | Najaf | Kufa | Al-Akhaa | 100% |
| 75 | Najaf | Al-Manathira | Mohammad Al-Dora | 100% |
| 76 | Najaf | Kufa | AL_Zohor | 100% |
| 77 | Najaf | Al-Manathira | Ur | 100% |
| 78 | Najaf | Kufa | Al-Fadhail | 100% |
| 79 | Najaf | Kufa | Maka Elmokarama | 100% |
| 80 | Najaf | Kufa | Al-Eskandarona | 100% |
| 81 | Najaf | Al-Manathira | Al-Suwaiss | 100% |
| 82 | Najaf | Kufa | Al-Ezdihar | 100% |
| 83 | Najaf | Al-Manathira | Al-Bathaa/Sinaa | 100% |
| 84 | Najaf | Kufa | AL_Mashael | 100% |
| 85 | Najaf | Al-Manathira | Zaid bint Ali | 100% |
| 86 | Najaf | Al-Manathira | AL_Maari | 100% |
| 87 | Najaf | Kufa | Halwan | 100% |
| 88 | Najaf | Kufa | Shat el Arab | 100% |
| 89 | Najaf | Al-Manathira | AL_Maali | 100% |
| 90 | Najaf | Kufa | Maryam Al-Athra | 100% |
| 91 | Najaf | Al-Manathira | Shohada Jisr Al-Aemah | 100% |
| 92 | Najaf | Al-Manathira | Al-Fajr Al-Jadeed | 100% |
| 93 | Najaf | Al-Manathira | AL_Eslah | 100% |
| 94 | Najaf | Al-Manathira | AL_Ghazali | 100% |
| 95 | Najaf | Kufa | Qortoba | 100% |
| 96 | Najaf | Al-Manathira | Al-Hadar | 100% |
| 97 | Najaf | Al-Manathira | Rafah | 100% |
| 98 | Najaf | Kufa | Abtal Al-Jolan | 100% |
| 99 | Najaf | Kufa | Poor Said | 100% |
| 100 | Najaf | Kufa | Zanobia | 100% |