- United Nations Development Group Iraq Trust Fund

- Project #:B1-29 (a+b)

- Date and Quarter Updated: 30 September 2008 (3rd Quarter)

- Part One: Summary

| Participating UN Organisation: UNICEF & UNHABITAT | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Directorates of Education in selected governorates in close collaboration with Ministries of Education in Baghdad and Erbil |  |

| Title | School Rehabilitation and Capacity Development for Enhanced Access and Retention in Primary Education |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Governorates: Muthanna, Dohuk, Kirkuk, Missan & Najaf - Ministry of Education (MoE) letter no. 13146 dated 21/4/2008 requested the transfer of ten schools from Kirkuk’s share to Anbar as per attached list. |  |  |  |  |
| Project Cost | US $11,325,596 (UNICEF $7,312,914 & UNHABITAT $4,012,682) |  |  |  |  |
| Duration | [12 Months] |  |  |  |  |
| Approval Date (SC) | 28 Jun 2007 | Starting Date | 16 Oct 2007 | Completion Date | 31 Dec. 2008 (request for extension till 31 Mar 2009 has been submitted) |
| Project Description | The project aims at increasing the enrolment, completion and retention in primary education, especially for girls through: rehabilitation of WES facilities in schools; basic rehabilitation of school buildings; provision of educational supplies; on the job training in classrooms and school-based management for education staff through exposure to best practices in the region; increase community participation and parents' support to learning in school through reactivation of Parent Teacher Associations (PTAs); teacher training in gender–sensitive and child-centred methods; and health and hygiene education. |  |  |  |  |

- Development Goal and Immediate Objectives

The developmental goal of the project is to demonstrably improve access to and quality of primary education and intermediate levels of education, with particular focus on girls and girls’ schools, as well as mixed schools in 200 disadvantaged rural schools throughout Iraq. - Immediate Objectives are: To upgrade 200 girls’ and mixed schools to child-friendly status; to create awareness among community and religious leaders on the importance of girls’ education and gender issues; to equip teachers with innovative teaching methods, and promote gender-sensitive attitudes; to equip the principals and educational supervisors with supervisory and leadership skills; to increase parent participation through strengthening of PTAs; and to include health and hygiene activities in the school curriculum.

- Outputs, Key activities and Procurement

| Outputs | - 200 schools will be rehabilitated in five governorates; - 200 schools in five governorates will be equipped with appropriate furniture, learning materials, sanitary kits, playgrounds and safe water and sanitation facilities; - 25 education staff will be trained on multi purpose schools; - Principals of the 200 selected schools and educational supervisors will be trained in school and classroom-based management, and leadership skills and strategies; - Four meetings of each PTA will be conducted at the 200 selected schools, e.g. addressing issues of safety and privacy of girls in schools and on their way to school; - Teachers and students will be equipped with skills to take care of their personal health and hygiene and maintain a healthy school environment. |
| --- | --- |
| Activities | - Rehabilitation of WES facilities in 200 schools and repair of school buildings. - Upgrading of 200 schools through: procurement and distribution of school furniture and recreational materials; establishment of safe recreational areas; on the job training for 25 education staff of multipurpose schools in the Region. - Improving teaching methods, child-centred learning and gender sensitivity through: A study tour and training for 25 educational staff; upgrading five schools to a multipurpose school; elaboration of training manuals; elaboration and printing of teaching learning materials; and exposing 200 teachers to innovative methods in teaching. - Improving supervisory, management and leadership skills of principals. - Establishment and printing of guidelines for PTAs, as well as supporting the preparation and implementation of four PTA meetings. - Including health and hygiene activities in the school curriculum. Procurement and distribution of sanitation kits to all selected schools. Reprinting 200 manuals for rehabilitated schools. |
| Procurement (major items) | Furniture, learning materials, sanitary kits, and recreational materials. |

- Part Two:

- UNICEF

| Funds Committed | $ 7,134,642 | % of approved | 97.5 % |
| --- | --- | --- | --- |
| Funds Disbursed | $ 3,224,562 | % of approved | 44 % |
| Forecast final date | 31 December 2008 | Delay (months) | N/A |

- UNHABITAT

| Funds Committed | $ 2,640,123 | % of approved | 66% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 1,328,186 | % of approved | 33% |
| Forecast final date | 31 December 2008 | Delay (months) | N/A |

- Quantitative achievements against objectives and results

| Rehabilitation of Water & Sanitation facilities in 200 schools and minor repair of school building and playground. | Rehabilitation works for 92 (56 for UNICEF & 36 for UNHABITAT) schools are completed. Rehabilitation in 75 schools (43 UNICEF & 32 UNHABITAT) is ongoing. 33 schools are under bidding ( 1 UNICEF & 32 UNHABITAT) | % of planned Bidding process only | 75% |
| --- | --- | --- | --- |
| To create awareness among community and religious leaders on the importance of girls’ education, modern teaching methodology and gender issues. | 24 staff representing MoE Baghdad and KRG visited Egypt and received the subject training. | % of planned | 10% |
| To equip teachers with innovative teaching methods, and promote gender-sensitive attitudes. | For 167 schools in centre/south 441 teachers were trained in child-centred and gender-sensitive teaching methods. For 33 schools in Kurdistan, 16 teachers were trained on the same subject. | % of planned | 93% |
| To equip the principals and educational supervisors with supervisory and leadership skills. | 154 headmasters in centre/south and 4 in Kurdistan were trained on the subject. | % of planned | 93% |
| Equip 200 schools with school furniture | 3 schools have received furniture and the process is ongoing. | % of planned | 1.5% |
| To increase parent participation through strengthening of PTAs | The preparation of PTA meetings will start soon. | % of planned | 00% |

- Qualitative achievements against objectives and results

Evaluation of the project will be conducted towards the end of year 2008. Once the evaluation results come out, qualitative achievements will be reported.

Names & Locations of schools

(Schools in blue to be rehabilitated by UNHABITAT but to be equipped with furniture and training by UNICEF)

| 1. UN-HABITAT |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Governorate | District | School | Progress |
| 1 | Al Muthanna | Samawa / Al Suwalim | Al Mujahid | 100% |
| 2 | Al Muthanna | Samawa / Centre | Al Jumhorya | 100% |
| 3 | Al Muthanna | Samawa/ Hay Al Shaheed Al Sadir | Al Ghadeer | 100% |
| 4 | Al Muthanna | Samawa | Al Nazaha | 75% |
| 5 | Al Muthanna | Samawa | Al Zuhoor / Secondary | 75% |
| 6 | Al Muthanna | Samawa / Mamlaha | Tabarek | 75% |
| 7 | Al Muthanna | Samawa/ Al Qushla | Bint Al Huda | 75% |
| 8 | Al Muthanna | Rumaithah / Al Khawam | Toa'a | 100% |
| 9 | Al Muthanna | Rumaithah/ Al Abou Hassan | Al Shatte' | 100% |
| 10 | Al Muthanna | Rumaithah/ Al Tabo | Al Qabas | 100% |
| 11 | Al Muthanna | Al Khidhr / Al Bdairy | Ali Al Akbar/ Intermediate | 70% |
| 12 | Al Muthanna | Al Khidhr/ Qatyat Al Sabia | Al Ayat | 70% |
| 13 | Al Muthanna | Al Warka'a | Al Salman | 70% |
| 14 | Al Muthanna | Al Warka'a/ Al Jirabe | Al Noor | 10% |
| 15 | Al Muthanna | Al Warka'a/ Bani Zraje | Al Dhifer/Halima | 10% |
| 16 | Al Muthanna | Al Warka'a/ Bani Zraje | Haleema Al-Sadeya | 10% |
| 17 | Al Muthanna | Al Majed | Al Majed/ Secondary | 70% |
| 18 | Al Muthanna | Al Majed | Al Dyar | 70% |
| 19 | Al Muthanna | Al Salman | Jawad Al-Aema | 70% |
| 20 | Al Muthanna | Al Suwear | Al Khaleej Al Arabi/ Secondary | 70% |
| 21 | Kirkuk | Debass/ Al Malha | Barda Qaraman | 100% |
| 22 | Kirkuk | Debass/ Mshearfa' | Goran | 100% |
| 23 | Kirkuk | Debass/ Balkana | Sarkawtn | 100% |
| 24 | Kirkuk | Kirkuk Centre/ Taba | Kalwar | 100% |
| 25 | Kirkuk | Kirkuk Centre/ Raheem Awa | Sarchinar | 100% |
| 26 | Kirkuk | Kirkuk Centre/ Raheem Awa | Sonaboly | 60% |
| 27 | Kirkuk | Kirkuk Centre/ Raheem Awa | Dubizni | 60% |
| 28 | Kirkuk | Kirkuk Centre/ Raheem Awa | Al Khazrajea | 45% |
| 29 | Kirkuk | Al Toon Kopri/ Centre | Zarqaa Yamama | 45% |
| 30 | Kirkuk | Al Toon Kopri/ Cloor | Daraman | Under evaluation |
| 31 | Missan | Nahr Saad | Al Emam Ali | 100% |
| 32 | Missan | Nahr Saad | Abu Al Qasim Al Shabi | 100% |
| 33 | Missan | Al Huda | Al Safa' / Secondary | 100% |
| 34 | Missan | Nahr Saad | Al Imam Al Jawad | 100% |
| 35 | Missan | Kumate | Sukaina Bint Elhusain | 100% |
| 36 | Missan | Ali Al Shaqi | Al-Mustafa | 100% |
| 37 | Missan | Ali Al Gharbi | Al-Haboobi | 100% |
| 38 | Missan | Ali Al Gharbi | Ghareeb Karbala | 100% |
| 39 | Missan | Ali Al Shaqi | Um Ammar | 100% |
| 40 | Missan | Al Umara | Al-Huda | 100% |
| 41 | Missan | Al Umara | Al-Mutanabi | 100% |
| 42 | Missan | Al Umara/ Awasha | Al Khansa | 100% |
| 43 | Missan | Al Umara/ Awasha | Al-Kawthar | 100% |
| 44 | Missan | Al Umara/ Al Wahda | Ali Alsharqi | 100% |
| 45 | Missan | Al Umara/ Al Wahda | Mesr Al-Arabia | 100% |
| 46 | Missan | Al Umara/ Al Qadsiya | Al-Shohob | 60% |
| 47 | Missan | Al Umara/ Al Qatta' | Al-Hidaya | 60% |
| 48 | Missan | Al Umara/ Al Al Rawaba' | Um Albaneen | 60% |
| 49 | Missan | Al Umara/ Dbeasat | Al-Qibla | BoQs under review |
| 50 | Missan | Al Umara/ Al Musharah Way | Ali Algarbi | BoQs under review |
| 51 | Missan | Al Umara/ Al Musharah Way | Balqees | BoQs under review |
| 52 | Missan | Al Umara/ Al Musharah Way | Heteen | BoQs under review |
| 53 | Missan | Al Umara/ Al Musharah Way | Al-Farouk | BoQs under review |
| 54 | Missan | Al Umara/ Al Askari | Al-Shaheed Hazah | BoQs under review |
| 55 | Missan | Al Umara/ Al Askari | Al-Musharah | BoQs under review |
| 56 | Missan | Al Umara/ Al Kahla' Way | Al-Baraem | BoQs under review |
| 57 | Missan | Al Umara/ Al Mugharba | Sebaa | BoQs under review |
| 58 | Missan | Al Umara/ Al Mugharba | Al-Aamal | BoQs under review |
| 59 | Missan | Al Umara/ Al Areas | Al Khaleej Al Arabi | BoQs under review |
| 60 | Missan | Al Umara/ Al Iza' | Al Iza' | BoQs under review |
| 61 | Missan | Al Umara/ Basateen Saniya | Al Imam Al Hassan | BoQs under review |
| 62 | Missan | Al Umara/Al Maimona /Al Hussainya | Al Amin | BoQs under review |
| 63 | Missan | Al Umara/Al Maimona /Al Tubar | Al Rahman | BoQs under review |
| 64 | Missan | Al Umara/Al Maimona /Abu Saba' | Al Suroor | BoQs under review |
| 65 | Missan | To be identified | Replacement for Al-Yarmouk school | BoQs under review |
| 66 | Najaf | Kufa | Al-Esra | 100% |
| 67 | Najaf | Al-Manathira | AL_-Botolah | 100% |
| 68 | Najaf | Al-Manathira | AL_Thahab | 100% |
| 69 | Najaf | AL_Haidariah | Al-Thowar | 100% |
| 70 | Najaf | AL_Haidariah | Al-Aqsa | 100% |
| 71 | Najaf | Al-Manathira | Heteen/Quresh | 100% |
| 72 | Najaf | Kufa | Zaid Ben Ali | 100% |
| 73 | Najaf | Kufa | Abi Firas | 100% |
| 74 | Najaf | Kufa | Al-Akhaa | 100% |
| 75 | Najaf | Al-Manathira | Mohammad Al-Dora | 100% |
| 76 | Najaf | Kufa | AL_Zohor | 90% |
| 77 | Najaf | Al-Manathira | Ur | 90% |
| 78 | Najaf | Kufa | Al-Fadhail | 90% |
| 79 | Najaf | Kufa | Maka Elmokarama | 90% |
| 80 | Najaf | Kufa | Al-Eskandarona | 90% |
| 81 | Najaf | Al-Manathira | Al-Suwaiss | 90% |
| 82 | Najaf | Kufa | Al-Ezdihar | 90% |
| 83 | Najaf | Al-Manathira | Al-Bathaa/Sinaa | 90% |
| 84 | Najaf | Kufa | AL_Mashael | 90% |
| 85 | Najaf | Al-Manathira | Zaid bint Ali | 90% |
| 86 | Najaf | Al-Manathira | AL_Maari | BoQs under review |
| 87 | Najaf | Kufa | Halwan | BoQs under review |
| 88 | Najaf | Kufa | Shat el Arab | BoQs under review |
| 89 | Najaf | Al-Manathira | AL_Maali | BoQs under review |
| 90 | Najaf | Kufa | Maryam Al-Athra | BoQs under review |
| 91 | Najaf | Al-Manathira | Shohada Jisr Al-Aemah | BoQs under review |
| 92 | Najaf | Al-Manathira | Al-Fajr Al-Jadeed | BoQs under review |
| 93 | Najaf | Al-Manathira | AL_Eslah | BoQs under review |
| 94 | Najaf | Al-Manathira | AL_Ghazali | BoQs under review |
| 95 | Najaf | Kufa | Qortoba | BoQs under review |
| 96 | Najaf | Al-Manathira | Al-Hadar | BoQs under review |
| 97 | Najaf | Al-Manathira | Rafah | BoQs under review |
| 98 | Najaf | Kufa | Abtal Al-Jolan | BoQs under review |
| 99 | Najaf | Kufa | Poor Said | BoQs under review |
| 100 | Najaf | Kufa | Zanobia | BoQs under review |

2. UNICEF

| No | Governorate | District | Sub district/village | School | Progress (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | Tamim | Kirkuk | Kirkuk | Tafka | 100% |
| 2 | Tamim | Kirkuk | Kirkuk | Shaheed | 100% |
| 3 | Tamim | Kirkuk | Kirkuk | Bent Al Huda | 100% |
| 4 | Al Muthanna | Al Rumaithah | Al-Rumaitha | Al A'aridhiat | 100% |
| 5 | Missan | Amara | Al-Amel | Al Ahid Al-Jadeed | 100% |
| 6 | Missan | Amara | Awasha | Al Sayida Zainab | 100% |
| 7 | Missan | Amara | AL-Imarat | Intifadhat Al Aqsa | 100% |
| 8 | Missan | Amara | Al-Askari | Utba Bin Ghazwan | 100% |
| 9 | Missan | Amara | Al-Amel | Um Salama | 100% |
| 10 | Dohuk | Dahuk | Dahuk | Halgurd | 100% |
| 11 | Tamim | Kirkuk | Kirkuk | Naghda | 100% |
| 12 | Missan | Amara | Abo Rumana | Babil | 100% |
| 13 | Missan | Amara | Al-Moaalmeen | Tarablus | 100% |
| 14 | Missan | Amara |  | Al Ahrar/Imam Al Hady | 100% |
| 15 | Missan | Amara | Al-Iskan | Al Tahira | 100% |
| 16 | Missan | Amara | Abo Rumana | Asia | 100% |
| 17 | Tamim | Kirkuk | Kirkuk | Kal Sedrah | 100% |
| 18 | Dohuk | Dahuk | Dahuk | 11 Aylul | 100% |
| 19 | Dohuk | Dahuk | Dahuk | Jihan | 100% |
| 20 | Dohuk | Dahuk | Dahuk | Shakhke | 100% |
| 21 | Dohuk | Dahuk | Dahuk | Salaidin | 100% |
| 22 | Dohuk | Sumel | Sumel | Davar | 100% |
| 23 | Dohuk | Sumel | Sumel | Kany Arab | 100% |
| 24 | Dohuk | Zakho | Zakho | Runahi | 100% |
| 25 | Dohuk | Zakho | Zakho | Karez | 100% |
| 26 | Dohuk | Zakho | Zakho | Halo | 100% |
| 27 | Dohuk | Dahuk | Dahuk | Kurdayatee | 100% |
| 28 | Dohuk | Dahuk | Dahuk | Halat | 100% |
| 29 | Dohuk | Dahuk | Dahuk | Brushky | 100% |
| 30 | Dohuk | Shekhan | Shekhan | Beedol | 100% |
| 31 | Dohuk | Shekhan | Shekhan | Balata | 100% |
| 32 | Dohuk | Amadiya | Sarsink | Kaladimdim | 100% |
| 33 | Dohuk | Amadiya | Deralok | Kurezhar | 100% |
| 34 | Dohuk | Dahuk | Dahuk | Etity-Itot | 100% |
| 35 | Dohuk | Dahuk | Dahuk | 14 Adar | 100% |
| 36 | Dohuk | Dahuk | Dahuk | Ararat | 100% |
| 37 | Dohuk | Dahuk | Dahuk | Kaverke/ Parlaman | 100% |
| 38 | Dohuk | Dahuk | Dahuk | Zozik | 100% |
| 39 | Dohuk | Dahuk | Dahuk | Malta Zhery | 100% |
| 40 | Dohuk | Dahuk | Dahuk | Malta Zhory | 100% |
| 41 | Dohuk | Sumel | Sumel | Bajid Kandal | 100% |
| 42 | Anbar | Ramadi | Romadi centre | Al-Rasheed | 100% |
| 43 | Anbar | Ramadi | Romadi centre | Al-Afah | 100% |
| 44 | Anbar | Ramadi | Romadi centre | Al-Amjad | 100% |
| 45 | Anbar | Ramadi | Romadi centre - Al-sufyah | IbnAl-Atheer | 100% |
| 46 | Anbar | Ramadi | Romadi centre | Al-Junid Al-Baghdadi | 100% |
| 47 | Najaf | Kufa | Kufa | Al Hakma | 100% |
| 48 | Najaf | Najaf | Najaf | Al Efa'a | 100% |
| 49 | Najaf | Kufa | Kufa | Um Salma-Um Salam | 100% |
| 50 | Najaf | Najaf | Najaf | Al Muhajreen | 100% |
| 51 | Najaf | Najaf | Najaf | Al Makaseb | 100% |
| 52 | Najaf | Kufa | Kufa | Al Kameliya | 85% |
| 53 | Najaf | Kufa | Kufa | Al Hayat | 85% |
| 54 | Najaf | Njaf | Najaf | Al Maqassed | 85% |
| 55 | Najaf | Kufa | Kufa | Urafat | 85% |
| 56 | Najaf | Najaf | Al Jadeeda | Al Ferdous | Under bidding |
| 57 | Dohuk | Akre | Akre | Dogondan Gawre | 50% |
| 58 | Dohuk | Akre | Akre | Dogondan Bijuk | 50% |
| 59 | Dohuk | Akre | Akre | Morilan | 50% |
| 60 | Dohuk | Akre | Akre | Qaranaz | 60% |
| 61 | Al Muthanna | Al Rumaithah | Al-Rumaitha | Al Kifah | 91% |
| 62 | Al Muthanna | Al Rumaithah | Al-Rumaitha | Al Futowa | 91% |
| 63 | Al Muthanna | Rumaithah | Al-Rumaitha | Palistine | 91% |
| 64 | Al Muthanna | Al Rumaithah | Al-Rumaitha | Al Tahtheeb | 91% |
| 65 | Al Muthanna | Al Samawa | Al-Samawa | Al Akha' | 100% |
| 66 | Al Muthanna | Al Samawa | Al-Samawa | Al Razi | 100% |
| 67 | Al Muthanna | Al Samawa | Al-Samawa | Al Tadhamun | 100% |
| 68 | Al Muthanna | Al Samawa | Al-Samawa | Al Numoothaj | 100% |
| 69 | Al Muthanna | Al Samawa | Al-Samawa | Haifa | 100% |
| 70 | Al Muthanna | Al Rumaithah | Al-Rumaitha | Al Mustansiria | 91% |
| 71 | Al Muthanna | Al Samawa | Al-Samawa | Al Sahab | 91% |
| 72 | Al Muthanna | Al Rumaithah | Al-Rumaitha | Al Koofa | 91% |
| 73 | Al Muthanna | Al Khidhr | Al-Khidhir | Al Zawra' | 91% |
| 74 | Missan | Amara | Al-Risala | Al Manar | 95% |
| 75 | Missan | Amara | Al-Thawra | Abu Al Fadhil Al Abas | 95% |
| 76 | Missan | Amara | Hay Al-Thawra | Ausama Bin Zaid | 95% |
| 77 | Missan | Amara | Al-Wahda | Al Imam Al Qa'em | 95% |
| 78 | Missan | Amara | Al-Qadisiya | Al Hashmiya | 95% |
| 79 | Dohuk | Akre | Akre | Bakirman | 80% |
| 80 | Dohuk | Akre | Akre | Sarderian | 70% |
| 81 | Dohuk | Akre | Akre | Zeelka Fakher | 70% |
| 82 | Dohuk | Akre | Akre | Sheekhanok | 70% |
| 83 | Najaf | Kufa | Makhmur | Al Rarenjiya | 95% |
| 84 | Najaf | Kufa | Kufa | Nasema Al Ansareya | 95% |
| 85 | Najaf | Kufa | Kufa | Al Bayt Al Ateeq | 95% |
| 86 | Najaf | Kufa | Kufa | That Al Nitaqayn | 95% |
| 87 | Najaf | Kufa | Kufa | Al.Afrah | 95% |
| 88 | Anbar | Ramadi | Romadi centre | Kinda | 55% |
| 89 | Anbar | Ramadi | Romadi centre | Al Qaba' | 52% |
| 90 | Anbar | Ramadi | Romadi centre | Al-Bara'a Bn Malik | 53% |
| 91 | Anbar | Ramadi | Romadi centre | Qubat Al-Sakhra | 50% |
| 92 | Anbar | Ramadi | Al-Khaledia | Ukadh | 75% |
| 93 | Tamim | Kirkuk | Kirkuk | Bahra | 77% |
| 94 | Tamim | Kirkuk | Kirkuk | Chirdaghlu | 80% |
| 95 | Tamim | Daquq | Kirkuk | Amir Al Mumneen | 32% |
| 96 | Tamim | Kirkuk | Kirkuk | Mukhtar Oghlo | 78% |
| 97 | Tamim | Daquq | Kirkuk | Zaen Al Abdeen | 32% |
| 98 | Tamim | Daquq | Kirkuk | Fatima | 90% |
| 99 | Tamim | Kirkuk | Kirkuk | Sara | 78% |
| 100 | Tamim | Kirkuk | Kirkuk | Al Bikler | 80% |