# United Nations Development Group Iraq Trust Fund

# Project #: B1 – 31

# Date and Quarter Updated: 15 July 2009 (2nd Quarter)

| Participating UN Organisation: UNESCO | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education, Baghdad |

| Title | Distance Learning Project |
| --- | --- |
| Geographic Location | Baghdad – Iraq. Serving all of Iraq |
| Project Cost | US$ 6,505,228 |
| Duration | 23 months |
| Approval Date (SC) | 25th July 2007 | Starting Date | 31st July 2007 | Completion Date | 30th June 2009 |
| Project Description | The project aims at supporting primary and secondary levels students - all over Iraq - to overcome the deteriorating security conditions resulting in a noticeable decline in enrolment and attendance rate and closure of several schools. The effect of life-threatening attacks on students and teachers will be targeted through the provision of learning opportunities through the distance learning delivery mechanisms such as educational TV programs based on formal Iraqi school curricula. The project gives priority to serving students of grades 12, 9 and 6 (transitional grades) all over Iraq. |

Development Goal and Immediate Objectives

The development goal of the project is increasing the participation and involvement of primary and secondary school students in their studies, within the context of the existing security situation, through distance learning tools designed according to the Iraqi formal school curricula. By developing and regular broadcasting of the educational programs, the project contributes to supporting primarily the Education for All (EFA) goals and other developmental goals in Iraq. The project will be highly instrumental in supplementing the on-going efforts of the Ministry of Education toward meeting the challenges outlined in its revised National Development Strategy (NDS) and the UN Assistance Strategy for Iraq (2007-2010).

| Outputs, Key activities and Procurement |
| --- |
| Outputs | 40 educational specialists from Colleges of Education and 80 TV technical specialists trained on the use of distance learning tools, specially, the design and broadcasting of curricular lessons. Educational TV, covering all subjects, produced and broadcasted to students all over Iraq |
| Activities | Capacity building of MOE technical staff on operating the TV satellite broadcasting unit through specialized training workshops. Capacity building of educational specialists from MOE and Colleges of Education on designing Educational TV programs. 1.2.1 Building scenarios and designing TV educational programs covering all subjects based on the Iraqi school curricula by MOE national educational experts. 1.2.2 Contracting private Iraqi studios in Iraq for the production of school-based educational TV programs. 1.2.3 Establishing and equipping the focal TV satellite unit at MOE for broadcasting the educational TV programs. |
| Procurement (major items) | Equipping the focal TV satellite unit at MOE for broadcasting the educational TV programs. Production of educational TV programmes based on the Iraqi formal curricula. |

| Funds Committed | US$ 3,781,030 | % of approved | 67.5% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 2,107,279 | % of approved | 38% |
| Forecast final date | 31st of January 2010 | Delay (months) | 12 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 140 planned | 30% |
| Women | 110 planned | 30% |
| Children | School students – grades 6,9 &12 Approx. 1.5 M students | 100 % |
| IDPs | School students – grades 6, 9 &12 Approx. 100 Thousand Student. | 100 % |
| Others | All School Students including IDPs and Refugees after 2 years of project completion. Approx. 7 M students | 25 % |
| Indirect beneficiaries | The Iraqi Community at large |  |
| Employment generation (men/women) | 250 direct – 300 indirect | 50% - 100% |

| Quantitative achievements against objectives and results |
| --- |
| 40 educational specialists from Colleges of Education and 80 TV technical specialists trained on the use of distance learning tools, specially, the design and broadcasting of curricular lessons. | Completed | % of planned – Phase I | 100% |
| Educational TV programs, covering all subjects, produced and broadcasted to students all over Iraq. | The technical specifications of the production studio were finalized in Feb. 2009. The tender for supplying and installing the TV production equipment was issued and offers evaluated in March 2009. | % of planned – Phase I | 80% |

Main implementation constraints & challenges (2-3 sentences)

# Comments

Just completed will do fine.

No need to mention items reported on in previous reports – this fiche for jan-Mar 2009 only.

No constraints with a delay of 12 months?