- United Nations Development Group Iraq Trust Fund

- Project #:B1-31

- Date and Quarter Updated: 22nd June 2008 (2nd Quarter)

- Part One: Summary

| Participating UN Organisation: UNESCO | Cluster: B |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Education , Baghdad |  |

- Programme/Project Number:

| Title | Distance Learning Project |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Location | Baghdad – Iraq. Serving all of Iraq |  |  |  |  |
| Project Cost | US$ 5,605,228 |  |  |  |  |
| Duration | 18 months. |  |  |  |  |
| Approval Date (SC) | 31 July 2007 | Starting Date | 31st July 2007 | Completion Date | 31 January 2009 |
| Project Description | The project aims at supporting primary and secondary levels students - all over Iraq - to overcome the deteriorating security conditions resulting in a noticeable decline in enrolment and attendance rate and closure of several schools. The perpetuating life-threatening attacks on students and teachers will be addressed by providing learning opportunities through the distance learning delivery mechanisms such as educational TV programs based on formal Iraqi school curricula. The project gives priority to serving students of grades 12, 9 and 6 (transitional grades) all over Iraq. |  |  |  |  |

- Development Goal and Immediate Objectives

The development goal of the project is increasing the participation and involvement of primary and secondary school students in their studies, within the context of the deteriorating security situation, through distance learning tools designed according to the Iraqi formal school curricula. By developing and regular beaming and broadcasting of the educational programs on TV the project contributes to supporting primarily the Education for All (EFA) goals and other developmental goals in Iraq. The project will be highly instrumental in supplementing the on-going efforts of the Ministry of Education toward meeting the challenges outlined in its revised National Development Strategy (NDS) and the UN Assistance Strategy for Iraq (2007-2010).

- Outputs, Key activities and Procurement

| Outputs | - 40 educational specialists from Colleges of Education and 80 TV technical specialists trained on the use of distance learning tools, specially, the design and broadcasting of curricular lessons. - Educational TV, covering all subjects, produced and broadcasted to students all over Iraq |
| --- | --- |
| Activities | - Capacity building of MOE technical staff on operating the TV satellite broadcasting unit through specialized training workshops. - Capacity building of educational specialists from MOE and Colleges of Education on designing Educational TV programs. 1.2.1 Building scenarios and designing TV educational programs covering all subjects based on the Iraqi school curricula by MOE national educational experts. 1.2.2 Contracting Private Iraqi studios in Iraq for the production of school-based educational TV programs. 1.2.3 Establishing and equipping the focal TV satellite unit at MOE for broadcasting the educational TV programs. |
| Procurement (major items) | - Equipping the focal TV satellite unit at MOE for broadcasting the educational TV programs. - Production of Educational TV Programmes based on the Iraqi formal curricula. |

- Part Two: Situation as of 22nd of June 2008

| Funds Committed | $ 2,291,396 | % of approved | 41% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 132,448 | % of approved | 2.36% |
| Forecast final date | End April 2009 | Delay (months) |  |

- Quantitative achievements against objectives and results

| - 40 educational specialists from Colleges of Education and 80 TV technical specialists trained on the use of distance learning tools, specially, the design and broadcasting of curricular lessons. | - 32 MOE Educational Specialists were trained on “Preparing and Presenting Educational TV Programs”. Training commenced on 1 June 2008 and was completed on 12 June 2008. - A contract for building the capacity of MOE technical staff on operating the TV satellite broadcasting unit was signed. | % of planned | 60 % |
| --- | --- | --- | --- |
| - Educational TV programs, covering all subjects, produced and broadcasted to students all over Iraq. | - Renovation of the Educational TV Station was completed. - A contract for Educational TV episodes production was signed. Expected completion date Jan 2009. - A bid for the production of animated TV episodes on human rights, gender equality…etc issued. - MOE TV broadcasting studio, lighting system delivered and stored to be installed in July 2009. - Broadcasting uplink equipment shipped. Expected delivery in Baghdad 3rd week of July 2009. - TV control units’ equipment shipped. Expected delivery in Baghdad end of July 2009. - TV Transmission contract prepared to be signed 1st week of July. | % of planned | 30% |

- Qualitative achievements against objectives and results

The project is still in its early starting phase, and it’s premature to report on qualitative achievements.