# United Nations Development Group Iraq Trust Fund

# Project #:B1-32

# Date and Quarter Updated: 31 Dec 2007

# Part One: Summary

| Participating UN Organisation: UNICEF | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education in collaboration with MoH, MMPW, MoB,& MoLSA |

| Title | Integrated Community Based Services Project - Basrah |
| --- | --- |
| Geographic Location | [Governorate: Basra] [District: Al-Basra & Al-Qurnah] [Villag/Town: Shat Al Arab, Hay Al Hussain, Hay Al Hadi Al Zubair, Hay dajla, Qurna centre, Sharash, Hay Al Jameia] |
| Project Cost | 1,755,155 USD |
| Duration | [12 Months] |
| Approval Date (SC) | 04 October 2007 | Starting Date | October 2007 | Completion Date | 4 October 2008 |
| Project Description | Provide an integrated package of community-based interventions to increase availability, quality and access to basic services in selected communities in Basra. Schools are identified in communities of Basrah governorate as entry point for coordinated interventions in education, health and water & sanitation. |

# Development Goal and Immediate Objectives

Improving access and quality of basic social services in disadvantaged communities through an integrated community approach! In selected communities in Basrah governorate, Iraqi authorities will be able to fulfil their obligations towards vulnerable populations in terms of responding to their immediate needs for basic social services in a transparent and equitable manner in line with democratic principles and international human rights standards, contributing to the achievement of following MDG goals: enrolling all children in primary school (MDG-2), eliminating gender disparities in primary and secondary education (MDG-3), reducing by half the proportion of people without access to safe drinking water (MDG-7), reducing child mortality (MDG-4) and finally poverty reduction (MDG-1). Immediate Objectives Improve Participation and retention as well as access to and quality of education in thirteen schools in Basrah Governorate; Improve access to potable water and sanitation services in the communities around the selected schools; Improve the quality of basic primary health and nutrition services in the communities around the selected schools; Assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children.

# Outputs, Key activities and Procurement

| Outputs | The overarching output will be to upgrade thirteen schools to Child-Friendly status : 1.1 School participation and retention as well as access of primary school children will improve; 2.1 Availability and improved quality of water and wastewater disposal will increase; 2.2 Sanitary facilities for school children, especially for girls will be available. 3.1 Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment 3.2 Two primary health care centres serving the 13 local communities will be physical rehabilitated. 3.3 The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities. 4.1 Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities; 4.2 Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project, Parent Teacher Associations (PTAs) will be engaged in project implementation. |
| --- | --- |
| Activities | Improved School participation and retention of primary school children Availability and improved quality of water and wastewater disposal as well as sanitary facilities for school children, especially for girls will increase sanitary facilities for school children, especially for girls will be available. Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment Two primary health care centres serving the 13 local communities will be physical rehabilitated The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities. Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities through Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project, Parent Teacher Associations (PTAs) will be engaged in project implementation |
| Procurement (major items) | Sanitation kits, school furniture & recreational kits; Essential vaccines, basic medicines, medical supplies/equipment for PHC/MCH units; Wastewater laboratory equipment for Sewage Treatment Plant; |

# Part Two:

| Funds Committed | 24,109.8 | % of approved | 0.01 |
| --- | --- | --- | --- |
| Funds Disbursed | 24,109.8 | % of approved | 0.01 |
| Forecast final date | As planned (October 2008) | Delay (months) |  |

# Quantitative achievements against objectives and results

| Rehabilitation of water and sanitation facilities, play grounds and minor rehabilitation of schools buildings | All 13 schools are selected and physical assessment is in progress. | 10% of planned | 10 |
| --- | --- | --- | --- |
| Rehabilitation of WES facilities in communities | Rehabilitation sites are identified. Preparation of Bill of Quantities is underway. | % of planned | 0 |
| Rehabilitation of PHCs in Basra | One PHC in Basra / Al Qurna District | 0% of planned Bidding process only | 5% |
| Training of PHCC staff and village volunteers | Scheduled for 2008 | % of planned |  |
| Training on operation and maintenance of water supply facilities | Will be conducted during the actual implementation of works | % of planned | 0 |
| Training on the Operation and Maintenance of Sewerage facilities | Will be conducted during the actual implementation of works | % of planned | 0 |
| Training on wastewater quality monitoring | Will be conducted in July 2008 upon delivery of lab supplies | % of planned | 0 |
| Teachers training on school sanitation and hygiene promotion for 3 days | 52 teachers and head teachers in the thirteen schools trained for environmental sanitation & hygiene education | % of planned | 100% |
| Governorate Steering Committee meeting (10 times) | Meetings held in October and November, 2008 | % of planned | 20% |
| Training in decentralized planning & good governance practices for local authorities and governorate council members | Scheduled for 2008 | % of planned |  |
| Training of TOT on psychosocial activities | Scheduled for of 2008 | % of planned |  |
| Training on psychosocial interventions to community based workers and volunteers including parents | Scheduled for of 2008 | % of planned |  |
| Community-based awareness meetings on child rights and psychosocial needs of children, including youth participation meetings | Scheduled for 2008 | % of planned |  |
| Basic health supplies/ equipment/ furniture | Procurement and distribution in 2008 | % of planned |  |
| Design and printing of advocacy documents for awareness campaigns (WES) | Scheduled for May – July 2008 | % of planned | 0 |
| Procurement of network design software (including orientation) | In the process of identification of suitable software | % of planned | 0 |
| Procurement of wastewater laboratory equipment for Basrah Sewage Treatment Plant | List of required equipment and supplies identified. Procurement process initiated. | % of planned | 0 |
| Procurement & distribution of sanitation and recreation kits | Kits procured, distribution scheduled for Feb 2008 | % of planned |  |
| Procurement & distribution of psychosocial recreation kits | Procurement and distribution to be synchronized with activities scheduled for 2008 | % of planned |  |

# Qualitative achievements against objectives and results

The project has just started and will report on qualitative achievement in future

List of targeted schools

| No | Governorate | District | School Name | Status |
| --- | --- | --- | --- | --- |
| 1 | Basra | Al Qurnah | Al-Sharash | Under bidding |
| 2 | Basra | Al Qurnah | Al-Muthana | Under bidding |
| 3 | Basra | Al Qurnah | Al –Thura | Under bidding |
| 4 | Basra | Al Qurnah | Al – Shema Al-Arabiya | Under bidding |
| 5 | Basra | Al Qurnah | Al-Qurna | Under bidding |
| 6 | Basra | Al Basra | Al Wahda Al arabiya | Under bidding |
| 7 | Basra | Al Basra | Arafat | Under bidding |
| 8 | Basra | Al Basra | Al Somod | Under bidding |
| 9 | Basra | Al Basra | Shat Al Arab | Under bidding |
| 10 | Basra | Al Basra | Al Maseer Al Wahid | Under bidding |
| 11 | Basra | Al Basra | Balqees | Under bidding |
| 12 | Basra | Al Basra | Al Jazira Al Arabiya | Under bidding |
| 13 | Basra | Al Basra | Al Hussain | Under bidding |