# United Nations Development Group Iraq Trust Fund

# Project #: B1-32

# Date and Quarter Updated: April - June 2009 (2nd Quarter)

| Participating UN Organisation: UNICEF | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Basra Directorates of Education, in close collaboration with the Ministry of Education in Baghdad and the Governorate Council in Basra |

| Title | Integrated Community-based Services Project Basra |
| --- | --- |
| Geographic Location | Governorate: Basra Basra District (Hai Al Hadi, Hai Al Tanoma, Hai Al Qibla, Hai Al Zubair, Shat-al-Arab, Hai Al Qiblah, Kut Al Hajjaj, 5 mile) Al Qurnah District ( Hai Al Sharash, Hai Al Nussayr, Hai Al Salaam, Al Qurnah Centre) |
| Project Cost | US$ 1,755,155 |
| Duration | Original: 15/Oct/07 – 15/Oct/08 (12 months) 1st Extension: 15/Oct/08 – 31/Dec/08 2nd Extension: 31/Dec/08 – 15/Apr/09 3rd Extension: 14/Apr/09 – 30/Jun/09 |
| Approval Date (SC) | 4/Oct/07 | Starting Date | 15/Oct/07 | Completion Date | Original: 15/Oct/08; 1st Extension: 31/Dec/08; 2nd Extension: 15/Apr/09; 3rd Extension: 30/Jun/09 |
| Project Description | Provide an integrated package of community-based interventions to increase availability, quality and access to basic services in selected communities in Basra. Schools are identified in communities of Basra governorate as entry point for coordinated interventions in education, health and water and sanitation. |

Development Goal and Immediate Objectives

Improving access to and quality of basic social services in disadvantaged communities through an integrated community approach. In selected communities in Basra governorate, Iraqi authorities will be able to fulfil their obligations towards vulnerable populations in terms of responding to their immediate needs for basic social services in a transparent and equitable manner in line with democratic principles and international human rights standards, contributing to the achievement of the following MDGs: enrolling all children in primary school (MDG-2), eliminating gender disparities in primary and secondary education (MDG-3), reducing by half the proportion of people without access to safe drinking water (MDG-7), reducing child mortality (MDG-4) and poverty reduction (MDG-1). Immediate Objectives are: Improve participation and retention as well as access to and quality of education in 13 schools in Basra Governorate; Improve access to potable water and sanitation services in the communities around the selected schools; Improve the quality of basic primary health and nutrition services in the communities around the selected schools; Assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | The overarching output will be to upgrade 13 schools to Child-Friendly status; School participation and retention as well as access of primary school children will improve; Availability and improved quality of water and wastewater disposal will increase; Sanitary facilities for school children, especially for girls will be available; Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment; 2 PHC Centres (PHCCs) serving the 13 local communities will be rehabilitated; The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities; Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities; Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project. Parent Teacher Associations (PTAs) will be engaged in project implementation. |
| Activities | Improved school participation and retention of primary school children Procurement from inside Iraq and distribution of school furniture, recreational materials, school sanitation kits and garden kits to all selected schools; Establishment of safe recreational areas in all selected schools; Creation of school gardens at all selected schools. Availability and improved quality of water and wastewater disposal as well as sanitary facilities for school children, especially for girls will increase through: Training of all teachers in the selected schools in health and hygiene promotion. Hygiene promotion and community awareness campaigns in select communities. Sanitary facilities for school children, especially for girls will be available Rehabilitation/ construction of water and sanitary facilities in schools where required. Selected PHC/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment Procurement and distribution of essential/basic medical supplies and equipment for PHCCs/ MCH units. Two PHCCs serving the 13 local communities will be physically rehabilitated through: Physical rehabilitation of some PHCCs if required (based on the preliminary assessment of the facilities considered for this project); Training of PHC health workers on basic health and nutrition services, including growth monitoring and counselling activities for parents of children suffering from malnutrition, as well as systematic referral of all severe cases of malnutrition to nutrition rehabilitation centres. The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities Support community health and nutrition programmes through community volunteers (former community child care units), in order to strengthen growth monitoring, health and nutrition promotion and referral to PHCCs. This output will also be supported by UNICEF national country programme. Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities through; Supporting psychosocial training for teachers, health workers, parents, youth and other community members in psychosocial intervention and care for children and youth and provide supplies for use in existing spaces (such as schools, health centres and youth centres) in establishing child friendly spaces/psychosocial activities. Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, communities are exercising ownership of the project and PTAs will be engaged in project implementation through: Conducting capacity building courses for relevant government authorities on planning, management and monitoring of area-based programmes; Conducting social mobilization around selected schools to activate PTAs and involve them in planning, implementation and monitoring of the project to the extent possible; while at the central level advocating for government support to the expanded role of PTAs. |
| Procurement (major items) | Recreational and sanitation kits and essential/basic medical supplies and equipment for PHCCs/ MCH units |

| Funds Committed | $ 1,753,786.38 | % of approved | 99.9% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 1,610,430.03 | % of approved | 91.7% |
| Forecast final date | 30 June 2009 | Delay (months) | 8.5 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 200,000 people in the targeted communities | 100% |
| Women |  |  |
| Children | Children in 13 schools | More than 100% (20,735 students (33% girls) including those in the guest schools) |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries |  |  |
| Employment generation (men/women) | 1,900 person days of employment generated. | 100% |

| Quantitative achievements against objectives and results |
| --- |
| Availability and improved quality of water and wastewater disposal will increase | Rehabilitation of Al Faihaa Compact Treatment Unit (200 m3/hr) in Shatt Al Arab district in Basra governorate is physically completed. | % of planned | 100% |
| Sanitary facilities for school children, especially for girls will be available | Rehabilitation of sanitation facilities in 13 schools agreed upon with the Directorate of Education (DoE) has been successfully completed. Funds saved from the rehabilitation work enabled the rehabilitation of an additional four schools. The rehabilitation works of these schools were also completed, bringing the total number of children benefiting from the rehabilitation of the 17 schools to 20,735 students (33% girls) including guest school students. | % of planned | 100% |
| Selected PHCCs/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/ equipment | Orders for procurement of supplies and equipment for PHCCs and MCH units, which were developed in consultation with Directorate of Health counterparts, have been placed. | % of planned | 100% |
| Two PHCCs serving the 13 local communities will be physically rehabilitated | Rehabilitation of Al Qurna PHCC (as per Government request) was satisfactorily completed and handed over to the Government. | % of planned | 100% |
| The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities | Plans for capacity building by DoE Basra have been developed jointly with the Integrated Community Initiative for Children (ICIC) team in Basra for improving the quality of health and nutrition services. Plans include support to community volunteers to improve growth monitoring, health and nutrition promotion and strengthening referral to PHCCs. Implementation of these plans has commenced. | % of planned | 60% |
| Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities | M&E tools were developed and used in the targeted schools to monitor implementation of programme and its impact on improving the wellbeing of children and teachers as well as school environment in providing psychosocial care. The results of these M&E activities will be used to assess the implementation of the programme and apply any required adjustments, as well as to document good practices in preparation for scaling up the project nationwide. A Model Building Workshop brought together senior officials from Ministries of Education and Labour and Social Affairs from Baghdad and Kurdistan Region, Ministry of Higher Education/ Baghdad, UNICEF staff, and implementation partner’s staff. The workshop reviewed the teacher training model and amendments agreed upon to adapt it to the Iraqi context. Involvement of governmental staff in building a model for teacher training will lead to government ownership of the project, hence ensure sustainability. The training model will be used in the teacher training institute/Ministry of Education and in providing on-the-job training for teachers to scale up the project to cover additional schools. The workshop reviewed the implementation plan, recommended amendments and prepared plan for handover to the Ministry of Education. | % of planned | 100% |
| Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, communities are exercising ownership of the project, and PTAs will be engaged in project implementation | 18 Water and Sewerage Authority staff have strengthened skills in different thematic areas. All supplies/ equipment for the conduct of routine wastewater testing and analysis have been delivered to Sewage Lab in Basra. 43 government staff have increased awareness of hygiene practices. Two sets of Water and Sewerage network design software were provided to the Ministry of Municipalities and Public Works (MMPW) training centre in Basra. A similar set of software was also provided to the MMPW training centre in Baghdad. In addition, 14 engineers were also trained on the use of the above software. | % of planned | 100% |

Qualitative achievements against objectives and results

Qualitative achievements will be assessed once the project is completed.

Main implementation constrains & challenges (2-3 sentences)

Annex.1:  Status of school rehabilitation in Basra

| No | Governorate | District (HIC) | Sub dis-village | School Name | Progress (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | Basra | Al Basra | Hay Al-Hadi | Al Wahda Al arabiya | 100% |
| 2 | Basra | Al Basra | Hay Al-Hadi | Arafat | 100% |
| 3 | Basra | Al Basra | Al-Tanomah | Al Somod | 100% |
| 4 | Basra | Al Basra | Shat Al-Arab | Shat Al Arab | 100% |
| 5 | Basra | Al Basra | Hay Al-Hussain | Al Maseer Al Wahid | 100% |
| 6 | Basra | Al Basra | Hay Al-Qibla | Balqees | 100% |
| 7 | Basra | Al Basra | Al-Zubair | Al Jazira Al Arabiya | 100% |
| 8 | Basra | Al Basra | Hay Al-Qibla | Al Hussain | 100% |
| 9 | Basra | Al Qurnah | Al-Sharash Dist. | Al Sharash | 100% |
| 10 | Basra | Al Qurnah | Al-Sharash Dist. | Al Muthanna | 100% |
| 11 | Basra | Al Qurnah | Hay Al-Nusayr | Al Thura | 100% |
| 12 | Basra | Al Qurnah | Hay Al-Salam | Al Shema Al Arabiya | 100% |
| 13 | Basra | Al Qurnah | Al-Qurna center | Al Qurna | 100% |
| 14 | Basra | Al Basra | Shat Al-Arab | Sinjar | 100% |
| 15 | Basra | Al Basra | Hay Al-Hadi | Poor Saeed | 100% |
| 16 | Basra | Al Basra | 5Mile | Diyala | 100% |
| 17 | Basra | Al Basra | Kut Al-Hajaj | Al-Risafy | 100% |