# United Nations Development Group Iraq Trust Fund

# Project #: B1-32

# Date and Quarter Updated: October – December 2008 (4th Quarter)

| Participating UN Organisation: UNICEF | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Basra Directorates of Education, in close collaboration with the Ministry of Education in Baghdad and the Governorate Council in Basra |

| Title | Integrated Community-based Services Project Basra |
| --- | --- |
| Geographic Location | Governorate: Basra Basra District (Hai Al Hadi, Hai Al Tanoma, Hai Al Qibla, Hai Al Zubair, Shat-al-Arab, Hai Al Qiblah, Kut Al Hajjaj, 5 mile) Al Qurnah District ( Hai Al Sharash, Hai Al Nussayr, Hai Al Salaam, Al Qurnah Centre) |
| Project Cost | US$ 1,755,155 |
| Duration | Original: 12 months 1st Revision: 14.5 months 2nd Revision: 18 months |
| Approval Date (SC) | 04 Oct 2007 | Starting Date | 15 Oct 2007 | Completion Date | Original: 15 Oct 2008 1st Ext: 31 Dec 2008 2nd Ext: 15 April 2009 |
| Project Description | Provide an integrated package of community-based interventions to increase availability, quality and access to basic services in selected communities in Basra. Schools are identified in communities of Basra governorate as entry point for coordinated interventions in education, health and water and sanitation. |

# Development Goal and Immediate Objectives

Improving access and quality of basic social services in disadvantaged communities through an integrated community approach. In selected communities in Basra governorate, Iraqi authorities will be able to fulfil their obligations towards vulnerable populations in terms of responding to their immediate needs for basic social services in a transparent and equitable manner in line with democratic principles and international human rights standards, contributing to the achievement of the following MDGs: enrolling all children in primary school (MDG-2), eliminating gender disparities in primary and secondary education (MDG-3), reducing by half the proportion of people without access to safe drinking water (MDG-7), reducing child mortality (MDG-4) and poverty reduction (MDG-1). Immediate Objectives are: Improve participation and retention as well as access to and quality of education in 13 schools in Basra Governorate; Improve access to potable water and sanitation services in the communities around the selected schools; Improve the quality of basic primary health and nutrition services in the communities around the selected schools; Assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children.

# Outputs, Key activities and Procurement

| Outputs | The overarching output will be to upgrade 13 schools to Child-Friendly status; School participation and retention as well as access of primary school children will improve; Availability and improved quality of water and wastewater disposal will increase; Sanitary facilities for school children, especially for girls will be available; Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment; 2 PHC Centres (PHCCs) serving the 13 local communities will be rehabilitated; The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities; Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities; Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project. Parent Teacher Associations (PTAs) will be engaged in project implementation. |
| --- | --- |
| Activities | Improved school participation and retention of primary school children Procurement from inside Iraq and distribution of school furniture, recreational materials, school sanitation kits and garden kits to all selected schools; Establishment of safe recreational areas in all selected schools; Creation of school gardens at all selected schools. Availability and improved quality of water and wastewater disposal as well as sanitary facilities for school children, especially for girls will increase through: Training of all teachers in the selected schools in health and hygiene promotion. Hygiene promotion and community awareness campaigns in select communities. Sanitary facilities for school children, especially for girls will be available Rehabilitation/ construction of water and sanitary facilities in schools where required. Selected PHC/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment Procurement and distribution of essential/basic medical supplies and equipment for PHCCs/ MCH units. 2 PHCCs serving the 13 local communities will be physically rehabilitated through: Physical rehabilitation of some PHCCs if required (based on the preliminary assessment of the facilities considered for this project); Training of PHC health workers on basic health and nutrition services, including growth monitoring and counselling activities for parents of children suffering from malnutrition, as well as systematic referral of all severe cases of malnutrition to nutrition rehabilitation centres. The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities Support community health and nutrition programmes through community volunteers (former community child care units), in order to strengthen growth monitoring, health and nutrition promotion and referral to PHCCs. This output will also be supported by UNICEF national country programme. Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities through; Supporting psychosocial training for teachers, health workers, parents, youth and other community members in psychosocial intervention and care for children and youth and provide supplies for use in existing spaces (such as schools, health centres and youth centres) in establishing child friendly spaces/psychosocial activities. Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, communities are exercising ownership of the project and PTAs will be engaged in project implementation through: Conducting capacity building courses for relevant government authorities on planning, management and monitoring of area-based programmes; Conducting social mobilization around selected schools to activate PTAs and involve them in planning, implementation and monitoring of the project to the extent possible; while at the central level advocating for government support to the expanded role of PTAs. |
| Procurement (major items) | Recreational and sanitation kits and essential/basic medical supplies and equipment for PHCCs/ MCH units |

| Funds Committed | $ 1,703,037.00 | % of approved | 97% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 1,073, 040.00 | % of approved | 61% |
| Forecast final date | 15 April 2009 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Availability and improved quality of water and wastewater disposal will increase | During the 4th quarter, the following capacity development activities were carried out: 4 Water Authority Engineers participated in the training on Implementation and Supervision of Water Distribution Network in Amman during October 2008 - using funds under the project and other resources. 30 Water Authority Engineers participated in the two day Hygiene Awareness workshop in Basra in October 2008. In addition, some of the resources from the project were also used to develop advocacy materials for the Global Hand Washing Day. The contract for rehabilitation of Alfaiha complex has been awarded and work commenced. | % of planned | 25% |
| --- | --- | --- | --- |
| Sanitary facilities for school children, especially for girls will be available | Rehabilitation of water and sanitation facilities completed in 5 schools bringing the total number of completed schools to 13. In addition physical assessment and BoQs completed for 4 additional schools, where similar activities will be implemented using funds saved during project implementation. | % of planned | 71% |
| Selected PHCCs/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/ equipment | Detailed list of supplies and equipment for PHCCs and MCH units have been drafted by Directorate of Health (DoH) counterparts and will be provided to UNICEF shortly for procurement in 2009. | % of planned | 25% |
| Two PHCCs serving the 13 local communities will be physically rehabilitated | The Integrated Community Initiative for Children (ICIC) Team established within the Governorate Council in Basra had identified two PHCCs (Al Qurnah and Shat Al Arab) for rehabilitation. It was found that Shat Al Arab PHCC is in good condition while Al Qurnah PHCC requires extensive rehabilitation. The DoH sent a letter to UNICEF explaining that Al Qurnah PHCC serves a large population and has not been rehabilitated for several years due to scarcity of funds, and requested to use the total amount of US$ 130,000 for the rehabilitation of Al Qurnah PHCC. Rehabilitation has been completed and PHCC is handed over to DoH. | % of planned | 100% |
| The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities | Proposals for capacity building by DoH Basra have been shared with UNICEF. The plans include support to community volunteers to improve growth monitoring, health and nutrition promotion and strengthening referral to PHCCs. The activity is scheduled to be implemented in the 1st quarter of 2009. | % of planned | 30% |
| Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities | The school-based psychosocial care project has enabled the training of 255 teachers in Basra (70 male and 185 female) who are now providing psychosocial care to about 8112 children (3106 male and 5006 female) in 16 schools. Monitoring visits have been conducted in 3 randomly selected schools. As part of the cascade trainings on Child and Youth Participation, 28 children and young people (19 male and 9 female) have participated in awareness raising sessions on concepts and practices of child and youth participation in Basra, opening channels for young people to become proactive in advocating for community development activities amongst adults and decision makers. Another 50 young people will attend the sessions in January 2009. | % of planned | 100% |
| Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, communities are exercising ownership of the project, and PTAs will be engaged in project implementation | The ICIC governorate Council Team in Basra including the local council representatives from the selected districts are coordinating all activities being implemented by various line ministries/departments with support from UNICEF contracted Chief Facilitators. Partnership has been initiated with the NGO “People in Need” for mobilizing PTAs for their role in the education of children in the 13 schools (This activity is funded through other UNICEF resources). |  |  |

# Qualitative achievements against objectives and results

Qualitative achievements will be assessed once the project is completed.

Names and Locations of Facilities being rehabilitated under B1-32

Status of school rehabilitation in Basra

| No | Governorate | District (HIC) | Sub dis-village | School Name | Progress (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | Basra | Al Basra | Hay Al-Hadi | Al Wahda Al arabiya | 100% |
| 2 | Basra | Al Basra | Hay Al-Hadi | Arafat | 100% |
| 3 | Basra | Al Basra | Al-Tanomah | Al Somod | 100% |
| 4 | Basra | Al Basra | Shat Al-Arab | Shat Al Arab | 100% |
| 5 | Basra | Al Basra | Hay Al-Hussain | Al Maseer Al Wahid | 100% |
| 6 | Basra | Al Basra | Hay Al-Qibla | Balqees | 100% |
| 7 | Basra | Al Basra | Al-Zubair | Al Jazira Al Arabiya | 100% |
| 8 | Basra | Al Basra | Hay Al-Qibla | Al Hussain | 100% |
| 9 | Basra | Al Qurnah | Al-Sharash Dist. | Al Sharash | 100% |
| 10 | Basra | Al Qurnah | Al-Sharash Dist. | Al Muthanna | 100% |
| 11 | Basra | Al Qurnah | Hay Al-Nusayr | Al Thura | 100% |
| 12 | Basra | Al Qurnah | Hay Al-Salam | Al Shema Al Arabiya | 100% |
| 13 | Basra | Al Qurnah | Al-Qurna center | Al Qurna | 100% |
| 14 | Basra | Al Basra | Shat Al-Arab | Sinjar | Under bidding |
| 15 | Basra | Al Basra | Hay Al-Hadi | Poor Saeed | Under bidding |
| 16 | Basra | Al Basra | 5Mile | Diyala | Under bidding |
| 17 | Basra | Al Basra | Kut Al-Hajaj | Al-Risafy | Under bidding |