# United Nations Development Group Iraq Trust Fund

# Project #:B1-32

# Date and Quarter Updated: April- June 2008

# Part One: Summary

| Participating UN Organisation: UNICEF | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Basra Directorates of Education in close collaboration with Ministries of Education Baghdad |

| Title | Integrated Community-based Services Project Basra |
| --- | --- |
| Geographic Location | Governorate: Basra |
| Project Cost | US$ 1,755,155 |
| Duration | 12 Months |
| Approval Date (SC) | 4 Oct 2007 | Starting Date | 24th Oct, 2007 | Completion Date | 31st Dec, 2008 |
| Project Description | Provide an integrated package of community-based interventions to increase availability, quality and access to basic services in selected communities in Basra. Schools are identified in communities of Basra governorate as entry point for coordinated interventions in education, health and water & sanitation. |

# Development Goal and Immediate Objectives

Improving access and quality of basic social services in disadvantaged communities through an integrated community approach. In selected communities in Basra governorate, Iraqi authorities will be able to fulfil their obligations towards vulnerable populations in terms of responding to their immediate needs for basic social services in a transparent and equitable manner in line with democratic principles and international human rights standards, contributing to the achievement of the following MDG goals: enrolling all children in primary school (MDG-2), eliminating gender disparities in primary and secondary education (MDG-3), reducing by half the proportion of people without access to safe drinking water (MDG-7), reducing child mortality (MDG-4) and finally poverty reduction (MDG-1). Immediate Objectives are: Improve participation and retention as well as access to and quality of education in thirteen schools in Basra Governorate; Improve access to potable water and sanitation services in the communities around the selected schools; Improve the quality of basic primary health and nutrition services in the communities around the selected schools; Assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children.

# Outputs, Key activities and Procurement

| Outputs | The overarching output will be to upgrade thirteen schools to Child-Friendly status School participation and retention as well as access of primary school children will improve; Availability and improved quality of water and wastewater disposal will increase; Sanitary facilities for school children, especially for girls will be available; Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment; Two PHC centres serving the thirteen local communities will be physically rehabilitated; The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities; Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in thirteen communities; Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project, Parent Teacher Associations (PTAs) will be engaged in project implementation. |
| --- | --- |
| Activities | Improved school participation and retention of primary school children Procurement from inside Iraq and distribution of school furniture, recreational materials, school sanitation kits and garden kits to all selected schools; Establishment of safe recreational areas in all selected schools; Creation of school gardens at all selected schools; Availability and improved quality of water and wastewater disposal as well as sanitary facilities for school children, especially for girls will increase through: Training of all teachers in the selected schools in health and hygiene promotion. Hygiene promotion and community awareness campaigns in select communities. Sanitary facilities for school children, especially for girls will be available. Rehabilitation/ construction of water and sanitary facilities in schools where required; Selected PHC/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment Procurement and distribution of essential/basic medical supplies and equipment for PHC centres/ MCH units. Two PHC centres serving the thirteen local communities will be physically rehabilitated through Physical rehabilitation of some PHC centres if required (based on the preliminary assessment of the facilities considered for this project); Training of PHC health workers on basic health and nutrition services, including growth monitoring and counselling activities for parents of children suffering from malnutrition, including systematic referral of all severe cases of malnutrition to nutrition rehabilitation centres; The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities. Support community health and nutrition programmes through community volunteers (former community child care units), in order to strengthen growth monitoring, health and nutrition promotion and referral to PHC centres. This output will also be supported by UNICEF national country programme. Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in thirteen communities through; Supporting psychosocial training for teachers, health workers, parents, youth and other community members in psychosocial intervention and care for children and youth and provide supplies for use in existing spaces (such as schools, health centres and youth centres) in establishing child friendly spaces/psychosocial activities. Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project, PTAs will be engaged in project implementation through: Conducting capacity building courses for relevant government authorities on planning, management and monitoring of area-based programmes; Conducting social mobilization around the selected schools to activate the PTA and get it involved in the planning, implementation and monitoring of the project to the extent possible; while at the central level advocating for government support to the expanded role of the PTAs; |
| Procurement (major items) | Procurement and distribution of recreational and sanitation kits and essential/basic medical supplies and equipment for PHC centres/ MCH units |

# Part Two:

| Funds Committed | US$ 753,889.83 | % of approved | 46% |
| --- | --- | --- | --- |
| Funds Disbursed | US$158849.53 | % of approved | 10% |
| Forecast final date | 31.12.08 | Delay (months) | N/A |

# Quantitative achievements against objectives and results

| Availability and improved quality of water and wastewater disposal will increase; | As agreed with MOMPW, Al-Faihia complex compact unit to be rehabilitated in Shat Al Arab district. BOQs developed and waiting for approval by Water Authority. Trainings scheduled for July- August. | 0% of planned | 10% |
| --- | --- | --- | --- |
| Sanitary facilities for school children, especially for girls will be available. | BOQs for rehabilitation of sanitation facilities in 13 schools agreed upon with DOE and included in the rehabilitation contracts for schools | 0% of planned | 52% |
| Selected PHC/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment | Details of supplies and equipment for PHCs and MCH units being agreed upon in consultation with DOH counterparts. Lists developed but awaiting approval. | 0% of planned | 25% |
| One PHC centre serving the 13 local communities will be physically rehabilitated | DOH Basra submitted a request for rehabilitation of Al Qurna PHC centre instead of rehabilitation of two PHC centres with the available funding. (Details of this change notified to the UNDG- ref B1-32- Change of Scope). Contract for rehabilitation issued but rehabilitation work delayed due to recent insecurity and clashes between Government forces and Shia Militias. Rehabilitation work progress satisfactory. | 0% of planned | 35% |
| Quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities | Meeting of Integrated Community Initiative for Children (ICIC) Team in Basra Governorate Council held on 24th March. Plans for capacity building by DOH Basra being developed for improving the quality of health and nutrition services. Training plans developed and awaiting approval. | 0% of planned | 20% |
| Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities | Partnership mechanisms for this activity are being identified. TOT for teachers training on psychosocial services scheduled for July 2008. NGO identified to conduct the TOT. | 0% of planned | 15% |
| Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project, PTAs will be engaged in project implementation. | Governorate Council ICIC established in Basra Governorate with representation from all line ministries and District Councils. Regular consultations being held to implement the project in a coordinated manner. Modalities for linking up with PTAs and community are being worked out. | 0% of planned | 35% |

# Qualitative achievements against objectives and results

Project just started and might be too early to comment on qualitative achievements, will be reported in future,

Names & Locations of Facilities being rehabilitated under B1-32

| Governorate | District | Sub dis/village | School Name | PHC | WESH |
| --- | --- | --- | --- | --- | --- |
| Basra | Basra Central | Al Qibla | Al-Shaheed Amjad Ali Al Ghareeb for girls/ Al Hussain for girls |  |  |
|  |  |  | Balqees for girls/Al jihad for girls/ Al-l'eamar for boys |  |  |
|  |  | Al Hadi | Arafat for girls |  |  |
|  |  |  | Al- Wehda for girls/Al Safa for girls |  |  |
|  |  | Al-Husain City Centre | Al-Maseer Al Wahid for boys/Bilad Al Nahrein for boys/Al Tajdeed for boys |  |  |
|  | Al Zubair | Al Hassan Basri | Al- Jazeera Al Arabiay (mixed)/ Tabarak Al Rahman (mixed) |  |  |
|  | Al Qurna | Al Qurna | Al Qurna for girls/Al Aqeeda Al Hashimiya for girls | Al Qurna PHC |  |
|  |  |  | Al Thura for boys/Al Kawakib for boys/Al Mursaleen for girls |  |  |
|  |  | Hay Al Jamia | Al Hadatha for girls/Al- Shema Al Arabia for boys/Al Abrar for boys |  |  |
|  |  | Al Sharash | Al Sharash for boys/Al Shaheed Abdul Hassan for boys |  |  |
|  |  | Al Sharash | Al Muthanna for boys. Al Iqtidar for girls |  |  |
|  | Shat Al Arab | Shat Al Arab | Al-Somod for boys/ Thawrat Al Hussain for boys |  | Al Faihia Complex |
|  |  |  | Shat Al Arab for girls / Al- Dhifa Al Sharkia for boys/ Al- Hamad for girls |  |  |