NINTH Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: |  | Old Cluster: Education |
| --- | --- | --- |
| WHO |  | New Sector: SOT Education |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| B1-25: Strengthening school health services at Primary School level through implementation of the Health Promoting Schools |  | 4 ATLAS Award: 54859 ATLAS Project: 66859 |

| Reporting Period: |  | Project Budget |
| --- | --- | --- |
| 1 July- 31December 2008 |  | US$ 1,757,280 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Ministry of Health Ministry of Education |  | All governorates |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| - COSIT Central Organization of Information and Statistical Technology - HPSI Health Promoting schools Initiative - IBSP Integrated Basic services Project - MDG Millennium Development Goals - MOH: Ministry of Health - MoE Ministry of Education - MoEn Ministry of Environment - PTA Parent Teacher Association - UNICEF:United Nations Children Fund |  | Approved 14 April 07 Duration: 12 months/ The project implementation is currently ongoing. First extension: 31 September Second extension:31 March 2008 Third extension:31 July 2009 |

# NARRATIVE REPORT FORMAT

# Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

The aim of the project is to assist Ministry of Health (MoH) and the Ministry of Education (MoE) to strengthen the school health services at primary level through updating the health education concepts into school curriculum in all governorates.

Main objectives are to:

- Implement health promoting schools programme (life skills education and psychological first aid) implemented in 46 schools in 18 governorates (2 schools in each governorate except for Baghdad governorate 12 schools in (Karch and Rasafa).

- Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children as part of the Strengthening Primary Health Care system.

- Raise awareness among community on Health Promoting Schools Initiative and the role of Parent Teachers Association (PTA) meetings

- Hearing aids and eyeglasses provided for needy students and for those with Musclo- skeletal abnormalities, referred to specialists.

- Effective partnerships between all stakeholders including the community  to build public awareness and strengthen demand for the school health services

The expected outcomes of the program within this reporting period were:

- (100) teachers and school staff trained on health promoting school initiative in 46 schools in all governorates and MoH officials informed about health promoting school Initiative.

- School health including psychological first aid services strengthened and maintained at all levels through successful coordination approaches between schools and primary health care centers.

- screening for visual, hearing problems and Muscular-skeletal abnormalities of all students in the 150 schools at 8 governorates( completed)  and 100 teachers trained on detection of visual ,hearing defects and Musclo- skeletal abnormalities

- Provision of eyeglasses and hearing aids to school children with visual and hearing difficulties and those students with musculo skeletal abnormalities referred to specialists completed.

- Community committees established to build public awareness in demanding for school health services.

The Ministry Of Health (MoH) is WHO’s and the UN Health and Nutrition Sectors primary partner. The overall goal of the MoH is to transform the centrally-planned and curative care-based services into a new system based on prevention and evidence-based, equitable, high quality accessible and affordable primary health care (PHC). This strategy is described in the National Development Strategy published in 2007.

b- Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI  :

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

NDS Targets by 2010:

- (Target) (4) Completing all curriculums in primary and secondary education levels for all girls and boys

- (Target) (5) Waiving off gender discrimination in all educational levels

ICI Target by 2010

- Reduce illiteracy with 50% (Baseline UBN 31.8% of population have no access to education)

- Ensure coverage for priority health programme in remote areas, targeting vulnerable group and in carrying outreached activities, and community mobilization. ( 4.4.1.4 of the 2008 JMM)

Working in close collaboration with government counterparts at both the central and regional levels, the UNCT has committed to reinforce its support to institutional capacity-building and the provision of key basic services in addressing urgent Iraqi needs and priorities.  This realignment of UNCT Sector (SOT) activities shall remain flexible in responding to the evolving operational context within the overall strategic framework.

The implementation of the health promoting schools approach in Iraq is based on the WHO health promoting schools initiative and the UNESCO FRESH manuals. It will assist MoH and MoE in developing new school policies and guidelines and provide teachers with the necessary support to enable them to promote health at schools. It is expected that this will lead to an improvement in the standard of the health services and health status of school children and community through increasing their awareness about main health problems and its preventive measures. Also it will lead to increased self esteem of children and decrease of risk taking behavior in later life. As a result, the program will contribute to the following UN Millennium Development Goals (MDG):

- Achieve universal primary education (MDG2)

- Promote gender equity and empower women (MDG3)

- Reducing child mortality (MDG-4)

- Poverty reduction (MDG-1)

- Improve maternal health (MDG5)

The project addresses the health of students, school personnel, families and community members. Currently, the health status of school children is deteriorated due to lack of proper and periodic health care, inefficient pre-entry primary school check up, lack of awareness on main health problems and psychosocial well being.

The project proposal is fully in line with the 2005-2007 UN Strategy for Assistance to Iraq and  conforms closely to the priorities expressed by the Iraqi Authorities during the July 2005 Donors’ conference -– embracing  education, water & sanitation and health needs and demonstrating good impact, contributing to the overall targets of reducing morbidity and mortality. Specifically the project addresses the following clusters and some of the relevant matrix outcomes (underlined) from the Joint UN-Iraq Assistance strategy:

| Sector | Matrix outcomes |
| --- | --- |
| Education Cluster-B | To enhance access to all levels of education with special reference to disparity reduction (gender, geographic, ethnic, socio-cultural, economic and other disparities); To improve rates of retention, completion and participation at all levels of education; To improve learning outcomes at all levels of education.\ |
| Health& Nutrition Cluster-D | 50% reduction in under five and infant mortality; 15% reduction in maternal mortality; Increase access to quality health care services especially for vulnerable group and un-reached; Enhance disease prevention and control including HIV/Aids. |

Moreover this program is also in line with the Dead Sea strategic meeting held in July 2006, since this program ensures the provision of basic services and education

c. Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

Government of Iraq

WHO have a long established partnership with the Government and continues to enjoy very close collaboration with the Ministries of Education, Health, and Environment in the Directorates of the Governorates (DoD) where the project will be implemented.  WHO works very closely with these line Ministries starting from the needs assessment to joint implementation of activities, supervision, monitoring and evaluation, to project closure. It is worth noting that partners in the line Ministries are very familiar with the WHO modus operandi and have benefited from multiple capacity building opportunities in the integration of health and education sector programming. Coordination is facilitated by WHO national staff based in Baghdad and other sub offices in south/center and Kurdistan Regional Governorate (KRG).

Communities and Schools

By introducing the health promoting schools initiatives (HPSI) in 20 schools in Baghdad and working with the communities and parents teachers association in the selected areas, WHO are encouraging and enabling them to in identifying children‘s needs and priorities. School health programme managers at central and governorate level assisted with the implementation of the school health screening component within the UNICEF Integrated Basic Services Project (B1-19 in 2005-2006). For successful achievement of the health and education goals, WHO draws on previous projects like the B1 19 and on formal and informal agreements with public and private sectors as well as the civil societies. Moreover, community participation is crucial for a successful education system in Iraq.  This entails the change of community behaviour and awareness for education and school health services provided at PHC level especially after the deterioration in this service over the past few years.

- Human Resources

a.	National Staff & Consultants: Provide the number and role (operation/ programme)

- For the implementation of the various project components, one medical officer has been supporting the implementation of the project.

- On the other hand, WHO network of national focal points in Baghdad, Basrah, Mosul, Erbil, Babil, and Suliemania actively participated in providing their technical support in  the implementation process in close coordination and collaboration with stakeholders.

b.       International Staff: Provide the number and role (operation/programme)

- One international staff at WHO/Iraq office will provide good management and

Coordination of the project throughout the entire implementation period

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- The project started in early October (beginning of the new school term 2007-2008) and implementation is ongoing according to the project workplan.

- Main achievements for this reporting period include the training of trainers for central and local supervisors at DoH and DoE. This aims at strengthening capacity on health promoting schools, psychosocial interventions and school health screening. It also includes printing of the environmental assessment and school health screening  forms, orientation and advocacy meetings, provision of supplies and equipment which are needed for the implementation of health education and school health screening components of the project building on the previous experience of school health screening within the Integrated Basic services(IBSP) Project B1-19 with UNICEF.

- WHO/Iraq continues to maintain a low profile, for obvious security reasons, to avoid any possible negative repercussions to premises and staff, in particular. In line with this policy, international staff remains based in Amman and provide guidance and support to national staff and monitors operations within Iraq. When  security situation was permitting, short missions, to Baghdad, south /center and Kurdistan region were undertaken.

- WHO/Iraq provides also technical support to the national staff in MoH and MoE and monitors the implementation of the activities through the continuous communication with the project's focal points through video/ teleconferences.

- The Ministry of health will be the key stakeholder at the national level to ensure that the integration of school health in PHC System which will work in close co-ordination and partnership with the other line ministries such as the Ministry of Education and Ministry of Environment to endorse the schools/ communities selected for needed interventions and provide policy guidance in school health. Ministry of environment is usually informed about the environmental aspects at schools as reported by the MoEv monitoring team during their periodic visits and the rapid environmental school assessment. The information will be circulated to all line ministries and requested for action to be taken.

- At the Governorate level, the respective directorate was jointly involved in the assessment, implementation and the subsequent monitoring & evaluation processes. At the central level, the establishment of steering committee which consists of members of related stake holders including the community local leaders/representative of PTAs with the responsibility to oversee the implementation of the activities, follow-up on the interventions and therefore ensure the convergence of basic services.

- The role of Ministry of Health is to integrate the work between partners and identify the role of each partner involved in the process including contractors and the organization for contract tendered for cars and supplies.

Quality control at the project sites was ensured through regular supervision by local national staff and project focal points at peripheral level that will make random visits to a statistically significant number of project sites. The Local Authority staff will be involved in every step/process and monitoring during implementation

At the onset of the project, WHO through its focal points have established a base line data related to the project outputs. Post completion of the project, the monitors would once again assess the outputs against the established base line data to determine the outcome of the project.

Moreover WHO has been working closely with cluster members in different thematic areas e.g. UNICEF on immunization campaigns and maternal and child health; FAO and UNIDO in food safety; and World Bank in health care financing and national health accounts. There is constant dialogue with other UN health cluster members such as WFP and UNFPA to ensure integration in the areas of malnutrition and emergency obstetric care.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

WHO has well established procurement procedures and goods are generally delivered to Baghdad under international insurance coverage. The procurement process is being carried out through the application of the international bidding process for most of the goods to be procured, based on WHO rules and regulations, which are geared to ensuring the quality, efficiency and cost effectiveness. In a few cases, local procurement is applied and follows a set of clear documented procedures.

WHO corporate procurement manuals followed are providing strict guidance on procedures for international and local procurement. They cover standard procedures of invitation to bids, bids opening, bids analysis, bids review and contract award, and conditions abiding the winner and WHO. There are specific committees for QC/ QA at each stage of the bidding process.

Procurements and shipment of project material is a challenge in Iraq and delays due to difficulties at border crossings, processing and remote management is often impacting the management of the project.

In order to establish the needs of the supplies and medical equipments for the school health screening (Audiometers, Ophthalmoscopes and Snellne's charts), a needs assessment was carried out at central level in close collaboration with directorate of health at governorate level. Consultations between WHO and the project steering committee were held to agree on the final requirements.

Bill of quantities with detailed generic technical specifications for the agreed items was prepared, with a cost break down. After delivering the requested supplies and equipments to the end users at MoH , the final payment to the supplier will be processed according to the purchase order.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

WHO and the steering committee are maintaining regular communications through various Tele conferences and meetings to evaluate the implementing process and impact and to identify constraints and solutions in order to ensure a flexibly efficient approach. The project implementation is also managed by the district directors. Technical national project officer from its base in Amman together  with the WHO national staff network at Governorates (Erbil, Mosul, Basrah and Baghdad), work closely with the MOH/district director through teleconferencing and direct meeting in Amman. Information flow will be streamlined for sharing with partners, planning, decision making and for advocacy purposes.

Four focal points are appointed and each is responsible for 3 governorates except for Baghdad, the assigned focal points were supervising and monitoring 6 governorates. These Focal Points work closely with the DoH on ensuring proper implementation. They have to oversee the implementation at the governorate level and should report to WHO on all activities implemented with detailed information on the achieved activities, constraints during implementation with the possible suggested solution.

These focal points will report to WHO offices in the governorates mentioned above, which in turn will convey the reports  to Amman, the base for consolidation and for action to be take  if necessary.

Financial tracking will be according to WHO rules and regulations in issuing financial statements related to commitment and disbursement during the implementation of the project components.

Whereas, at the end of the project, the impact will be assessed by measuring performance-based indicators and compare them to baseline information collected at project implementation

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

Universal access to basic education and the achievement of primary education by the world’s children is one of the most important goals of Millennium Development Goals and A world fit for children. The recent Iraq Family Health Survey 2006/07 indicates that access to essential health services and education is a major problem for the conflict-affected communities. The results showed high proportion on non -attendance at school among age group 5-9 years(38.7%) reflects the fact that children are being enrolled late for school, a finding that was also obtained in the 2006 MICS-3. Also, the results of the survey showed gender disparity in access to education. The percentage of females who have not attended school is approximately twice as high as the percentage of males (26.8% and 14.6%respectively).  This survey has contributed in obtaining baseline data and updating health and education indicators, some of which are related to children mortality and morbidity and will have a direct application in assessing the impact of the project with regard to improvement of education and combating poverty, empowering women and protecting children from water and food borne diseases.

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries

During the reporting period, the following activities were implemented.

- Introduction of the health promoting schools and psychosocial support into school curriculum of the 46 schools involved in the project. (100% achieved). Training of 80 doctors and 50 teachers on health promoting school initiatives and health education.

- 18 national training courses for 450 doctors, technicians and teachers on early detection of visual errors among students screened and detection of hearing difficulties by using audiometers and examination of Musclo skeletal problems.

- Screening of 6615 students for visual and hearing difficulties and Musclo-skeletal abnormalities were conducted in 147 primary schools (Target 150 schools) in 8 governorates (Baghdad Karch and Rasafa, Missan, Basrah, Theeqar, Najaf and Suliamania, Muthana and Wasit) to improve the health status of students for better education performance. Screening of student in three schools in Al-Sader city was postponed due to security situation  at time of implementation of the project

- 19 national training activities were successfully for 280 doctors and 100 teachers on psychosocial support was conducted to update their knowledge on health education and key health massages, communication skills and psychological first aid services.

- Assessment of the environmental health situation at the 46 schools implementing the health promoting schools initiative was conducted. Data entry completed and finalization of the report is in process.

- Data editing and entry of the school health screening was completed. Data analysis and report writing are in process.

- Six technical meeting of the members of the steering committee to review the results of the school health screening.

- 72 advocacy meeting for 2,844 community leaders, teachers and parent were held at governorates in collaboration with DoH and DoE to raise awareness of the community on health and hygiene and the importance of participating in making the school environment a health and friendly one (100% achieved)

- Procurement of equipments to School health unit in each directorate of health with a total cost of USD 15,000

- Procurement of supplies snellen’s charts(100) for the health screening component of the project(100% achieved)

- 10  supervisory visits by six members of the steering committee to primary schools in Baghdad, Basrah, Theeqar, Wasit, Muthana, Mosul and Suliamaniya, Babil and Karbalah to follow up the implementation of the project.

- Monthly evaluation report is submitted by the project focal points on the progress of the implementation of the projects at governorate level besides the daily communication with MoH and MoE focal point to provide technical assistance and solutions for most of the difficulties facing the implementation process.

b-Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

- The implementation of the health promoting schools approach in Iraq have assisted MoH and MoE in developing new polices and guidelines, and provided teachers with the necessary support to enable them to promote health.

- Improvement in the standard  of the health services provided to students leading to a reduction of morbidity and mortality rates among all targeted groups and improve student’s performance. This was achieved through screening of children for visual, hearing difficulties and detection and management of musclo skeletal abnormalities. Also it will lead to increased self –esteem of children and decrease of risk taking behaviour in later life.

- The introduction of health education programme within the school curriculum and the up-grading of schools to a more child friendly status, coupled with interventions on health education on various health key practices and raising awareness among communities around the schools including families for the school children and community leaders on importance of health promoting schools and the active participation of the parents through the revitalized parent teachers association have directly contributed to improvement the health status of children and the school environment.(The assessment of school environment have shown great  improvement regarding health and hygiene 83.6% in comparison to 48.5% before the implementation of the project.

- It also focused on building the capacity of human resources (health professionals and teachers) through upgrading their skills and knowledge on health and psychosocial support  and provision of equipment and supplies in order to provide good quality service.

c-Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

There have been several elements affecting the timely implementation of the project:

- Security concerns in the country continue to be a major limiting factor and are constraining the presence of international expertise inside the country.

- Conducting trainings in other governorates is becoming increasingly difficult and expensive as for facilitators from Baghdad, they need transportation support for return trip and work inside the governorate.

- Lack of coordination between MoH and MoE

- Difficult access to some hot districts, such as in Al Sader city and in Baghdad/ Karch  district and many changes  in holidays and school  vacations.

- Other issues that are playing a major role in delaying the supervision and monitoring of the implemented activities as scheduled are Violence and insurgence, attacks against Health professionals, lack of adequate resources and high turnover of senior officials

Lessons learnt:

- The long years of war and sanctions have severely weakened the school health services in Iraq; More efforts and  resources are needed to strengthen the school health services.

- Human resources development is an important need in Iraq; for proper functioning of proper school health services health services, there is need for developing of national policies, strategies and procedures.

- Lack of cooperation between MoH, MoE and other related ministries in terms of technical consultations.

- Sustainability of quality heath services with periodic examination of students will lead to improvement in the health and performance of students at school.

d- List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The main implementing counterpart of the project is MOH represented by school health unit/Directorate of Public health and primary health care in close coordination with MoE. WHO is working closely with line ministries such as MOH, MoE. MoP and MOEv. The partnership provides a forum through which members can combine their strengths and implement solutions that no one partner could achieve alone. The partnership supports national training programmes; management policy, and the monitoring and evaluation system.

In addition, the MOH, MoE and DoH, DoE personnel continue to be fully engaged in all implementation stages so as to ensure the ownership of the project by the targeted stakeholders once the project is completed.

e- Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The conducted training activities and advocacy meeting   during the reporting period have taken into consideration the gender balance where possible. Out of a total of 3440  health professionals, teachers and community leaders trained, 1621 were female (47%), Cross cutting issues related to the project will be reflected from the regular school visits, the facilitators who will assess the relative levels of activities /involvement of the Parent Teacher Association (PTA) in each school, social mobilization and community participation. Assessment reports will be obtained by the facilitators which will provide WHO with valuable insight on the behaviours of the children at primary schools implementing the health promoting school Initiative and their families living in the area of project implementation. Moreover, the implementation of this project is focused to School children who are more vulnerable to the mental health effects of the ongoing conflict situation.

The project is expected to generate direct and indirect employment; already about 112 job opportunities inside Iraq were created through subcontracting private companies for transportation and provision of supplies needed for the project

- Future Work Plan

  - Summarize the projected activities up to the end of December 2008 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- Continue the support MoH and MoE  in the implementation of the health promoting school initiative through conducting of 18 two days refreshing courses on health promoting schools and psychosocial support at governorate level for  head masters,  health professionals, and teachers  on health promoting  schools.

- Training of (100) teachers and health personnel working at primary health care  centers on providing first aid psychological and basic mental health care for children with psychosocial problems.

- 4 days refreshing training course of 50 doctors and teachers   on school health screening.

- Completing the school health screening for 154 students in three schools in Al-Sader city with environmental assessment of schools.

- Support the pre-entry school examination for students attending the first level at primary schools

- Advocacy among community and religious leaders through training and distribution of    educational materials and strengthening the Parent Teachers Association (PTA) meetings

- Provision of eyeglasses and hearing aids to those screened students in need.

- Follow up the management of referred students with muscle skeletal abnormalities by the Orthopaeditians at hospitals.

- Follow up the referred student with psychological problems by psychologist at hospitals.

- Finalization of the data analysis of the school health screening component and finalization of the report.

- Printing of IEC material on health promoting schools.

- Six monthly Performance Indicators assessment

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1: Health promoting schools programme implemented in 2 schools in each governorate and 10 Schools in Baghdad governorate (Karch and Rasafa). |
| IP Output 1.1 Improve health of school personnel, families and community members as well as students | Indicator 1.1.1 Number of schools implementing HPS | 22 | 46 | 46 | Monthly reports from MoH and MoE | 2 schools in each governorate and 12 in Baghdad |
|  | Indicator 1.1.2 Number of community advocacy meetings | 0 | 76 | 72 | Monthly reports from MoH and MoE | Advocacy meeting for teachers, community leaders and parents within the PTA's |
| IP Output 1.2 (100) teachers and school staff trained on health promoting school initiative in 46 schools in all governorates. | Indicator 1.2.1 Number of teachers and school health staff trained | 0 | 100 | 150 | Monthly reports from MoH and MoE | Teachers were trained on important health and hygiene key massages |
|  | Indicator 1.2.2 |  |  |  |  |  |
| IP Outcome 2: Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children. |
| IP Output 2.1 Capacity of MoH officials strengthened on health promoting school Initiative and school health screening activities | Indicator 2.1.1 Number of doctors and paramedicals trained on health education | 0 | 200 | 162 | Monthly reports from MoH and MoE |  |
|  | Indicator 2.1.2 Number of teachers trained on visual aquity check up |  |  |  |  |  |
| IP Outcome 3: Achieve 100% coverage of students at 150 primary school in 8 governorates by health screening and mental health services. |
| IP Output 3.1 (300) teachers trained on detection of visual defects in 150 schools involved in Health screening | Indicator 3.1.1 Number of teachers trained | 0 | 300 | 150 | Monthly reports from MoH and MoE |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| IP Output 3.2 Primary school children with visual and hearing difficulties provided with eyeglasses and hearing aids and those with muscular skeletal abnormalities referred to specialists | Indicator 3.2.1 Number of students screened | 4500 | 8000 | 6615 | Monthly reports from MoH and MoE | Students in 147 schools in 8 governorates |
|  | Indicator 3.2.2 Number of students provided with eye glasses | 0 | 75 | 20 | Monthly reports from MoH and MoE |  |
| IP Output 3.3 Provision of supplies and equipments as Audiometers, visual and hearing aids for students in need. | Indicator 3.3.1 Number of audiometers and snellen's charts | 42 Audiometers | 80Audiometers 100 snellen's chart | 60 100 | Receiving reports by MoH | The audiometers and snellen's charts were used in screening of students |

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Highlight any new challenges/constraints, mitigation strategies and lessons learned during the reporting period and monitoring processes and assessments, evaluations and studies undertaken/published in the period. Attach documents.

- Attach any available photos relevant to the project.