CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

30 June 2008

| Participating UN or Non-UN Organization: | World Food Programme | UNCAPAHI Objective(s) covered: | Objectives 2,4,6 and 7 |
| --- | --- | --- | --- |
| Implementing Partner(s): | NA |
| Programme Number: | CFIA- B3 |
| Programme Title: | World Food Programme Pandemic Preparedness and Planning |
| Total Approved Programme Budget: | US$ 4,205,100 |
| Location: | Corporate with focus on 9 priority countries and 2 pandemic regional logistic capacity assessments |
| MC Approval Date: | 20 February 2008 |
| Programme Duration: | 12 Months | Starting Date: | 04/03/2008* ( 01/10/2007) | Completion Date: | 30/09/2008 |
| Funds Committed: | US$ 2,326,021 | Percentage of Approved: | 55% |
| Funds Disbursed: | US$ 1,626,021 | Percentage of Approved: | 38.5% |
| Expected Programme Duration: | 15 Months | Forecast Final Date: | 31/12/2008 | Delay (Months): | 3 Months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Operational contingency plans in place in 9 priority countries by the end of 2008 | Draft contingency plans developed for Ethiopia and Indonesia. | 22% |
| Transport alternatives of humanitarian goods along the main delivery corridors during a pandemic properly analysed and assessed integration of the project with other ongoing preparedness measures. | Analysed the potential impact of a pandemic on the supply chain of humanitarian goods along the East and South African Logistics corridor. Engaged stakeholders, conducted joint hazard and risk analysis for East and South African Logistics corridor. | 48% |
| Logistics training programme developed and key operational staff (WFP and non WFP; WHO, UNHCR, UNICEF, IFRC and selected NGOs) trained on Standard Operating Procedures (SOPs) in immediate response for “containment / quarantined operations”. | Training material, including scope and draft scenario completed. WHO engaged as technical support partner. Health and safety guidance prepared in collaboration with the UN medical Directors for interagency use. | 24% |
| Improved pandemic preparedness planning across the organization. | Joint UNICEF, UNDP and WFP training within the framework of Pandemic Preparedness rolled out 72% of WFP country offices. | 70% |
| Impact of an influenza pandemic on the livelihood of vulnerable groups in priority countries analysed and programme response guidance developed. In close collaboration with sister UN agencies, the Red Cross Movement, NGOs and national authorities, the project will develop guidelines for the use of food assistance in a pandemic environment | Engaged with H2P initiative and contributed to the drafting of a study done on socio-economic indicators Linked WFP strategic planning scenarios for pandemic with food crisis. Pandemic preparedness integrated as part of draft policy on Preventing and Mitigating Disaster. Draft matrix of key indicators and for the analysis of a pandemic’s impact on food security developed. | 37% |
| Qualitative achievements against outcomes and results: |
| As outlined in the proposal, in determining the priority countries to prepare operation contingency plans, WFP has focused on high risk countries, where the humanitarian needs (including food assistance) were identified as being greatest, and where the operational role of WFP and UN is most pronounced. So far, contingency plans for Ethiopia and Indonesia have been drafted taking into consideration the multisectroal and operational aspects required for response. In line with its objectives and as indicated in the programme report of CFIA A1- activities of the project have aimed at analysing the potential impact of a pandemic on the supply chain of humanitarian goods along the main corridors for east and southern Africa. Following the review of the first segment of the process, lessons learnt and best practices are being considered during the remaining implementation phase of the assessment processes. Based on WFP’s experience in emergency response and operations, in particular given its role as the logistics cluster lead, a ‘Humanitarian Logistics Pandemic Preparedness and Response Simulation Training’ is being prepared. The pilot of a series of these trainings is scheduled to take place in Asia later this year. As stated by WHO Director General Margaret Chan, Business Continuity Planning under a pandemic environment will require essential preparedness measures. WFP has been engaged with UNICEF and UNDP to prepare its offices around the world. This has required training of staff to preparedness measures together with partners on the maintenance of operations. So far 72% of WFP country offices have been trained to not just bolster their own capacities but also to maintain operation and also able to provide support to the governments. WFP is an active member of the USAID funded, Humanitarian Pandemic Preparedness (H2P) initiative. The H2P initiative aims at enhancing national, regional and community specific response capacities and pandemic preparedness. In May of 2008, WFP hosted a consultation with the Academy of Educational Development (AED), the International Federation of Red Cross and Red Crescent Societies (IFRC), USAID, Save the Children/CORE Group and Pandemic Influenza Contingency (PIC) in line with this partnership. To meet the objective of analyzing the impact of an influenza pandemic on the livelihood of vulnerable groups in priority countries, WFP has developed an initial set of draft key indicators. In addition, WFP has integrated elements of key lessons learnt from the rising food prices as a means to further strengthen national resilience to such shocks. |