- United Nations Development Group Iraq Trust Fund

- Project #:C10-09d

- Date and Quarter Updated: December 2008 (4th Quarter)

| Participating UN Organisation: UNESCO | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education and Ministry of Labour and Social Affairs |  |

| Title | Local Area Development Programme (LADP) / Area Based Development |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Governorate of Sulymaniyah: Sayid Sadiq & New Halabja districts Governorate of Babylon: Hillah district Governorate of Basrah: Mdaina district Governorate of Thi Qar: Chibayesh district Governorate of Missan: Maymouna district |  |  |  |  |
| Project Cost | US$ 30, 338,384 (of which UNESCO’s budget = US$ 3,235,570) |  |  |  |  |
| Duration | 12 months (Project was extended for one year until end April 2009) |  |  |  |  |
| Approval Date (SC) | April 10, 2007 | Starting Date | May 1, 2007 | Completion Date | April 30, 2008 |
| Project Description | The Programme will strengthen the abilities of local authorities in three areas in the north, centre and south to prepare and implement human rights based, gender sensitive local area development plans. Second, it will work with local partners to stimulate local economic development and generate short term and sustainable long term employment. Third, it will improve social and physical infrastructure using labour intensive approaches and improve the service delivery capabilities of local authorities in the three selected areas. |  |  |  |  |

- Development Goal and Immediate Objectives

Development Goal: Improve living conditions and contribute to sustainable poverty reduction in the three selected areas in Iraq. Objective 1: Strengthen the capabilities of local authorities in three selected areas in the north, center and south to plan and manage reconstruction and development activities through the formulation and implementation of human rights based, gender sensitive local area development plans. Objective 2: Stimulate local economic development and generate short-term and sustainable long term employment in the three selected areas. Objective 3: Improve social and physical infrastructure using labour intensive approaches and the service delivery capabilities of local governments in the three selected areas.

- Outputs, Key activities and Procurement

| Outputs | (List in reference to the key immediate objectives) - Comprehensive human rights based, gender sensitive local area development plans (LADPs) for three areas prepared and adopted by local authorities and stakeholders assisted by a team of UN agencies based on joint-participatory needs assessments. - Strengthened coordination and communication mechanisms between central government and local authorities in the three areas. 2.1. Improved local business environment for small businesses in the three areas. 2.2. At least 80 new small enterprises and cooperatives established in three areas. 2.3. Enhanced employment skills for at least 1500 residents in three areas 3.1. 30 water and sanitation facilities and services improved in three areas 3.2. 9 primary educational facilities and programme activities improved in three areas 3.3. 12 health services centers and services improved in three areas. 3.4. 2500 housing units and 12 community facilities improved in three areas 3.5. Improved conditions for agriculture development and the promotion of environmental awareness including through 60 small infrastructures projects in three areas. 3.6. 30 community based electricity facilities and services improved in three areas 3.7. 9 damaged religious sites rehabilitated in three areas. |
| --- | --- |
| Procurement (major items) | - Furniture and lab and IT equipment to 8 schools (2 in Suleimanya, 3 in Hilla and 3 in the Marshlands). - Workshop equipment to 3 vocational training centres (1 in each governorate). |

- Situation as of 7th January 2009

| Funds Committed | US$ 665,030 | % of approved | 20.55% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 517,104 | % of approved | 15.98% |
| Forecast final date | 22 July 2009 | Delay (months) | 6 months |

- Quantitative achievements against objectives and results

| Objective 1: Strengthen the capabilities of local authorities in three selected areas in the north, center and south to plan and manage reconstruction and development activities through the formulation and implementation of human rights based, gender sensitive local area development plans. |  | % of planned |  |
| --- | --- | --- | --- |
| Objective 2: Stimulate local economic development and generate short-term and sustainable long term employment in the three selected areas. | Refer to output 2.3: - One vocational centre has been identified in each of the three areas and endorsed by local steering committee of each area (Sayed Sadiq VTC in Sulaimanya, Al Iskan Youth Center in Hilla and Al Maymoona VTC in the Marshlands. The disciplines for VTC workshops have been finalized. Specifications have been set and procurement procedures have started. A bidding process was launched and offers are now under technical evaluation. - UNESCO has worked with a national consultant to write TORs for training VTC instructors in the disciplines chosen by each area. Offers have been received and the evaluation of bids will be complete by 12 January 2009 with training courses expected to launch in February 2009. | % of planned | 40 % 30 % |
| Objective 3: Improve social and physical infrastructure using labour intensive approaches and the service delivery capabilities of local governments in the three selected areas. | Refer to output 3.2: - In Suleimanya, the MoE identified 2 schools; 1 in New Halabja and 1 in Sayyed Sadeq and provided UNESCO with their needs of lab equipment. The lists of specifications were endorsed by MoE. Contracts have been signed for physics labs. Contracts for Chemistry and Biology labs have been referred to UNESCO Headquarters with decision expected 15 January 2009. - In Hilla, the MoE identified 3 schools (Al Hilla High School for Boys, Al Khansa High School for Girls and Al Faiha’ High School for Boys) and provided UNESCO with their needs of lab equipment. The specifications were endorsed by MoE. Contracts have been signed for physics labs. As above, contracts are with Headquarters with decision expected 15 January 2008. - In the Marshlands, the MoE identified 3 schools (Al Mdayna High School for Boys Al Maymoona High School for Boys Al Jaza’ir High School for Boys) Contracts have been signed for physics labs. Contracts are with Headquarters for approval as above. | % of planned | 75 % |

- Qualitative achievements against objectives and results

The VTC workshops will have to be up and running before any tangible conclusion can be made as to the qualitative achievements.