- United Nations Development Group Iraq Trust Fund

- Project Summary Sheet

- C10-04

- Date and Quarter Updated: 08Q4

| Participating UN Organisation: ESCWA | Cluster: C – Governance and Human Development |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Municipalities and Public Works |  |

- Programme/Project Number: C10-04

| Title | Smart Community Project for Iraq |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Location | Sayid Dikhil, Altun Kopri and Dibbs |  |  |  |  |
| Project Cost | US$ 2,703,202.00 |  |  |  |  |
| Duration | September 05 – April 08 |  |  |  |  |
| Approval Date (SC) | 8 June 05 | Starting Date | 1 Sept. 05 | Completion Date | 31 Dec 08 |
| Project Description | The Smart Community Project (SCP) in Iraq was designed and is currently being implemented by ESCWA with the aim of building capacity in selected communities to generate employment, promote enterprise creation based on proven modern technologies, thus, reducing poverty. The SCP includes two core components: a Multipurpose Technology Community Centre (MTCC) and an Agro-Food Processing Unit (AFPU). Additionally, the SCP includes a number of auxiliary components including water treatment and the use of solar energy for process water heating. The final component of the project is the technology dissemination programme (TDP) designed to disseminating experiences gained and lessons learned in establishing the above-mentioned facilities. |  |  |  |  |

- Development Goal and Immediate Objectives

The SCP Development Goal is to build local and national capacity for creating employment and reducing poverty in Iraq on the basis of modern technology inputs. A summary of the main objectives follows: 1. Establishing two functioning smart community facilities in two selected impoverished rural locations in Iraq. 2. Providing, in collaboration with local, national and UN partners, a model to serve as basis for the introduction of modern technology inputs. 3. Providing hardware, software and know-how for implementing on the job training and enterprise support services. 4. Formulation of modalities for extending experience gained.

- Outputs, Key activities and Procurement

| Outputs | - Two MTCCs have been established and are currently operational, one in each of Altun Kopri and Dibbis; - Installation of two dairy processing facilities in Dibs and sayid Dikhil districts has been finalized. - Handover procedures formulated with the Ministry of Municipalities and Public Works. - Two Chemistry and Microbiology laboratories for food testing have been established and equipped within Salahaddine and Thi Qar Universities. |
| --- | --- |
| Activities | a. Partnerships Partnerships with Iraqi Universities ESCWA partnered with Salahaddine, Thi Qar, Mosul, Wassit, Al Qadisssiya and Baghdad Universities to implement several components of the project, namely to control and supervise operations at the established SCP facilities in the selected localities in north and south Iraq, as well as to establish and launch Community Development Units (CDUs) at the above-mentioned Universities. These CDUs are to provide technical and administrative support the existing SCP facilities and to disseminate the best practices learned into other localities in Iraq. ESCWA partnered with Salahaddine and Thi Qar Universities on the installation and commissioning of the dairy facilities established in Dibs and Sayid Dikhil, as well as with Mosul University to establish a Multi purpose Agro-Food Processing Unit (MPAFPU) within the University for training and educational purposes. Through these partnerships, ESCWA succeeded in installing and running the two dairy processing facilities as well as to establish the MPAFPU at Mosul University. e. Meetings and workshops ESCWA organized a final coordination meeting on the SCP between 22 and 24 July 08. The meeting aimed at setting up the final action plan leading to finalizing the installation and commissioning processes and formulating the handover procedures with the Ministry of Municipalities and Public Works (MMPW). Representatives from the MMPW, Salahaddine and Thi Qar Universities attended the meeting as well as the project coordinators in north and south Iraq. f. Technology Dissemination Programme (TDP) The TDP was launched and an implementation plan produced including items on networking; establishment of micro AFPUs on dairy processing, date pressing and fish farming; implementation of vocational computer-based vocational training programmes and additional training programmes on secretarial skills, English language, and basic literacy skills. g. Handover formalities As a result of the final coordination meeting on the SCP, ESCWA succeeded to formulate the handover procedures with the Ministry of Municipalities and Public Works. The SCP facilities shall be handed over to the MMPW. The MMPW shall proceed to rent the SCP facilities to the private sector or NGOs according to the Iraqi rules and regulations. |
| Procurement (major items) | - IT equipment including hardware and software, satellite Internet and necessary furniture items to set up 2 MTCCs in north and south Iraq. - Dairy processing equipment and associated quality control to set-up two AFPUs; Auxiliary facilities including reverse osmosis and ultra violet filtration systems as well as solar water heating units. |

- Situation as of 31/12/2008

| Funds Committed | $ 2,531,075.30 | % of approved | 94% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 2,414,790.22 | % of approved | 89% |
| Forecast final date |  | Delay (months) |  |

- Quantitative achievements against objectives and results

| Multipurpose Community Centres (MTCC) | Two MTCCs have been established and are currently operating in Sayid Dikhil and Altun Kopri. A total of 120 participants have already received computer literacy training since July 06; 25 graduates (20% of the total) have reportedly succeeded in securing new employment positions or improving their actual posts; | 100% finalized |
| --- | --- | --- |
| Agro-Food Processing Units (AFPU) | Two host buildings within Sayid Dikhil and Dibbs districts have been rehabilitated according to food safety regulations. Insataltion and commissioning of the dairy equipment has been finalised in both AFPUs. | 100% |
| Food Control Laboratories | Two Chemistry and Microbiology laboratories for food testing have been established and equipped within Salahaddine and Thi Qar Universities | 100% finalized |
| Technology Dissemination Programme | Design and implementation plan have been finalized and the programme launched with networking arrangements and vocational training programmes under implementation. | 100% |

- Qualitative achievements against objectives and results

Capacity building at community level is achieved on the basis of partnerships, training activities as well as coordination meetings. Partnerships established with local authorities at each site will ensure sustainability and achievement of final objectives. The TDP being implemented provides basis for promoting diffusion of best practices, optimal coordination and cooperation modalities as well as human resource sharing with particular emphasis on training, project planning, commissioning, and marketing. It also explores possibilities of extending the project to other rural areas of Iraq as well as expanding the scope of AFPU activities. The project has thus far succeeded in raising awareness and interest by local community members in these types of local community development projects as indicated by feedback received from municipalities as well as the line ministry.