- United Nations Development Group Iraq Trust Fund

- Project Summary Sheet

- Project # C10-04

- Date and Quarter Updated: 08Q3

| Participating UN Organisation: ESCWA | Cluster: C – Governance and Human Development |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Municipalities and Public Works |  |

- Programme/Project Number: C10-04

| Title | Smart Community Project for Iraq |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Location | Sayid Dikhil, Altun Kopri and Dibbs |  |  |  |  |
| Project Cost | US$ 2,703,202.00 |  |  |  |  |
| Duration | 18 months |  |  |  |  |
| Approval Date (SC) | 8 June 05 | Starting Date | 1 Sept. 05 | Completion Date | 31 Dec 08 |
| Project Description | The Smart Community Project (SCP) in Iraq was designed and is currently being implemented by ESCWA with the aim of building capacity in selected communities to generate employment, promote enterprise creation based on proven modern technologies, thus, reducing poverty. The SCP includes two core components: a Multipurpose Technology Community Centre (MTCC) and an Agro-Food Processing Unit (AFPU). Additionally, the SCP includes a number of auxiliary components including water treatment and the use of solar energy for process water heating. The final component of the project is the technology dissemination programme (TDP) designed to disseminating experiences gained and lessons learned in establishing the above-mentioned facilities. |  |  |  |  |

- Development Goal and Immediate Objectives

The SCP Development Goal is to build local and national capacity for creating employment and reducing poverty in Iraq on the basis of modern technology inputs. A summary of the main objectives follows: 1. Establishing two functioning smart community facilities in two selected impoverished rural locations in Iraq. 2. Providing, in collaboration with local, national and UN partners, a model to serve as basis for the introduction of modern technology inputs. 3. Providing hardware, software and know-how for implementing on the job training and enterprise support services. 4. Formulation of modalities for extending experience gained.

- Outputs, Key activities and Procurement

| Outputs | - Two MTCCs have been established and are currently operational, one in each of Altun Kopri and Sayid Dikhil; - Procurement of dairy AFPU equipment has been finalized and equipment has been delivered to the hosting sites; - Two Chemistry and Microbiology laboratories for food testing have been established and equipped within Salahaddine and Thi Qar Universities. - Two IT Centres have been established in cooperation with Gilken and Althadamun NGOs; - The following vocational training packages: (a) basic accountancy, (b) basic literacy, (c) basic living skills, (d) dairy processing and food safety, (e) secretarial skills and (f) handcrafts. |
| --- | --- |
| Activities | a) Training Activities  IT Trainings - Over 45 training sessions organized at the MTCCs in Altun Kopri and Sayid Dikhil starting June 2006 till present for women, youth, school students and employees; - Training sessions on IT for women were also conducted in cooperation with – Althathmun and Gilkent women NGOs;  Literacy, Women Basic Living Skills Awareness & Employment Generation Trainings - A total of 1749 Iraqi nationals from different training institutions and directorates as well as women NGOs have been trained on literacy, basic living skills and employment generation activities. b) Partnerships Partnerships with UN agencies - Letters of agreements with ILO, UNIDO and HABITAT were signed to implement specific components of the project. Partnerships with Iraqi Universities - Formalization of cooperation with Salahaddine and Thi Qar Universities on the installation and commissioning of the dairy equipment at the hosting sites in Dibs and Sayid Dikhil. - Formalization of cooperation Mosul University to launch the CDU and to establish a multi-purpose agro-food processing unit at the University for training and educational purposes. Partnership with the Local Authorities - ESCWA formalized the cooperation with the Ministry of Municipalities and Public Works (MMPW) to handover the SCP facilities to the hosting municipalities. The concerned municipalities shall liaise with MMPW to subcontract the SCP facilities to the private sector according to the Iraqi rules and regulations. c) Meetings and workshops - ESCWA conducted the final coordination meeting on the SCP between 22 and 24 July 08 in Beirut. The Meeting essentially focused on the finalization of the handing over procedures with the MMPW representative as well as setting up an action plan for the installation and commissioning phase of the dairy facilities with the concerned Universities. d) Technology Dissemination Programme (TDP) - Community Developments Units (CDUs) were established at Mosul, Thi Qar Salahaddine, Wassit, Al Qadissiya and Baghdad Universities to follow-up on the activities related to the Smart Community Project. |
| Procurement (major items) | - IT equipment including for the MTCCs in Altun Kopri and Sayid Dikhil. - Dairy processing equipment for the AFPUs in Dibs and Sayid Dikhil. . |

- Situation as of 30 September 2008

| Funds Committed | $ 2,558,628.05 | % of approved | 95% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 2,389,343.34 | % of approved | 88% |
| Forecast final date | 31 Dec 08 | Delay (months) | 21 |

- Quantitative achievements against objectives and results

| Multipurpose Community Centres (MTCC) | Two MTCCs have been established and are currently operating in Sayid Dikhil and Altun Kopri. A total of 120 participants have already received computer literacy training since July 06; 25 graduates (20% of the total) have reportedly succeeded in securing new employment positions or improving their actual posts; | 100% finalized |
| --- | --- | --- |
| Agro-Food Processing Units (AFPU) | Two host buildings within Sayid Dikhil and Dibbs districts have been rehabilitated according to food safety regulations. Equipment procurement is currently in the delivery stage. | 90% |
| Food Control Laboratories | Two Chemistry and Microbiology laboratories for food testing have been established and equipped within Salahaddine and Thi Qar Universities | 100% finalized |
| Technology Dissemination Programme | Design and implementation plan have been finalized and the programme launched with networking arrangements and vocational training programmes under implementation. | 100% |

- Qualitative achievements against objectives and results

Capacity building at community level is achieved on the basis of partnerships, training activities as well as coordination meetings. Partnerships established with local authorities at each site will ensure sustainability and achievement of final objectives. The TDP being implemented provides basis for promoting diffusion of best practices, optimal coordination and cooperation modalities as well as human resource sharing with particular emphasis on training, project planning, commissioning, and marketing. It also explores possibilities of extending the project to other rural areas of Iraq as well as expanding the scope of AFPU activities. The project has thus far succeeded in raising awareness and interest by local community members in these types of local community development projects as indicated by feedback received from municipalities as well as the line ministry.