# United Nations Development Group Iraq Trust Fund

# C 10- 05

# Project Summary Sheet

# Date and Quarter Updated: 08Q4

| Participating UN Organisation: ESCWA | Cluster: C – Human development and Good governance |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Planning and Development Cooperation (MoPD) |

# Programme/Project Number: C10-05

| Title | Development of National Gender Statistics in Iraq |
| --- | --- |
| Location | Nationwide |
| Project Cost | USD 856,553 |
| Duration | 18 months |
| Approval Date (SC) | 16/03/2005 | Starting Date: July 2006 (receipt of funds) | Completion Date: 31 December 2008 (as per approved project extension and budget revision dated March 2008) |
| Project Description | The project assists in the assessment and development of quality gender statistics needed to support results-based policy-making aimed at mainstreaming gender and achieving gender equality and women’s empowerment. |

# Development Goal and Immediate Objectives

Development goal: To assist in the development of quality gender statistics and indicators. Immediate objectives: Raise awareness on the importance of gender statistics in policy formulation and monitoring and gender mainstreaming of statistical work; Improve national capacities to produce, analyze and disseminate quality gender statistics.

# Outputs, Key activities and Procurement (as per project document)

| Total = 15 1 1 1 3 2 1 1 5 | List of critical gender issues Set of core gender statistics and indicators Report on the assessment of data availability Statistical publication and other materials on status of women and men in Iraq (i.e. wall chart, flyer, pocketbook, and photo gallery) Gender statistics website and database Report on the results and analysis of Time-Use Survey Strategic framework for enhancing national statistical capacities, developing gender statistics and mainstreaming gender in all statistical work Reports of meetings and workshops |
| --- | --- |
| Activities = 15 1 1 2 3 5 1 1 1 | Pre-meeting Data assessment, compilation and analysis Establishing a gender statistics Unit and equipping it Preparation of a statistical publication and other materials on the status of women and men in Iraq Training workshops (1st and 2nd National; Time-Use Survey; DevInfo Workshop; Mainstreaming Gender in Labour Statistics) Study tour Development of a national gender statistics website Development of gender database |
| Procurement (major items) | Server, Switch ,UPS + UPS batteries, Personal computer (5),Laptop (2),Software, Software antivirus, Projector (1) Inkjet printer (4), Laser printer (1), Scanner (1), Facsimile (1), Photocopier (1), Digital camera (1), |

# Situation as of 30 December 2008

| Funds Committed | $ 621,694.90 | % of approved | 73% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 459,224.18 | % of approved | 54% |
| Forecast final date | 31 December 2008 (originally November 2007) | Delay (months) | 1 year (as per the project extension approved in March 2008) |

# Quantitative achievements against objectives and results

| Establishing a gender statistics Unit and equipping it | Gender Unit at COSIT was established in mid 2007. 1 National expert and 2 Research Assistants and 1 Administrative Assistant were recruited in 2007. In 2008 3 staff are still working in the Gender Unit. | 100% |
| --- | --- | --- |
| Procurement of IT equipment | Refer to section on procurement | 100% |
| 5 Training workshops (1st and 2nd National; Time-Use Survey; NSDS & Gender; DevInfo) | - First National Workshop on Gender Statistics, Amman, December 2007:25 users and producers of statistics trained on production of gender statistics; - National Workshop on Gender Statistics and Time-Use Surveys, Amman, 4-6 November 2007: 7 national statistical staff from the Gender Statistics Unit and COSIT trained on concepts, definitions, methodologies and the analysis of time-use data and report writing -Training on the statistical software DevInfo: 7-10 July 2008: 6 representatives of the National Statistical Office in Iraq were trained on the stat5istcal software DevInfo v.5.0 -Second National Workshop on Gender Statistics, Beirut, November 2008:24 users and producers of statistics trained on production of gender statistics; and on developing a strategic framework for enhancing national statistical capacities and mainstreaming gender in the statistical work. - Workshop on Mainstreaming Gender in Labour Statistics, Turin, December 2008: 30 users and producers of statistics trained on mainstreaming gender in labour statistics. Additional Workshop - Workshop on the Design of National Strategies for the Development of Statistics: Mainstreaming Gender in Sectoral Statistics Istanbul, 24-26 March 2008: 7 representatives of the National Statistics office were trained on the PARIS21 guidelines for the development of statistics and how to mainstream the gender perspective in sectoral statistics. | 100 % |
| Study tour | - 2 fellowships from the national statistical cadres trained on statistical software (Regional Training on Dev Info, Cairo, 5 days in September 2007); - 5 fellowships were granted a study visit to the Jordanian Department of Statistics and Jordanian Ministry of Planning and International Cooperation (Amman, 7-8 November 2007) -3 fellowships were trained in the Community System Foundations in India, December 2008 on the development of databases using the DevInfo application. | 100% |
| Issuance of outputs | - List of critical gender issues (completed) - Set of core gender statistics and indicators (completed) - Report on the assessment of data availability (completed) - Men and Women publication (completed) - Flyer (completed) - Photo Gallery (completed) - Gender Statistics Website (finalized) - Gender Database (completed) - Report on the results and analysis of TUS (in process) - Strategic framework for enhancing national statistical capacities, developing gender statistics and mainstreaming gender in all statistical work (completed/incorporated in NSDS being finalized by COSIT) - Reports of meetings and workshops: - Final Report on the First National Workshop. - Final Report on the Time-Use Survey Workshop. -Final Report on the Second National Workshop (in process) -Final Report on DevInfo Training -Final Report on the Workshop on Mainstreaming Gender in Labour Statistics (in process) Additional -Final Report on Design of National Strategies for the Development of Statistics (NSDS) Workshop. | 85% |

# Qualitative achievements against objectives and results

During the Second National Workshop (Beirut, November 2008), 24 users and producers of statistics were trained on the design of strategic framework to enhance national capacity in mainstreaming gender in statistical work. In the Workshop on Mainstreaming Gender in Labour Statistics, Turin, December 2008, 30 participants were training on enhancing the quality and hence the impact of various national employment and training policies in Iraq from a gender perspective. Participants gained awareness of the importance of key gender-related statistics and indicators for the labour market as a pre-requisite for the formulation of appropriate and effective strategies for employment and training policies. - Study tours were also organized for the Gender Unit and COSIT: 3 fellowships were trained in the Community System Foundations in India, December 2008 on the development of databases using the DevInfo application.