- United Nations Development Group Iraq Trust Fund

- Project Summary Sheet- C10- 05

| Participating UN Organisation: ESCWA | Cluster: C – Human development and Good governance |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Planning and Development Cooperation (MoPD) |  |

- Programme/Project Number: C10-05

| Title | Development of National Gender Statistics in Iraq |  |  |
| --- | --- | --- | --- |
| Location | Nationwide |  |  |
| Project Cost | USD 856,553 |  |  |
| Duration | 18 months |  |  |
| Approval Date (SC) | 16/03/2006 | Starting Date: July 2006 (receipt of funds) | Completion Date: 31 December 2008 (as per approved project extension and budget revision dated March 2008) |
| Project Description | The project assists in the assessment and development of quality gender statistics needed to support results-based policy-making aimed at mainstreaming gender and achieving gender equality and women’s empowerment. |  |  |

- Development Goal and Immediate Objectives

Development goal: To assist in the development of quality gender statistics and indicators. Immediate objectives: - Raise awareness on the importance of gender statistics in policy formulation and monitoring and gender mainstreaming of statistical work; - Improve national capacities to produce, analyze and disseminate quality gender statistics.

- Outputs, Key activities and Procurement (as per project document)

| Total = 15 1 1 1 3 2 1 1 5 | - List of critical gender issues - Set of core gender statistics and indicators - Report on the assessment of data availability - Statistical publication and other materials on status of women and men in Iraq (i.e. Booklet on Women Empowerment, flyer and photo gallery, wallchart) - Gender statistics website and database - Report on the results and analysis of Time-Use Survey - Strategic framework for enhancing national statistical capacities, developing gender statistics and mainstreaming gender in all statistical work - Reports of five meetings and workshops |
| --- | --- |
| Activities = 15 1 1 2 3 5 1 1 1 | - Pre-meeting - Data assessment, compilation and analysis - Establishing a gender statistics Unit and equipping it - Preparation of a statistical publication and other materials on the status of women and men in Iraq - Training workshops (1st and 2nd National; Time-Use Survey; NSDS & Gender; DevInfo Workshop) - Study tour - Development of a national gender statistics website - Development of gender database |
| Procurement (major items) | Server,Switch,UPS + UPS batteries,Personal computer (5),Laptop (2),Software,Software antivirus,Projector (1),Inkjet printer (4),Laser printer (1),Scanner(1),Facsimile (1),Photocopier (1),Digital camera (1) |

- Situation as of 30 September 2008

| Funds Committed | $ 442,296.21 | % of approved | 52 % |
| --- | --- | --- | --- |
| Funds Disbursed | $ 259,257.85 | % of approved | 30 % |
| Forecast final date | 31 December 2008 (originally November 2007) | Delay (months) | 1 year (as per the project extension approved in March 2008) |

- Quantitative achievements against objectives and results

| Establishing a gender statistics Unit | Gender Unit at COSIT was established in mid 2007. 1 National expert and 2 Research Assistants and 1 Administrative Assistant were recruited in 2007. In 2008 3 staffs are still working in the Gender Unit. | 100 % |
| --- | --- | --- |
| Procurement | Procurement of all equipments as planned has been completed. Additional: 2 additional laptops are going to be purchased | 100 % |
| 5 Training workshops (1st and 2nd National; Time-Use Survey; NSDS & Gender; DevInfo) | 1- First National Workshop on Gender Statistics, Amman, December 2007: 25 users and producers of statistics trained on production of gender statistics; 2- National Workshop on Gender Statistics and Time-Use Surveys, Amman, 4-6 November 2007. 7 national statistical staff from the Gender Statistics Unit and COSIT trained on concepts, definitions, methodologies and the analysis of time-use data and report writing. 3- Workshop on the Design of National Strategies for the Development of Statistics: Mainstreaming Gender in Sectoral Statistics Istanbul, 24-26 March 2008: 7 representatives of the National Statistics office were trained on the PARIS21 guidelines for the development of statistics and how to mainstream the gender perspective in sectoral statistics. 4- Workshop on DevInfo Software Beirut, 7-10 July 2008 and hands-on training on 6 representatives from COSIT were trained on DevInfov5.0 in order to build a pool of expertise in compiling and managing databases, in addition to bring them up-to-date with the most recent upgraded version of the software. 5- Second National Workshop on Strategic Framework for Enhancing National Statistical Capacities and Mainstreaming Gender in the Statistical Work, Beirut, 25-27 November 2008, is in process of preparation.15 users and producers of statistics will be trained. Additional: 6- Workshop on Mainstreaming Gender in Labour Statistics, Turin, 9-12 December 2008, is in process of preparation.30 participants from COSIT and other related ministries will attend the Workshop. | 80 % |
| Study tour | - 2 fellowships from the national statistical cadres trained on statistical software (Regional Training on Dev Info, Cairo, 5 days in September 2007); - 5 fellowships were made to the Jordanian Department of Statistics and Jordanian Ministry of Planning and International Cooperation (Amman, 7-8 November 2007) | 100% |
| Issuance of outputs ( total of 15, mentioned above) | 1-List of critical gender issues has been completed 2- Set of core gender statistics and indicators has been completed 3- Data Assessment Report 1st draft is being finalized (50%) 4- Statistical publication and other materials on status of Women and Men in Iraq -National Report on Gender Indicators is being revised (50%) -Informational flyer on the Gender Unit has been completed -The photo gallery on Gender issues has initiated. The national photographer is sending photos to be agreed upon by ESCWA (20%) 5 -National Gender Statistics website is under-construction (30%) - Preliminary database for Gender Indicators has been created. Finalization and certification will follow after the consultant meets with the Gender Unit (60%) 6- Report on the results and analysis of Time-Use Survey is awaiting results of the survey from COSIT. 7- Strategic framework for enhancing national statistical capacities, developing gender statistics and mainstreaming gender in all statistical work is in process (20%) 8-Reports of meetings and workshops: 4 reports are completed (1st National Workshop, NSDS&Gender, Time-Use and DevInfo Workshops) | 62 % |

- Qualitative achievements against objectives and results

-Staffing of the Gender Statistics Unit to provide technical, administrative and logistical support in project implementation, and to ensure national ownership, a stakeholder-driven process, and sustainability beyond the project’s completion through the recruitment of three national project personnel -In First National Workshop on Gender Statistics, 25 users and producers of statistics trained on production of gender statistics. In addition, core gender issues and indicators were also identified and recommended in the final report. -Improved knowledge and skills in engendering statistical work, producing gender statistics, and use of instruments for the measurement of women’s work through a three-day training workshop on time-use surveys. Seven national statistical staff from the Gender Statistics Unit and COSIT trained on concepts, definitions, methodologies and good practices in the planning, design, and implementation of time-use surveys, and the analysis of time-use data and report writing. -During the Workshop on the Design of National Strategies for the Development of Statistics: Mainstreaming Gender in Sectoral Statistics, the participants were trained on the PARIS21 guidelines for the development of statistics and how to mainstream the gender perspective in sectoral statistics. Participants were able to put to use the concepts introduced by partaking in a number of working group exercises that included undertaking a SWOT analysis of their respective country’s statistical system and preparing their country’s statistical vision, mission and priority areas. -Six participants from COSIT were trained on DevInfo software which increases their capacities in compiling, disseminating and exchanging data and metadata. The DevInfo provides COSIT with a tool for effective working partnership among different data producers and it facilitates exchanging a unified official statistics to relevant Agencies and the Regional Commission in the region. It insures invaluable contribution by experts from COSIT in applying similar terminologies and being fully involved in the process of data collection and compilation. This will impact the databases of MDG Info and Gender Info databases in Iraq being developed. -Study tours were also organized for the Gender Unit and COSIT as stated above.