EIGHT  Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNDP |  | C – Governance and Human Development |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| C9-05: “Capacity Building and Institutional Strengthening of the Ministry of Municipality and Public Works” |  | 6 |

| Reporting Period: |  | Project Budget: US$ 3,018,710 |
| --- | --- | --- |
| 1 January-June 2008 |  |  |

| List Implementing Partners: Ministry of Municipalities and public Works Local Councils and Municipalities Local NGOs UNECWS, UNITAR, Team international Iraqi Engineering Association The Catalan local authorities Members of the Decentralize Cooperation network such as Tunisia, Lebanon, Morocco |  | Project Coverage/Scope: National Coverage-MMPW and the 18 governorates |
| --- | --- | --- |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| See above |  | 15 months with 12 months extension until end of March 2008 |

# NARRATIVE REPORT FORMAT

# Purpose:

1.1. Development Goal:

NDS: 	Regions and governorates development: Annual allocations and distributions to governorates; Development management in regions and governorates

Improving the quality of life: Human development

ICI:   	4.1.2: Develop framework for inter-governmental fiscal relations to ensure efficiency, transparency and equity while maintaining national fiscal integrity

4.4.1: Delivering basic services:

Review legislative and regulatory framework to delineate the role of national and sub-national units for basic service provision

Enable effective and efficient co-ordination between national and sub-national governance units on service delivery with specific regard to the function of planning and service management

Build sub-national information management capacity to improve quality and efficiency of execution

Sector Team Outcome(s):

Strengthened regulatory frameworks, institutions and processes of national and local governance

The overall development objective of this project is to:

Build up the institutional and human resource capacity, at the national and local administrative levels, of the Ministry of Municipalities and Public Works to enable it to guide the reconstruction and the development process of Iraq with the view to help build the institutions that provide fundamental services to Iraqis.  The objectives are supporting the MMPW deliver its mandate in an efficient and effective manner in the area of services to the public: water; sanitation; solid waste management and delivery of services at the local administrative level

Key objectives:

- A capacity building and institutional strengthening framework based on the human development paradigm and comprising:

Human resources development:
Policy development;
Institutional development;
Organizational development;
Local administration development (of Governorates):
Participation/representation development; and
Community development

- Capacity building for the leadership role of the executives, senior and mid-level management

- Capacity building at the human resource and organizational levels and integration of Information management and information technology

- Develop national and local administrative capacity to automate services

1.2 This project aims at strengthening the institutional, administrative and technical capacity of the Ministry of Municipality and Public Works of Iraq, which is an important precondition for sustainable human development. As such, the project addresses one of the priorities of UN intervention and ultimately contributes towards achieving the MDGs in Iraq, namely poverty eradication.

1.3 UNDP is working with several number of international and national partners in implementing this project. 

International Partners:

ESCWA, the Lebanese Center for Policy Studies, TEAM international, as key partners in the implementation of the management skills training, management crisis and strategic planning training,, decentralisation of municipal service delivery, financial management and internal audit, and Leadership skills, and gender issues in municipal work.

UNITAR is also a major partner in the implementation of the Pilot initiative to support Iraqi national and local authorities in capacity building of 45 senior managers on decentralization process, strategic planning of local development and services delivery, in addition to facilitating twinning arrangements between Iraqi and regional municipalities.

The Catalan local authorities, a major partners in the implementation of the training in Barcelona.

Members of the Decentralize Cooperation network such as Tunisia, Lebanon, Morocco are also partners in presenting their experiences to Iraqi participants.

National partners 

The Ministry of  Municipalities and Public Works, Local Councils, Service oriented NGOs. Iraqi Engineering Association is a major partner in the design and execution of the national comprehensive training needs assessment.

- Human Resources

  - National Staff:  National Project Manager, 4 National Project Assistants, 3 national consultants were recruited by the implementing partners for the project.  A national Porgramme Officer funded by UNDP.

2.2.International Staff: One international Programme Manager, and 4 International

consultants were recruited by the implementing partners for the implementation of

this project.

III. Methods of Operating

3.1 The primary implementation mechanism utilized has been DEX, through sub-contracting and UN implementing partners. UNDP is working with two UN agencies as implementing partners namely UNITAR and UNESCWA which are implementing the Institutional Strengthening component.

3.2 Provide details on the procurement procedures utilized and explain variances in

standard procedures.

No procurement activities during the reporting period.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Monitoring of the activities is done through evaluation of quarterly and final reports, participant evaluation forms, quality review of documents submitted by partner Ministries and oversight of budgets.

  - Report on any assessment, evaluations or studies undertaken

Comprehensive training needs assessment  for the MMPW, and Tripartite Review Meeting upon completion of the project activities.

I.V Results

4.1Provide  a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

All planned activities were on target and activities completed on time.

4.2 Report progress made towards the achievement of specific medium-term outcome of the programme/project as a result of the achieved short-term outputs during this reporting period.

See above.

  - Report on the key Output achieved in the six month period including # and nature of the activities (input), % of completion and beneficiaries.

All outputs achieved on time (98% completed)

During the reporting period all the remaining Management skills for middle management to improve the managerial and administrative skills of the managers completed.

- Three workshops on Management skills for middle managers from the MMPW and Municipalities at the governorate levels (62 participants 39 women).  The participants were introduced to new trends in public administration and managing the challenges of globalization, role of the government and private sector, management challenges, strategic planning and management, crisis management, performance management, etc…

- Two follow up workshops on progress made towards implementation of action plans prepared by 20 participants during the workshops attended during 2007.

- Follow up workshop on management of services provision under crisis conditions: the case of water, sanitation and municipal service delivery.

- Workshop on financial management and internal audit for three Ministries, Planning, Municipalities and Public Works, and Finance. 20 Participants attended the workshop which was implemented in partnership with the Ministry of Finance in Lebanon.

- Workshop on Management skills for middle management- Human resources. Twenty one participants attended.

- Training of Trainers on Decentralization of service delivery. Twenty trainers from the MMPW training centers attended.

- Leadership skills and Gender issues in Municipal work/service delivery workshop targeted twenty Local council representatives.

- A Tripartite Review Meeting between UNDP/MMPW/ESCWA to review achievements, challenges, lessons leant, and recommendations for future areas of intervention.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions take to mitigate future delays.

The security situation and communications challenges prevent UNDP from having more extensive collaboration with its counterpart team, which would have enabled a more speedy implementation

Furthermore, another risk is the difficulty in identifying proper participants and obtaining proper travel documents for training programmes, as well as the impact of the security situation on transportation in and out of Iraq.

In light of the challenging security situation and the political instability witnessed in Lebanon, ESCWA, as the implementing agency, was forced to relocate its activities to Jordan which has affected logistical changes, required further preparation and incurring additional expenses.

4. 5  List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

UNDP’s key partnerships have been outlined above in 1.3

  - Summarize achievements against planned results for cross cutting issues: Security,

gender, human rights, employment (including# of short and long-term job created), and environment.

The project created employment indirectly through sub-contracting some activities to Iraqi companies.

The project ensured the direct and full participation of both men and women in strategic planning, needs assessments, meetings and workshops, in addition to specific workshop on Leadership Skills and Gender Issues in Municipal Work/Service Delivery

V.Future Work Plan

The project is operationally compled.