SEVENTH Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNDP |  | C – Governance and Human Development |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| C9-05: “Capacity Building and Institutional Strengthening of the Ministry of Municipality and Public Works” |  | 5 |

| Reporting Period: |  | Project Budget: US$ 3,018,710 |
| --- | --- | --- |
| 1 July-December 2007 |  |  |

| List Implementing Partners: Ministry of Municipalities and public Works Local Councils and Municipalities Local NGOs UNECWS, UNITAR, Team international Iraqi Engineering Association The Catalan local authorities Members of the Decentralize Cooperation network such as Tunisia, Lebanon, Morocco |  | Project Coverage/Scope: National Coverage-MMPW and the 18 governorates |
| --- | --- | --- |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| See above |  | 15 months with 12 months extension |

# NARRATIVE REPORT FORMAT

# Purpose

1.1 The overall development objective of this project is to:

Build up the institutional and human resource capacity, at the national and local administrative levels, of the Ministry of Municipalities and Public Works to enable it to guide the reconstruction and the development process of Iraq with the view to help build the institutions that provide fundamental services to Iraqis.  The objectives are supporting the MMPW deliver its mandate in an efficient and effective manner in the area of services to the public: water; sanitation; solid waste management and delivery of services at the local administrative level

Key objectives:

- A capacity building and institutional strengthening framework based on the human development paradigm and comprising:

Human resources development:
Policy development;
Institutional development;
Organizational development;
Local administration development (of Governorates):
Participation/representation development; and
Community development

- Capacity building for the leadership role of the executives, senior and mid-level management

- Capacity building at the human resource and organizational levels and integration of Information management and information technology

- Develop national and local administrative capacity to automate services

1.2 This project aims at strengthening the institutional, administrative and technical capacity of the Ministry of Municipality and Public Works of Iraq, which is an important precondition for sustainable human development. As such, the project addresses one of the priorities of UN intervention and ultimately contributes towards achieving the MDGs in Iraq, namely poverty eradication.

This project addresses the GoI’s goal to establish a civil service corps on the principles of professionalism, integrity and non-partisanship, as set forth in the International Compact with Iraq.   Specifically, in section 9.43, it states that the Government will formulate a comprehensive civil service reform programme which is fundamental for the successful implementation of the Compact.

The project is based on Iraq’s national priorities identified in the National Development Strategy (NDS). which states the need for a civil service reform, especially management reform of the public sector institutions as a priority.

1.3 UNDP is working with several number of international and national partners in implementing this project. 

International Partners:

ESCWA, the Lebanese Center for Policy Studies, TEAM international, as key partners in the implementation of the management skills training, management crisis and strategic planning training,, decentralisation of municipal service delivery, financial management and internal audit, and Leadership skills, and gender issues in municipal work.

UNITAR is also a major partner in the implementation of the Pilot initiative to support Iraqi national and local authorities in capacity building of 45 senior managers on decentralization process, strategic planning of local development and services delivery, in addition to facilitating twinning arrangements between Iraqi and regional municipalities.

The Catalan local authorities, a major partners in the implementation of the training in Barcelona.

Members of the Decentralize Cooperation network such as Tunisia, Lebanon, Morocco are also partners in presenting their experiences to Iraqi participants.

National partners 

The Ministry of  Municipalities and Public Works, Local Councils, Service oriented NGOs. Iraqi Engineering Association is a major partner in the design and execution of the national comprehensive training needs assessment.

- Human Resources

  - National Staff:  National Project Manager, 4 National Project Assistants, 3 national consultants were recruited by the implementing partners for the project.  A national Porgramme Officer funded by UNDP.

2.2.International Staff: One international Programme Manager, and 4 International

consultants were recruited by the implementing partners for the implementation of

this project.

III. Methods of Operating

3.1 The primary implementation mechanism utilized has been DEX, through sub-contracting and UN implementing partners. UNDP is working with two UN agencies as implementing partners namely UNITAR and UNESCWA which are implementing the Institutional Strengthening component.

3.2 Provide details on the procurement procedures utilized and explain variances in

standard procedures.

No procurement activities during the reporting period.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Monitoring of the activities is done through evaluation of quarterly and final reports, participant evaluation forms, quality review of documents submitted by partner Ministries and oversight of budgets.

  - Report on any assessment, evaluations or studies undertaken

Comprehensive training needs assessment  for the MMPW

I.V Results

4.1Provide  a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

The planned activities for the 2nd half of 2007 were delayed due to the challenging security situation and the political instability witnessed in Lebanon, where these activities were planned to take place.  The implementing agency along with UNDP were  forced to relocate the project planned activities to Jordan which has affected logistical changes, required further preparation which had impact on the achievement of some planned outcomes on time.  A Tripartite review meeting was held to review priorities, and expedite implementation of activities.

4.2 Report progress made towards the achievement of specific medium-term outcome of the programme/project as a result of the achieved short-term outputs during this reporting period.

See above.

  - Report on the key Output achieved in the six month period including # and nature of the activities (input), % of completion and beneficiaries.

Management skills for middle management to improve the managerial and

administrative skills of the managers. The training targeted  82 mid-level

managers (47 women) at the central and governorate levels. In particular, the training

modules introduced participants to modern models and concepts of public sector

management, with special focus on the delivery of municipal services.      The

training included:

New trends in public administration and managing the challenges of globalization

The role of the government and the private sector

Management challenges: concepts, restructuring, organization

Strategic planning and management

Change management

Project management

Leadership skills

Communication skills

Time management

Building and managing teams

Delegation and empowerment

Information and communication technology

Human resources management

Crisis management

Performance management

Three modules of management of services provision under crisis condition: the case of water, sanitation and municipal service delivery were conducted for 52 (2 women) senior staff of Iraqi municipalities.  The  workshop covered  (a) technical module on crisis management; the main topics covered are:

- Defining crisis and vulnerability

- Management and decentralization under crisis

- Capacity and vulnerability assessment and possible scenarios analysis

- Technologies and techniques for service provision during emergency

- Management of resources under crisis

- International SPHERE standards in service provision under crisis

- Conflict resolution skills

- Negotiation skills

- Team building and leadership skills

Strategic Planning (4 days)

Several informative comments were made by the participants regarding the problems they faced during service provisions under crisis. Some of these problems are:

- Bureaucracy in the administrations which delays or obstruct quick decision making;

- Uncoordinated instructions between central ministries and local authorities at governorate level;

- Security situation which limit access in the field and hinder transport of personnel and goods;

- Lack of available financial resources to support adequate response during crisis;

- Expansion of urban area horizontally rather than vertically requiring the expansion of the services’ networks (pipes) instead of utilizing the available networks thus incurring significant cost;

- The deteriorated conditions of the infrastructures which culminated recently for lack of maintenance;

- The incompetence or lack of experience of newly recruited technical staff.

UNDP TEAM International, Lebanese Center for Policy Studies (LCPS) and Strategic Planning Specialist through ESCWA  designed and implemented the modules. Similar to the pervious training workshops, support provided to the participants to develop individual and group action plans to be implemented upon return over a period of 6 months.  Practical steps were put in place by UNDP\MMPW in order to improve the impact of the training on the work of the MMPW, and to support behavioural change of the participants once they return to their work.  These steps include the embedding of the training into the workflow of the MMPW through several actions:  Debriefing of superiors on what have been learned, and what actions they intend to pursue, e.g. individual and group work plans.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions take to mitigate future delays.

The security situation and communications challenges prevent UNDP from having more extensive collaboration with its counterpart team, which would have enabled a more speedy implementation

Furthermore, another risk is the difficulty in identifying proper participants and obtaining proper travel documents for training programmes, as well as the impact of the security situation on transportation in and out of Iraq.

In light of the challenging security situation and the political instability witnessed in Lebanon, ESCWA, as the implementing agency, was forced to relocate its activities to Jordan which has affected logistical changes, required further preparation and incurring additional expenses.

Lessons learned:

Trying to implant international models into the Iraqi reality was premature, and local  governance models developed in the region may be more acceptable, but need to be locally adapted.

The roles and responsibilities among the various institutional actors working on service delivery at the central and local levels are not well established or understood due to absence of legal framework. However,  adoption of a legal framework, possibly later this year, will hopefully clarify roles & responsibilities. Until then, engagement needs to be gradually incremental, because the roles are evolving and currently unclear to all.

The engagement of a national experienced partner with multidisciplinary expertise, that were able to visit the municipalities to conduct extensive consultations, led to the production of an excellent finding of the training needs of the MMPW and the municipalities in the 18 governorates.

4. 5  List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

UNDP’s key partnerships have been outlined above in 1.3

  - Summarize achievements against planned results for cross cutting issues: Security,

gender, human rights, employment (including# of short and long-term job created), and environment.

The project created employment indirectly through sub-contracting some activities to Iraqi companies.

The project ensures the direct and full participation of both men and women in strategic planning, needs assessments, meetings and workshops.

V.Future Work Plan

Management Skills for Middle Managers: Human Resources Management (one module, expected delivery: end January),

ToT for MMPW Training Centres on Decentralization of Service Delivery (one module, expected delivery: February 08),

Seminar on Financial Management and Internal Audit (expected delivery: February

08),

Leadership Skills and Gender Issues in Municipal Work/Service Delivery (one module, expected delivery: March 08).

Facilitation of partnership agreements between Iraqi and regional municipalities.

Carryout an evaluation  of the project activities with partners, leading to recommendations and detailed proposal for second phase implementation.