Narrative Report

(C9-10)

UNDP Media Constitution

January – June 2007

- Purpose:

  - This project sought to strengthen media reporting on the current Iraqi political process, in particular on the draft constitution in the run-up to a national referendum in October 2005 and a general election in December 2005. The project sought to collect and disseminate throughout the country reliable, impartial reports so all Iraqi communities could have equal access to the information they needed to take part in national, regional and local politics and civil society.

The project also aimed to lay the foundation for a permanent independent news agency in the belief that Iraq cannot develop democratic politics or an efficient economy without an independent, reliable source of national news. The objective during the project period was to expand the network of contributors to include all parts of Iraq and to more than double the output of news carried on the Aswat al-Iraq website to approximately 2,000 items a month, covering all important national and regional developments. The viewpoints of all main ethnic and different communities of the country were to be reflected.

The project was also designed to include a training component that would give up to six journalists intensive on-the-job experience in sub-editing on Aswat al-Iraq’s newsdesk, temporarily based in Cairo.  Courses would be run in other venues such as Amman, Beirut or Cairo to train journalists in news reporting skills and train photographers ahead of the launch of a planned photo service.

  - Aswat al-Iraq was launched in November 2004 in the belief that Iraq could not develop democratic politics or an efficient economy without an independent, reliable source of national news.

Media in Iraq before the project started, while free from the censorship and government control of the past, lacked the human and financial resources to cover political and economic developments adequately. In the absence of a national news agency, each newspaper and broadcaster was struggling to report the country with its own network of correspondents, hampered by political violence and poor communications. Specialist coverage of the economy and business was rudimentary.

Some Iraqi editors argued that the entire survival of independent media in Iraq might depend on the establishment of a news agency. They said even the biggest newspapers were fighting to stay afloat financially; revenues were limited because political violence was hampering distribution and constricting advertising. The only thriving publications were those funded by political parties or other outside sources, which were clearly not independent. A news agency would provide a mechanism for independent media to cut costs by sharing the expenses of newsgathering. International and Arab media, government and business also required an improved level of news coverage from across Iraq to inform public opinion and provide a firmer basis for policy-making and investment.

The importance of communication to the MDGs is conclusive. “The success of current development policies will therefore depend upon citizens, particularly those living in poverty, being able to hold governments to account and to engage actively as informed citizens (…) It believes that genuine involvement and participation can only occur if the information needs of all citizens (including those at the margins of societies) are met, and the voices of those most affected by development decisions are heard”. In this direction, Aswat al-Iraq has ensured access to its service by even the poorest sectors of society by providing news using an inexpensive internet-based platform that can currently be accessed for free. Besides, in an effort to make its service relevant to all Iraqis, Aswat´s news coverage goes beyond the day’s political and security stories to include reports on those hit hardest by the violence in Iraq, including refugees, the unemployed, the underemployed and the sick.

  - The main international implementing partner is Reuters Foundation; the charitable arm of Reuters Group Plc. Reuters Foundation has provided project management, training and planning support to Aswat al-Iraq from its inception, aiming to transfer Reuters’ unique knowledge of how to finance independent news reporting.

The Reuters Foundation’s general management was provided by a RF project manager and supervising consultant, an Arabic-speaking former senior editorial manager for Reuters who project-managed Aswat al-Iraq part-time. The supervising consultant was succeeded by an Arabic-speaking veteran Reuters reporter and manager, who managed the project full time from the end of September onwards.

Day-to-day editorial supervision was provided by a temporary Cairo-based editing desk set up by Reuters Foundation and managed by the former editor of Reuters Arabic Service, who also directed all of the Arabic-language training courses and workshops for Aswat al-Iraq’s journalists. The General Counsel’s Office of Reuters provided internal and external expertise to guide the structuring of the agency’s legal entity so that Aswat al-Iraq will be properly constituted as an independent news service, with suitable guarantees to protect it from improper influences and biased direction. Reuters Foundation’s accountants managed the financial resources deployed during the project and provided reporting to donors.

Reuters also provided free internet access to Reuters’ Arabic service, allowing editors at Aswat al-Iraq to see what news Reuters was publishing in Arabic and how news was being covered.

The main national implementing partner is the Board of Directors and Editorial Committee of Aswat al-Iraq itself. A team of senior Iraqi journalists was recruited to manage and develop the news agency:

The Editorial Committee is responsible for day-to-day management:

- Editor-in-Chief

- Managing Editor

- Editorial Secretary

- Editorial Secretary (Kurdish service)

The Board is responsible for strategic direction:

- Chair of Board is the distinguished Iraqi sociologist.

- Three editors of independent newspapers (from Baghdad, Sulaimaniya and Basra) are non-executive directors.

- The Editor-in-Chief, Managing Editor and Editorial Secretary are executive directors

Monitoring has been achieved by the following mechanisms:

Daily monitoring of editorial quality by the news-editing desk (temporarily located in Cairo) and senior editors

Monthly reports from the management team to the project supervisor and from the project supervisor to the UNDP project manager

Three-monthly meetings between the project supervisor, the head of the Cairo desk and the Iraqi management team outside Iraq (in London, Amman, Beirut and Cairo). Regular meetings between UNDP project manager, project supervisor, the head of the Cairo desk and the Iraqi management team.

Frequent telephone and e-mail contact between the UNDP project manager, the project supervisor and the Iraqi management team.

- Resources

Financial Resources:

- US$ 993,751 (Jul-05) + 355,000 (Dec-06) from Iraq Trust Fund (IRFFI)

- US$ 217,000 from TRAC 1.1.1. UNDP own resources (in 2005)

- US$ 125,000 from TRAC 1.1.1. UNDP resources (in 2006) / Spanish Agency for International Cooperation (AECI)

- TOTAL Project Cost (UNDG ITF and non-TF): US$ 1,690,751

A) Total Sub-Project Cost 00046540 Reuters Media Constitution

- US$ 826,341+ 48,607 (Jul-05) + 355,000 (Dec-06) from Iraq Trust Fund (IRFFI)

- US$ 217,000 from TRAC 1.1.1. UNDP own resources (in 2005)

- US$ 125,000 from TRAC 1.1.1 UNDP resources (in 2006) / Spanish Agency for International Cooperation (AECI)

- TOTAL Sub-Project BUDGET (UNDG ITF and non-TF): US$ 1,571,948

B) Total Sub-Project Cost 00046535 UNDP Media Constitution

- US$ 118,803 (Jul-05) from Iraq Trust Fund (IRFFI)

- TOTAL Sub-Project BUDGET (UNDG ITF and non-TF): US$ 118,803

Additional funding has been granted by the Spanish Agency for International Cooperation and implementation has been carried out from mid-December 2006 through June 2007.

In addition, the Spanish Agency for International Cooperation has earmarked to UNDP-Iraq extra funding to the Aswat al-Iraq’s project for July 2007 through July 2009 to consolidate Aswat’s development into a national news agency able to sustain itself through grant requests and revenue from its services.

Additional resources are of the utmost important and are being sought to complement the funding in the third phase of the project to develop a sales structure and bolster editorial to ensure the structures are in place that will make Aswat al-Iraq a self-financed, subscription based service within a few years.

Human Resources:

Aswat al-Iraq has 50 staff of different job functions at the culmination of the project period; editorial managers, reporters in all Arab and Kurdish governorates, English and Arabic translators, photographers, Arabic and Kurdish sub-editors, and support staff. In addition to the staff of Aswat, the UNDP and Reuters Foundation’s team based in Amman and London respectively are involved in the day-to-day project management and implementation

- Method of Operating:

xxxxxxxx

- Results:

During the project period, Aswat al-Iraq expanded its editorial network to cover all of Iraq’s 18 governorates and doubled its output of news items in Arabic, English and Kurdish to nearly 2,000 news items a month covering politics, business, sports and culture. An Iraqi editor-in-chief was recruited.

This progress was achieved despite increasingly threats to the safety of staff, which forced the temporary evacuation of the senior management team from Baghdad to Cairo and closure of the agency’s main office in Baghdad. However, security threats and recruitment problems delayed the launch of a much-needed photo service.

Here is a summary of the main project developments:

Aswat al-Iraq published a comprehensive news service from a network of correspondents across Iraq, emphasising particularly political and security news but with increasing numbers of stories on the economy, particularly oil, and on culture and sports. The number of stories published in Arabic increased from less than 1,000 a month at the start of the project to around 1,500 a month. English output almost tripled to 350 stories a month and Kurdish output rose to 150 from about 100 stories a month.

The most-read story was a detailed investigation of the killing by US forces of the insurgent leader Abu Musab al-Zarqawi in April. The most popular subjects, judged by the number of retrievals from the website, were business (particularly oil), freedom of the press, women, off-beat human interest stories and exclusive political stories – as well as news on the death sentence and execution of former president Saddam Hussein.

Aswat’s network of correspondents was expanded to around 40 covering all 18 of Iraq’s governorates, from 15 at the start of the year. Additional and replacement correspondents were recruited in a number of governorates where coverage had been weak, notably Basra and Anbar.

News items from Aswat al-Iraq were extensively published in all of Iraq’s leading daily newspapers, whether independent, government-funded, or party-funded.

Despite the challenges of finding a suitable, experienced Iraqi with the appropriate background to lead Aswat al-Iraq’s management team and be based in Iraq, Aswat managed to recruit a veteran journalist with more than 25-year journalistic career, as editor-in-chief. The editor-in-chief identified and secured new recruits to the network of correspondents worked with Reuters Foundation’s project manager and represented Aswat effectively in international meetings.

Increasingly threats to Aswat staff disrupted the agency’s operations. Three key reporters in Baghdad decided to leave the country because of increasing violence.

Security threats and recruitment problems delayed the launch of Aswat’s photo service, which had been planned for March. Competition for competent photographers made it difficult to recruit a suitable chief photographer to run the service, and when one was found he resigned after being threatened. Resignation of our computer support engineer disrupted efforts to solve technical issues with uploading of photos to an Internet publishing platform.

A mixture of technical and project management problems delayed Aswat’s move to a new website publishing system, Campsite. Essential customisation of the system was completed on time by the developers in February. But a series of floods at the company engaged to host the system, caused delays, as did the lack of a full-time project manager at Reuters Foundation to drive work forward.

The text of a constitution was drafted to register Aswat al-Iraq as an Iraqi non-governmental organisation with the Iraqi Planning Ministry. However, the drafting was much delayed by the difficulties of coordinating work by an Arabic-speaking lawyer in Baghdad with patchy Internet access and English-speaking lawyers advising Reuters Foundation in London. Too much translation and redrafting work fell to the part-time project manager at the Foundation.

Reuters Foundation recruited a full-time project manager to start work at the end of September to ensure sufficient management resources are available to meet future work deadlines.

The project’s measurable indicators included the website logs recording the number of news items carried each month. When Aswat still had a fully functioning office in Baghdad – now closed apart from administrative staff for security reasons – it monitored usage of news items in Iraq’s main print media. Reuters Foundation, as project implementing agency, provided UNDP with a list of governorates covered, the names of stringers in each, and regular updates with quantitative assessments of developments.

Operation of the news agency

Reporting of more than 50 news items every day by a network, which totalled around 40 correspondents in all 18 Iraqi governorates by mid-December.

Direction of the file by a team of three Iraqi editorial managers, based until May in Baghdad and after that in Cairo as a temporary security measure.

Editing of news items in Arabic by a team of 5 Egyptian sub-editors in Cairo, and more recently also by newly trained Iraqi sub-editors.

Translation of news items into English by an Egyptian specialist journalist in Cairo. An Iraqi specialist journalist came on board in early August, significantly boosting output.

Editing of news items in Kurdish and translation of news items into Kurdish by a team of three Iraqi sub-editors in Sulaimaniya.

Recruitment of new editorial staff

Editor-in-chief Zuhair al-Jezairy recruited

Correspondents were recruited to expand coverage network from 15 to all 18 of Iraq’s governorates and strengthen coverage in Basra and Anbar.

Office space

Aswat moved into temporary new office space at the Egyptian Press Syndicate in mid-January 2006. Reuters had provided office space, computers, Internet access and an international telephone line in its Cairo bureau for more than a year at no charge. But space was limited. The new office allowed the immediate recruitment of a full-time chief translator for the English service and an additional sub-editor for the Arabic service. As a result, output of the English service quadrupled in February, and the Arabic service processed more than 1,000 news items in a month for the first time. The new office also gave space for intensive on-the-job training of Iraqi sub-editors.

Aswat closed its headquarters office in Baghdad because of security threats.

Aswat rented a house to provide larger office premises in Sulaimaniya, moving out of a very constricted space in the offices of the Kurdish newspaper partner. The aim of the new space was to provide a base inside Iraq for the editing desks currently in Cairo and to provide facilities to run training courses inside Iraq.

Training

- Nine Iraqi journalists, including the three members of the Aswat editorial management team, received intensive on-the-job training in sub-editing in Cairo.

- Two training courses in business news were held in Beirut for a total of 12 journalists from Aswat and 9 from other Iraqi media. One was run by Reuters Foundation and the other by Aswat itself in conjunction with the NGO Reseau de Liberte

- A training course in photo-journalism, with lectures on personal safety, was run in Baghdad for 12 journalists from Aswat, 4 from Iraqi newspapers and 5 new recruits.

Intensive training in use of Adobe Photoshop image editing software was run in Baghdad for two senior photographers.

Two Aswat photo editors received intensive training in Cairo from a former Reuters photographer on photo editing, photo-journalism ethics and photo-related technology.

The Editor-in-Chief spent several days observing Reuters editorial operations in London. He joined editorial meetings and shadowed journalists on Reuters World Desk, Picture Desk, Sports Desk, Energy Desk and London reporting unit.

Six Aswat journalists attended a one-week Journalism training course in December 2006 run by Euro Arab Management School (EAMS) in Spain.

Security-related issues

The security situation in Iraq worsened sharply in February 2006. The security situations continued to deteriorate thereafter. A complete report on security-related issues concerning the implementation of Aswat al-Iraq’s project is available upon request to UNDP-Iraq.

Photo service development

A network of 14 part-time photographers was recruited in 10 governorates.

Camera equipment (Nikon D70 digital SLR cameras) was purchased for three full-time photographers in Baghdad. Computers and software were purchased to edit photos.

A web-based publishing platform, webdesk, was licensed and implemented at http://www.photos.aswataliraq.info.

More than 500 photos were gathered from photographers and stringers, concentrating on stock shots of people and places.

Launch of the service was delayed by security problems, which caused the resignations of two key staff and by technical problems uploading photos from Baghdad.

Website publishing system development

The Campsite website publishing system (www.campware.org) was customised for the essential requirements of a real-time news agency.

A computer company which has developed and hosted successful Arabic implementations of Campsite, created an implementation of Campsite for Aswat. This included a new, more user-friendly layout for the site and new more colourful graphics, and a full Kurdish interface.

Illustrated user guides to Campsite in English and Arabic were created for journalists and editors.

Logon identities were created for all Aswat’s current reporting and editing staff.

Registration of legal entity

After expert advice from Aswat’s Iraqi lawyers, it was decided that the agency could not be registered in Iraq as a commercial company with a governance structure that would protect the agency from being dominated in time by a single interest group or faction. However, the agency could be registered as a non-governmental organisation at the Planning Ministry, which would allow an appropriate governance structure without restricting its ability to generate commercial revenues.

The Aswat’s Iraqi lawyers redrafted Aswat’s proposed constitution to make it appropriate to an NGO rather than a commercial company.

Reuters, supported by its pro-bono legal advisers Slaughter and May, prepared registration of a separate UK entity, owned initially by appointees of Reuters, to act as the Council of Trustees of Aswat al-Iraq, protecting the agency from any attempt to undermine its editorial or managerial independence.

While the absolute impact of the project may be difficult to measure without a sweeping countrywide survey, informal feedback from a variety of Iraqi and foreign media indicate that the impact has been notable and positive.

A broad spectrum of Iraq and foreign media have come to rely on Aswat al-Iraq’s balanced reporting, giving some quantitative and some anecdotal indication of the impact the agency is having. The expected impact of the project longer term is that Iraqi citizens will have balanced news coverage they need to become active and knowledgeable participants in their country’s politics, economics and society.

The impact will include greater public trust in at least one element of the Iraqi media scene and will also include an increase in the professionalism of a sector of the Iraqi media and Iraqi journalists, who have been trained by, worked for, read, used or subscribed to Aswat al-Iraq.

- Future plan:

- Produce news coverage of Iraq in Arabic, Kurdish and English

The Aswat al-Iraq news agency operation producing textual news coverage of Iraq in Arabic, English and Kurdish will continue throughout the period from mid-December 2006 through June 2007 – and beyond, as funding allows. With funding from the Spanish Agency for International Cooperation (AECI), in the mid-December 2006 through June 2007 period, the project’s implementation will include the following activities:

A network of more than 40 correspondents in Baghdad and Iraq’s 17 other governorates.

A team of 3 Iraqi editorial managers directing news coverage and supervising editing of content in Arabic, and supervising the editors of the English and Kurdish services.

Arabic editing desk and English translation desk in Cairo moving to Erbil (or Amman) in early 2007.

Kurdish editing and Kurdish/Arabic translation desks in Sulaimaniya directed by editorial manager.

Production will rise to approximately 2,100 news items a month in the three languages combined.  There will be particular emphasis on developing business news coverage, concentrating on oil and reconstruction news, and on expanding services in English. This will support the earnings potential from Arab and international business, government, NGO and media customers.

The editorial management team and Aswat’s Arabic and English desks will move from Cairo to Erbil (or Amman) in early 2007, once sufficient Iraqi sub-editors and translators have been recruited and trained, so that the headquarters of the agency will be located closer to Iraq. The current temporary training centre and sub-editing desk in Cairo will be scaled down. A news office will be set up in Erbil (or Amman) on a temporary but probably medium-term basis, until conditions in Baghdad improve enough to make a return there safe and logistically viable.

A very productive Aswat al-Iraq Board meeting was held in February 2007 to review its plans for 2007 and prepare to admit a number of Iraqi media and civil society organisations as members of the agency (see Annexes for report on Aswat al-Iraq Board meeting Feb-07)

- Launch news pictures service

Aswat al-Iraq will launch a still photo service in early 2007. This operation will include:

Network of two staff photographers based in Baghdad, and stringer photographers and text correspondents trained to shoot photos in Iraq’s 17 other governorates.

Two desk editors directing photo coverage, editing photos and captions and uploading photos for distribution.

- Commercialisation of Aswat al-Iraq news services

A marketing and sales operation will be established to begin selling Aswat al-Iraq’s textual news and photos services commercially to customers in Iraq and internationally. This operation will grow to include:

Sales and Marketing Manager – probably based in Amman or Sulaimaniya -- able to travel to sell to international media.

Sales executive selling to international media.

Three sales executives selling to Iraqi media.

Location of sales executives to depend on who is recruited and security considerations.

Training for sales manager and executives

The Campsite textual news website publishing system and the WebDesk still photo publishing system will be implemented to support secure Internet delivery of Aswat al Iraq’s services to paying customers.

- Train Aswat al Iraq journalists, managers and sales staff

A programme of training workshops in Spain and attachments to Spanish media will be organized. The provisional timeline is as follows:

Up to 6 Aswat journalists will attend a second Spanish training course in 2007.

2-6 Aswat journalists/photographers will do a training attachment at a Spanish media organisation: Spanish news agency EFE, Spanish newspaper (El País) and Radio Nacional de España (Servicio Árabe - Radio Exterior)

2-4 journalists will to a training attachment at the Arabic service of the Spanish news agency EFE

Follow-up training will be conducted on a regular basis for new Arabic sub-editors who have already received their training in Cairo.

Two new translators for the English service will receive intensive training from current translators Nadia and Saleem. One of the prospective recruits is based in Baghdad and will be trained remotely with exercises, including written and verbal follow-up, by e-mail and telephone. The second prospective recruit is based in Cairo, and will receive face-to-face on-the-job training.

UNDP and Reuters Foundation’s aim is to equip Aswat al-Iraq to be managerially self-sufficient and to have started to earn revenues from its services by the end of 2007. From 2008, the agency needs to be well enough established to handle its own fundraising from donors and manage its own development without the need for day-to-day supervision by a project manager provided by UNDP and/or Reuters Foundation, even if UNDP and/or Reuters Foundation continue to offer a range of support in training and advice.

This goal can only be achieved if sufficient donor funding is committed to Aswat al-Iraq to cover the entire July 2007-end 2009 period.

# Footnotes

“Reference Paper on Communication for Empowerment” Oslo Governance Centre, United Nations Development Programme