- United Nations Development Group Iraq Trust Fund

- Project #:C9-10e

- Date and Quarter Updated: 17 June2008/ 2nd Quarter 2008

| Participating UN Organisation: UNDP | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: DEX/UN/NGO |  |

| Title | Involving the Iraqi Media and Journalists in Covering the Constitutional Process |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Iraq |  |  |  |  |
| Project Cost | $993,752 + USD342,000 from UNDP resources |  |  |  |  |
| Duration | 01 June 2005 – September 2007 – extension requested to end June 2008 |  |  |  |  |
| Approval Date (SC) | 08 June 2005 | Starting Date | 05 June 2005 | Completion Date | extension requested to end June 2008 |
| Project Description | The project seeks to strengthen media coverage of the Iraqi political process, in particular the political process, and to establish an independent news agency in Iraq. |  |  |  |  |

- Development Goal and Immediate Objectives

To promote debates among the Iraqis on wide-interest issues that Iraqis would like to address through the Constitution; involving local communities through the media in discussion on political and constitutional processes. IO1: To strengthen media coverage of the Iraqi political and constitutional processes. IO2: To establish an independent Iraqi news agency, Aswat al-Iraq. IO3: To expand the network of correspondents of Aswat to nationwide status. IO4: To support a training component within Aswat al-Iraq.

- Outputs, Key activities and Procurement

| Outputs | - Aswat’s coverage included hundreds of articles on political developments related to the constitutional process - Aswat doubled its output to around 2000 news items a month in Arabic and 350 a month in Kurdish - Aswat expanded its network of correspondents to cover all governorates - A team of senior Iraqi journalists was recruited to manage the newsagency - Aswat’s reports were widely published in Iraqi and regional media - Over 40 Aswat correspondents received training - Aswat developed a new website - Steps were taken to regularise the legal status of Aswat in Iraq while protecting its editorial independence |
| --- | --- |
| Activities | - Operate Aswat al-Iraq news agency in English, Arabic and Kurdish - Expand Aswat’s network to nationwide - Train journalists in political and constitutional news reporting - Develop website publishing system - Registration of Aswat as a legal entity |
| Procurement (major items) | Reuters Foundation was selected as UNDP’s implementing partner |

| Funds Committed | 993,751 I(IRFFI) + 342,000 UNDP resources | % of approved | 100 |
| --- | --- | --- | --- |
| Funds Disbursed | 973,000 (IRFFI) +342,000 UNDP resources | % of approved | 97 |
| Forecast final date | 30 June 2008 | Delay (months) |  |

- Quantitative achievements against objectives and results

| Operation of Aswat | Reporting of more than 50 items per day by a nationwide network of correspondents Trilingual news service developed Expansion of news agency to nationwide coverage Editor in chief and Board recruited | % of planned | 100 |
| --- | --- | --- | --- |
| Training | 5 training workshops on constitutional reporting, business and editing Training in photojournalism, graphics and photo management Training at EFE news agency in Spain | % of planned | 100 |
|  | New website developed and registration of legal entity | % of planned | 75 |

- Qualitative achievements against objectives and results

Aswat al-Iraq expanded its coverage to nationwide and in three languages. This was achieved despite security constraints (including the murder of three correspondents in 2007). Management has ensured that the correspondents represent the diversity of Iraq’s population and hires men and women correspondents The remaining USD25,000 is being spent on running costs for the media programme and UNDP is seeking operational and financial closure of this project end June 2008.