# United Nations Development Group Iraq Trust Fund

# Project #:C9-12

# Date and Quarter Updated: 4th quarter

# October - December 2008

| Participating UN Organisation: UNDP, UNOPS | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Planning and Development Cooperation (MoPDC) |

| Title | C9-12: Support to Government of Iraq in International Assistance Coordination and Capacity Building |
| --- | --- |
| Location | Baghdad, Erbil, Basra |
| Project Cost | $2,643,000 |
| Duration | 42 months |
| Approval Date (SC) | 09 November 2005 | Starting Date | 1 January 2006 | Completion Date | 30 June 2009 (expected) |
| Project Description | The provision of technical expertise, hardware and software for international aid coordination, as well as multidimensional capacity building in donor and inter-ministerial coordination |

# Development Goal and Immediate Objectives

Development Goal: The overall goal of the project is to assist the Government of Iraq in establishing a comprehensive inter-ministerial, decentralized, sustainable, transparent and accountable aid coordination system, based on multidimensional capacity building of 4-6 ministries and 2-4 Southern Governorates to be specified at early stages of the project Immediate Objective 1: The Government of Iraq through each of the designated Ministries are able to take informed and grounded decisions on the mobilization and coordination of the aid into the country. This project should contribute to achieving tangible and sustainable results in the reconstruction and development of Iraq. Immediate Objective 2: The Government of Iraq is able to define an e-governance strategy and is equipped with pilot e-governance systems, including interactive web portals of listed key Ministries. Immediate Objective 3: To contribute to the decentralization process through building capacity of the newly established Provincial Councils, among others, in aid information management and integration with the Government lead aid coordination system, in the Lower South of Iraq.

# Outputs, Key activities and Procurement

| Output 1.1: DAD management units (DMU) are established in designated Ministries, and respective employees are appointed and trained accordingly. | Activities: 1.1.1. Thorough needs assessment in all designated Ministries to identify training required 1.1.2. Capacity building of listed Ministries in various dimensions of aid coordination and DAD operation, administration and maintenance through training and workshops both inside and outside Iraq. 1.1.3. Mechanisms and regulations ensuring the sustainability of data collection, updates, and dissemination as well as management processes are designed and implemented. Procurement: Contractors, Consultant, Training |
| --- | --- |
| Outputs 1.2: Donor Assistance Databases are developed, installed, hosted and operational in six ministries and interconnected to enable data flow among them and a comprehensive analysis of international assistance. | Activities: 1.2.1. Thorough needs assessment in all designated Ministries to identify and design hardware specifications and DAD functionality 1.2.2. Development, installation and technical support of DAD software applications in designated Ministries 1.2.3. Initial input and regular update of contents 1.2.4. Monitoring, evaluation and quality control of input data 1.2.5. Training in administration and maintenance Procurement: Contractors, Consultants, Software and hardware |
| Outputs 2.1: Establishment of Internet connectivity and local networking for designated Ministries | Activities: 2.1.1. Design of network architecture 2.1.2. Long-term contracting of a local Internet service provider (ISP) 2.1.3. Implementing local networks and connectivity in designated Ministries Procurement: Contractors, Consultants, IT infrastructure |
| Outputs 2.2: Development and installation of interactive web portals of the designated Ministries for publishing key data and reports on international assistance on National and Ministerial sector / community levels | Activities: 2.2.1. Development of recommendations on the implementation of an e-governance framework in Iraq 2.2.2. Development, installation and technical support of web portals 2.2.3. Initial input and regular update of contents 2.2.4. Monitoring, evaluation and quality control of input data 2.2.5. Training in administration and maintenance Procurement: Contractors, Software |
| Outputs 3.1: A framework and procedures are designed on the use of DAD by the governorates and data management and supply from governorates to DAD. | Activities: 3.1.1. Development of guidelines for data gathering and input. 3.1.2. Conducting a workshop on DAD use and data management. Procurement: Consultant, Training |
| Outputs 3.2: Information Coordination Centre for data gathering and processing established and 25 university staff trained in data gathering and processing | Activities: 3.2.1.Signing of MoU with University 3.2.2.The setting-up of the equipment, with the intended location at University 3.2.3. Selection of Staff for the centre, consisting of twenty-five(25) Procurement: Contractors, Equipment |
| Outputs 3.3: Planning Centre for all 4 governorates of the Lower South (located in Basra) established. 12 local government staff from 4 LS governorates trained in information managements, analysis and planning. | Activities: 3.3.1. Training of the staff. 3.3.2. Conduct two filed surveys during the duration of the project Procurement: Consultant, Training |

| Funds Committed | $2,643,000 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | $2,319,866 | % of approved | 88% |
| Forecast final date | 30 June 2009 | Delay (months) | 18 months |

# Quantitative achievements against objectives and results

| 1.1 DAD management units (DMU) are established in designated Ministries, and respective employees are appointed and trained accordingly. | 20 capacity building courses delivered. Final training delayed until 2009 until technical development completed | % of planned | 90% |
| --- | --- | --- | --- |
| 1.2 DADs are developed, installed, hosted and operational in six ministries and interconnected to enable data flow among them and a comprehensive analysis of international assistance. | DAD-Iraq fully operational and DAD-Kurdistan launched in 2008. Residual development required to upgrade DAD KRG, align aid with national budget and improve synchronization between DAD Iraq & DAD KRG. | % of planned | 80% |
| 2.1. Establishment of Internet connectivity and local networking for designated Ministries | Internet connection provided to MoPDC in 2006-2007 and for MoP KRG in 2008; equipment provided to MoP KRG, MoMPW and MoEl. Long term solution for servers hosted in UNDP Iraq to be sought. | % of planned | 90% |
| 2.2. Development & installation of interactive web portals of the designated Ministries to publish key data & reports | MoPDC portal fully operational; MoMPW finalised and MoP KRG portal in final stage of development. | % of planned | 90% |
| 3.1. A framework and procedures are designed on the use of DAD by the governorates and data management and supply from governorates to DAD | Fully achieved | % of planned | 100% |
| 3.2. Information Coordination Centre for data gathering and processing established and 25 university staff trained in data gathering and processing | Fully achieved | % of planned | 100% |
| 3.3. Planning Centre for all 4 governorates of the Lower South (located in Basra) established. 12 local government staff from 4 LS governorates trained | Fully achieved | % of planned | 100% |

# Qualitative achievements against objectives and results

Overall, the project is now in the final stages of assisting the Government of Iraq to establish a comprehensive inter-ministerial, decentralized, sustainable, transparent and accountable aid management system, based on multidimensional capacity building both at the central Government and regional/sub-national levels. DAD Iraq, an aid information management system, has been successfully implemented under the ownership of the MoPDC, the primary counterpart of the project, and the completion of a large number of training workshops has had a significant impact on the capacity of GoI to manage aid flows to Iraq. Considerable progress has been made to achieve Outcome 1, focused on enabling the Government of Iraq to improve the mobilisation and coordination of aid. Since DAD-Iraq was deployed, it has been continuously maintained and MoPDC have now taken full responsibility and ownership for it. Remaining development activities are also due to be implemented following agreement of design by MoPDC. In addition, a regional subset, DAD Kurdistan, was successfully launched in 2008 by the Ministry of Planning – Kurdistan Regional Government (MoP KRG). New services have been requested by MoP KRG and the project team worked hard to deliver these by end of 2008. Final training and handover for both DAD Iraq and DAD Kurdistan will be conducted in 2009. Considerable progress has also been made to achieve Outcome 2, focused on enabling the Government of Iraq to take advantage of the potential of e-governance. In particular, equipment and internet connectivity has been provided to both MoPDC and MoP-KRG. As a product of training activities conducted during the reporting period, the bi-lingual MoPDC portal is now operational and in use by the Ministry to communicate their mission, organisation, news and other updates. Portal development for Ministry of Municipalities and Public Works has been finalised and the portal for MoP KRG is in the final stages of design. Outcome 3, focused on building the capacity of the Provincial Councils in the Lower South of Iraq in aid information management, has been fully completed by the responsible agency, UNOPS.