# United Nations Development Group Iraq Trust Fund

# Project No.:  49911

# Date and Quarter Updated:  January-March 2009

Participating UN Organisation: UNDP Sector: Governance Government of Iraq – Responsible Line Ministry: Board of Supreme Audit

| Title: | Institutional Strengthening Programme for the Board of Supreme Audit (BSA) |
| --- | --- |
| Geographic Location: | Iraq (country wide) |
| Project Cost: | 4,879,535.98 USD |
| Duration: | 1 January 2006- 30 June 2009 |
| Approval Date (SC): | 29 October 2005 | Starting Date: | 1 January 2006 | Completion Date: | 30 June 2009 |
| Project Description: | Institutional strengthening programme to promote transparency and efficient management of public funds. |

# Development Goal and Immediate Objectives:

The project’s main development goal is to promote good governance, honesty, transparency and accountability in the use and management of public resources by strengthening the capacity of the BSA of Iraq, realizing the outcome "Strengthening Institutional and Administrative Infrastructure” in the UN-Iraq Assistance Strategy Matrix. The project’s main objectives are: To conduct and complete a Training Needs Assessment of the BSA; To conduct research, from international experiences, on money laundering to develop future audit programmes (assessment of Australian & Canadian experiences); To conduct off-the-shelf short-term courses around the Arab Region for 269 auditors in priority areas: 4. To conduct Train-the-Trainer workshops to develop the long-term training programme for 3 groups of 30 audit practitioners in the areas of: financial auditing and fraud detection – revenue and expenditure; computer auditing; and performance audit; To conduct a workshop that aims to develop the capacities of 30 technicians in coordinating and supporting the introduction of the audit operations’ computerization as well as BSA’s administrative systems, and to develop a guide to this effect; To develop and disseminate Audit guidance on the training activities referred above; a code of conduct to BSA based on INTOSAI code of ethics; To adapt and to disseminate BSA guide on fraud awareness and detection; To ensure the sustainability of BSA Iraq’s capacity reinforcement ensured.

# Outputs, Key activities and Procurement

| Outputs: | The project’s outputs, as appear in the Project Document, are: Comprehensive Training Needs Assessment conducted covering 18 regional offices. Research paper and recommendations on ‘money laundering’ audit programmes for BSA drafted and presented. Ten (10) short-term courses for 269 auditors over 44 weeks conducted. Three (3) teams of 30 FRLs (Functional Responsibility Leaders) formed (in financial audit and fraud detection, computer auditing and performance auditing). The FRLs to develop long-term customized training programmes on the above noted subject matters. Three (3) standardized course manuals on the subject matters noted in 4.1 developed. A pool of 30 technicians formed, capable of coordinating and supporting the initiation of the BSA operations’ computerization and a guide produced to facilitate this computerization. Audit guidance and Ethic’s Code manual developed and disseminated. The guide on fraud awareness and detection adapted and disseminated. Three (3) experimental audits conducted. The Institutional Strengthening Committee (ISC) and workgroup formed. A secretariat established to support BSA’s needs in coordinating future activities with donor agencies. BSA (strategic and operational) institutional strengthening plan developed. |
| --- | --- |
| Activities: | Comprehensive Training Needs Assessment Study Tour on Money Laundering Performance Audit Course Debt Accounting and Audit Course Fraud Detection Audit Course Aid Management and Co-ordination Audit Course Procurement and Contract Management Audit Course International Standards and Guidelines Course Privatisation Audit Course Information Technology Audit Course Incomplete Records Audit Course Financial Audit Course Long Term Training Programme IT Technician Training Workshop Institutional Computerisation Guide Electronic Document Management System Audit Guides Code of Conduct Fraud Awareness and Detection Guide Experimental Audits Institutional Strengthening Committee Training and Donor Aid Co-ordination Secretariat Institutional Strengthening Plan |
| Procurement: (major items) | Electronic Document Management System Video-conference equipment |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 228 | 112% (overall) 47 additional BSA staff were trained |
| Women | 202 |  |
| Children | n/a | n/a |
| IDPs | n/a | n/a |
| Others | n/a | n/a |
| Indirect beneficiaries | n/a | n/a |
| Employment generation (men/women) | As a capacity building programme; the project will generate little employment |  |

| Funds Committed | 100 | % of approved |  |
| --- | --- | --- | --- |
| Funds Disbursed | 90 % | % of approved |  |
| Forecast final date | 30 June 2009 | Delay (months) | 24 months |

# Quantitative achievements against objectives and results

| Comprehensive Training Needs Assessment Study Tour on Money Laundering Performance Audit Course Debt Accounting and Audit Course Fraud Detection Audit Course Aid Management and Co-ordination Audit Course Procurement and Contract Managment Audit Course International Standards and Guidelines Course Privatisation Audit Course Information Technology Audit Course Incomplete Records Audit Course Financial Audit Course Long Term Training Programme IT Technician Training Workshop Institutional Computerisation Guide Electronic Document Management System Audit Guides Code of Conduct Fraud Awareness and Detection Guide Experimental Audits Institutional Strengthening Committee Training and Donor Aid Co-ordination Secretariat Institutional Strengthening Plan | 100 100 100 0 100 100 100 100 100 100 100 100 100 100 100 50 100 100 100 100 100 100 100 | % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned |  |
| --- | --- | --- | --- |

# Qualitative achievements against objectives and results

Output – Incomplete Records Audit training Course A two-week training course in incomplete records auditing for twenty-four auditors from the BSA was given in Amman, Jordan during October 30 -November 9, 2007. Audit and training experts from the National Audit Office of the United Kingdom prepared and delivered the course. The course provided auditors with improved skills in the basics of financial auditing and auditing in an environment of incomplete records. An improved skill set in the area of “Incomplete Records Audit” would enable BSA auditors to better cope with instances where circumstances dictate that work be completed in offices where some records may be missing. Output – Development of an Institutional Strengthening Plan An international expert in institutional strengthening of Supreme Audit Institutions was hired and brought to Amman in December 2006 to work with the BSA to develop an institutional strengthening plan (i.e. a strategic development plan) charting the BSA’s capacity building course over the next three years. The plan was finalised just before the end of the year. In early 2007, the team re-assembled in Amman and used the plan as the basis for developing a project document and funding request for the second phase of the programme. Output – Training of a Staff Member of the BSA’s Training Secretariat In December 2006, the BSA seconded one of its staff to the UNDP-Iraq. This staff member worked alongside the UNDP-Iraq’s project manager as part of a planned project activity whereby the BSA’s institutional capacities have been strengthened through “on-the-job” training. This activity would ensure a smooth transition of duties and responsibilities from the UNDP-Iraq to the BSA in future stages. Output – Development of the Project Document/Funding Proposal for Phase 2 An international expert in institutional strengthening of Supreme Audit Institutions was hired and brought to Amman in January 2007 to work with the BSA to develop a project document/funding proposal for the second phase of the project. The project document was based on the institutional strengthening plan (i.e. a strategic development plan) for 2008-2010 that was developed in December 2006. Output – Purchase of IT and A/V Equipment for the BSA Training Secretariat Two laptops and an electronic video projector were purchased for the BSA’s training secretariat. Output – Oracle Developer Training Course A three-week training course on the Oracle Developer enterprise system for eighteen (18) information technology technicians from the BSA was conducted in Amman, Jordan during February 18 - March 8, 2007. The course was prepared and delivered by a private sector firm specialising in these types of systems and this type of training. Output – Fraud Prevention and Detection Audit Course (Technical Module) A two-week technical training course in fraud prevention and detection audit for twenty-seven (27) auditors from the BSA was conducted in Amman, Jordan during February 19 - March 1, 2007. The course was prepared and delivered by audit and training experts from the National Audit Office of the United Kingdom. Output – Financial Audit Course A two-week technical training course in financial audit for twenty-nine (26) auditors from the BSA was conducted in Cairo, Egypt during February 25 - March 8, 2007. The course was prepared and delivered by audit and training experts from the Central Auditing Organisation of Egypt. In parallel to the technical training module, the train-the-trainer module of this course for eighteen (18) auditors from the BSA was delivered in Cairo by the Central Auditing organisation during February 25 - March 22, 2007. Output – Procurement Audit Course (Technical Module) A two-week technical training course in procurement audit for twenty-seven (28) auditors from the BSA was conducted in Amman, Jordan during April 9- 19, 2007. The course was implemented in cooperation with the World Bank while the course material was prepared and delivered by audit and training experts from the International Labour Organisation-International Training Centre and the Court of Accounts of Morocco. Output – International Accounting and Auditing Standards Course (Technical Module) A two-week technical training course in international accounting and auditing standards for thirty-nine (39) auditors from the BSA was given in Amman, Jordan from April 16 to 26, 2007. The course was prepared and delivered by audit and training experts from the National Audit Office of the United Kingdom. Output – Int’l Accounting and Auditing Standards Course (Train-the-Trainer Module) A one-week train-the-trainer training course in international accounting and auditing standards for eighteen (18) auditors from the BSA was conducted in Amman, Jordan during June 3 - 7, 2007. The course was prepared and delivered by audit and training experts from the National Audit Office of the United Kingdom. Output – Information Technology Audit Course A training course in information technology audit for twenty-four (24) auditors from the BSA was conducted in Noida, India during June 11 - 30, 2007. The course was prepared and delivered by audit and training experts from the Office of the Comptroller and Auditor General of India. Output – Training of a Staff Member of the BSA Training Secretariat The BSA seconded one of the staff of it Training Secretariat to the UNDP-Iraq for the period of December 2006 - August 2007. This staff member worked alongside the UNDP-Iraq’s project manager as part of a planned project activity whereby the BSA’s institutional capacities have been strengthened through “on-the-job” training. This activity would ensure a smooth transition of duties and responsibilities from the UNDP-Iraq to the BSA in future stages. Output – Performance Audit Course (Technical and Train-the-Trainer Modules) A two-week technical training course in performance auditing for twenty-nine (29) auditors from the BSA, followed immediately by a four-week train-the-trainer module for eighteen (18) auditors, was conducted in Tunis, Tunisia during August 20 -September 28, 2007. The course was prepared and delivered by audit and training experts from the Court of Accounts of Tunisia. Output – Fraud Prevention and Detection Audit Course (Train-the-Trainer Module) A two-week train-the-trainer course in fraud prevention and detection auditing for eighteen (18) auditors from the BSA was conducted in Amman, Jordan during October 21 - November 1, 2007. The course was prepared and delivered by audit and training experts from the National Audit Office (NAO) of the United Kingdom. Output – Pilot Audit Workshop Six (6) auditors from the BSA travelled to NAO offices in the United Kingdom for a one week workshop held during November 26 - 30, 2007. It was the first of four workshops which aims were: (1) to help the BSA to develop institutional audit programmes that comply with international standards, (2) to prepare for a pilot (test) audit, (3) to obtain feedback on the conduct of the pilot audit during the exercise, and (4) to obtain guidance on the completion of the audit. Output – Institutional Strengthening Committee Meeting A meeting was held during December 9-10, 2007 between representatives of the BSA, the UNDP-Iraq, the World Bank, the National Audit Office of the United Kingdom, the Central Audit Organisation of Egypt, the Audit Bureau of Jordan, the Comptroller and Auditor General of India and the United States Department of State. During the first part of the meeting, the delegates analysed the activities that had already been delivered and identified areas of improvement for the future. The second half of the meeting focused on the contributions that various technical partners could make during the second phase of the BSA programme. Output – Institutional Fraud Awareness Workshop A four-day institutional fraud awareness workshop was delivered to eighteen (18) managers and directors of the BSA in Amman, Jordan during December 11 - 16, 2007. The workshop focused on: (1) the role of the supreme audit institution in a country’s overall accountability and transparency framework,(2) the institutions’ relationship with other government entities, civil society and the public and (3)a practical case of fraud detection. Output – Institutional Fraud Awareness Guide A team of five BSA directors spent three days with an international supreme audit institution capacity building expert during December 17 - 19, 2007 in Amman, Jordan. The group drafted a structure for an institutional fraud awareness guide. This was the first of four other meetings that aim to complete the guide and the fraud detection audit plan , which would be applicable in the future for all BSA audits. Output – Fraud Manual Working Meetings (3) Three fraud manual development working meetings were held in Amman, Jordan during August 6- 7, 2008. The working meetings were held between four dedicated senior audit officers of the BSA and an international expert in institutional fraud awareness. The meetings convened to complete work on an ‘Institutional Fraud Awareness Guide’ being developed for the BSA. Output – Pilot Audit Workshops (3) Four pilot audit workshops were held in London, England during July 21 - 25, 2008. Six senior audit officers, chosen to be pilot audit champions within the BSA, attended the meetings. The workshops aim to significantly improve the national capacity for auditing. Output – Procurement Audit Course (Train-the-Trainer Module) A two-week train-the-trainer course in procurement audit for nineteen (19) auditors from the BSA and OFM was conducted in Turin, Italy at the ITCILO Center. The course was implemented in cooperation with the World Bank while the course material was prepared and delivered by audit and training experts from the International Labour Organisation-International Training Centre and the Court of Accounts of Morocco. Output – Institutional Meeting of BSA President with National Audit Office of the U.K A one week meeting between the BSA President and the National Audit Office of the United Kingdom was held in London, UK during December 8 - 16, 2008. The meeting discussed the technical cooperation with the Iraqi Board of Supreme Audit (BSA), as well as the prospects for future cooperation as UNDP- Iraq moves into Phase Two of the Institutional Strengthening Project of the BSA. Output – Oracle Developer Training Course A four-week training course on the Oracle Developer ( Advance level) enterprise system for five (5) information technology technicians from the BSA was held in Amman, Jordan during January 11- February 10, 2009. The course was prepared and delivered by a private sector firm specialising in these types of systems and this type of training. Output – Translation Course An eight-week translation course for the Board of Supreme Translator / Auditors was delivered in cooperation with London Metropolitan University during January 19 – March 13, 2009. The beneficiaries were 23 translators from the BSA. The main objective was to develop the skills of translators in the field of written translation, grammar and the use of translation equipments. Output- Study Tour on Money Laundering A three-day study tour was organized between the BSA President and the Italian Court of Audit Department. The objective of this study tour, which took place in Rome 24-26 March, 2009, was to familiarise the BSA delegation with the legal framework, mission statement, institutional set-up, role & functions of the Italian public authorities.The activity was implemented in cooperation with the International Labour Organisation in Turin-Italy.

Main implementation constrains & challenges

The fact that the UNDP-Iraq project office is located in Amman, Jordan rather than Baghdad, Iraq and the communication difficulties resulting from the security and infrastructure issues in Iraq has caused delays in activity implementation.