United Nations Development Group Iraq Trust Fund 

Project #: C9-21/e
Date and Quarter Updated: 15th January 2009; 4th quarter, October – December 2008
	Participating UN Organisation:  UNOPS, 

	Sector: Governance

	Government of Iraq – Responsible Line Ministry:  Ministry of Council of Representatives Affairs 




	Title
	Support to Parliamentary Affairs and Constitutional Outreach

	Geographic Location
	Nationwide with bulk of activities in Baghdad.

	Project Cost
	US$ 1,067.388

	Duration
	21 months

	Approval  Date (SC)
	5th February 2007
	Starting Date
	12th March 2007
	Completion Date   
	31st March 2009

	Project Description
	This project aims at supporting the process of strengthening the capacities of the Ministry of Council of Representatives Affairs to fulfil its mandate in supporting legislative processes in Iraq. The project also includes a component on support for the process of peacebuilding on community/grass-root level. The project is part of an umbrella programme developed by Cluster C, titled Support to the National Dialogue and Reconciliation process, Institutional Development and Capacity Building, Reconstruction and Stabilization efforts and Promotion of Civil Society and Media Strengthening (UNDP, UNOPS, UNIFEM, UNICEF, UNESCO).


Development Goal and Immediate Objectives
	Development Goal

To contribute to the constitutional and legislative processes in Iraq by strengthening the capacity of the Iraq State Ministry of Council of Representatives  Affairs (MoCRA) to fulfil its law-drafting support mandate as well as by supporting civic education activities initiated by the Civil Society and the Academia on the review process and on parliamentary affairs. 
This project directly contributes to achieving the fourth goal of the UNCT Assistance Strategy matrix: “To promote good governance and democratic processes, assist to uphold the rule of law and establish a human rights regime”.
Immediate Objectives: 

1. Build capacities of the Ministry of Council of Representatives Affairs to provide assistance to other line ministries in the preparation of draft laws, in particular for the implementation of constitution-mandated laws.
2. Encourage participation of the public in the constitutional and parliamentary development process by supporting the civil society and academic world to produce educational resources and carrying out civic education initiatives.


Outputs, Key activities and Procurement

	Outputs
	1.1. Capacity-building plan devised and implemented for MoCRA, to strengthen its administrative and legal capacity. 

1.2. Increased cooperation of MoCRA with regional parliaments and parliamentary support institutions
1.3. Role of MoCRA in supporting the drafting of bills in relation to constitutional-mandated legislation and institutions is more prominent.

2.1. Supported civil society and academic networks to work on civic education programs on the revised constitution and on parliamentary affairs.
2.2. Educational resources made available for awareness campaigns, forums, and conferences through small grants provided to NGOs and CSOs

	Activities
	1.1.1. Assess capacity-building needs of the MoCRA staff in relation to its mandate and current constitutional process and prepare capacity-building plan (parliamentary affairs expert).

1.1.2. Develop training curriculum for MoCRA and identify local / regional training resource persons

1.1.3. Carry out internal training programme based on assessed needs.

1.1.4. Provide administrative development support.

1.1.5. Equip MoCRA with relevant learning resources

1.2.1. Establish twinning agreement with the Arab International Parliamentary Union and the Egyptian’s Ministry for Parliamentary Affairs.

1.2.2. Send selected MoCRA staff for short internships in the counterpart organizations.

1.2.3. Support interaction of MoCRA with the International Parliamentary Union and the POGAR
 (UNDP/UNOPS). 

1.3.1. Facilitate participation of MoCRA staff in various constitution-related activities organized under the programme of the Office for Constitutional Support, in particular multi-party dialogues and study tours.

1.3.2. Support collaborative efforts between MoCRA and the Secretariat of Constitutional Review Committee with regards to providing it legal drafting support.

1.3.3. Promote joint capacity-building activities between MoCRA and the Parliament’s Research Directorate.

2.1.1. Identify network of CSOs and Academic Institutions (AIs) with good track record in the field of civic education.

2.1.2. Receive, select and support proposals to implement innovative civic education projects in relation to the revised constitution and parliamentary affairs, including delivery of school / university classes, focus group sessions, open conferences and forums, and targeting in particular youth and women.

2.1.3. Provide networking support for selected CSOs / AIs before and during the implementation of their small projects.

2.2.1. Production of educational and promotional materials (posters, fliers, brochures, calendars, etc.) by selected CSOs / Academic institutions to support their civic education initiatives. 

2.2.2. Facilitate constant communication stream between CSOs / AIs and the Constitutional Review Committee, as well as MoCRA, on the revised constitution and parliamentary affairs.

	Procurement

(major items) 
	In the reporting period major procurement items were related to provision of transportation, accommodation, training services related to participation of MoCRA staff in training in Beirut as well as training/workshop organized in Erbil  


	Funds Committed 
	USD 786,010
	% of approved
	74%

	Funds Disbursed
	USD 695,058
	% of approved
	65%

	Forecast final date 
	Extended to 31st March 2009 – planned submission of budget revision request
	Delay (months)
	


Quantitative achievements against objectives and results 

	1. Build capacities of the Ministry of Council of Representatives Affairs to provide assistance to other line ministries in the preparation of draft laws, in particular for the implementation of constitution-mandated laws.

	1. National Center for Consultation and Management Development of Ministry of Planning carried out in Baghdad first part of training activities for MoCRA;

2. 6 MoCRA staff members completed workshop on Legislative Drafting organised in Beirut by UNDP POGAR ( 27th October – 1st November);
3. Contacts with Parliamentary Affairs Directorate in Lebanese Council of Ministers established with regards to organising an internship for MoCRA staff. Preparations underway. 


	% of planned
	70%

	2. Encourage participation of the public in the constitutional and parliamentary development process by supporting the civil society and academic world to produce educational resources and carrying out civic education initiatives.

	1. (co-funded with project C9-20): (i) 1 Training on Rapid Participatory Appraisal for 2 NGOs and communities leaders from Baghdad and Kirkuk was organized in Erbil (11th – 23rd October, 17 participants); (ii) 1 Erbil workshop for 2 NGOs and communities representatives from Baghdad and Kirkuk, on presenting RPA findings and community planning was organized (13th – 17th December, 13 participants). 

2. 1 Project on Pecebuilding in Kirkuk district Rapareen continued (implemented by local NGO Insan). 

3. Egyptian company AIDME rendered ongoing TA for the NGOs implementing peacebuiding projects in Baghdad and Kirkuk (shared with project C9-20), 1 dedicated website was established.
	% of planned
	80%


Qualitative achievements against objectives and results 

	Objective 1 

MoCRA staff have been provided with both in-house training offered by the National Center for Consultation and Management Development as well as opportunity to participate in the workshop organised by POGAR in Beirut. This, apart from the benefits of increasing specialised knowledge on law drafting, exposed participating to international contacts and networking. In effect there is a high probability that selected MoCRA staff will have an opportunity to be hosted by the Parliamentary Affairs Directorate in the Lebanese Council of Ministers, where the internship for Iraqis could be organised. 
Objective 2 

Peacebuilding projects in Baghdad (Al Jididah district) and Kirkuk (Rapparin district) contributed to activation of the communities around the peacebuilding issues by the way of support to concrete activities (job creation, support to schools, awareness rising). NGOs and communities carried out Participatory Rapid Appraisal exercise that allowed to assess, in a participatory way, communities’ needs and engage in future planning. 

Projects are underway and are supported by community members and local authorities.

NGOs participating in the project had a unique chance to be trained and to practice techniques of RPA under the guidance of a specialised Egyptian company. This contributed to further development of the communities and involved NGOs.

	


� POGAR is the Programme for Governance in the Arab Region.





