# United Nations Development Group Iraq Trust Fund

# Project #:C9-22

# Date and Quarter Updated: January- March, 1st Quarter 2009

| Participating UN Organisation: UNOPS | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Deputy Prime Ministers Office |

| Title | Assistance for the Establishment of the Secretariat for the International Compact with Iraq (Compact Secretariat) |
| --- | --- |
| Geographic Location | Activities will mostly take place in Baghdad and Erbil, however participants will come from all Governorate Elections Offices. |
| Project Cost | USD 3,414,826 |
| Duration | 12 months |
| Approval Date (SC) | 4th October 2007 | Starting Date | 10th October 2007 | Completion Date | 9th October 2008 |
| Project Description | The project aims to provide assistance in establishing the Secretariat for the International Compact with Iraq (ICI). The Secretariat will be the Government of Iraq’s mechanism in charge of coordinating, monitoring and reporting on the implementation of the Compact. Support will be provided through the engagement of an external management consultancy to support the implementation of the ICI |

Development Goal and Immediate Objectives

Effective, accountable and sustainable Iraqi mechanism for policy planning, program design, monitoring and evaluation to support the implementation of the ICI in line with UNCT Goal 4: Promote good governance and democratic processes, assist to uphold the rule of law and establish a human right regime. The Immediate objectives are: 1. Provide policy, program, technical and administrative support for the implementation of the International Compact with Iraq (ICI) by the identification and contracting of an external management company. The company will • Establish and manage the Administrative and Technical Support Unit • Provide procurement support to the Unit is terms of identifying and contracting consultants (4) in the relevant fields to shadow/ mentor the government staff seconded as programme Officers to the PPU • Select consultants to support the Secretariat administratively and technically on a short term basis as requested by the Secretariat Director • Work with the Compact Steering Committee to develop a programme/ project pipeline 2. Support the selected service provider by acting as a liaison with other UN agencies, development partners and any other relevant stakeholders

| Outputs, Key activities and Procurement |
| --- |
| Outputs | 1.1 Definition of Management Company ToR by UN and development partners and agreement to these by the Secretariat Director and Compact Steering Committee 1.2 Successfully implemented Management Company procurement process in line with UN procurement procedures 1.3 Engagement of selected company, according to UN and UNOPS procedures, by UNOPS to provide the required consultancy services as defined in the approved ToR 1.4 Support to the Administrative and Technical Support Unit from one full time management consultant and activities as defined in the ToR for the Secretariat 1.5 Recruitment of Management Consultants (pool of experts) with the specific skill sets as defined in ToRs to be responsible for “shadowing” the Programme Officers seconded from the GoI (Deputy Minister/ DG) sit in PPU 1.6 Necessary skills have been put in place to ensure Iraqi management of the Secretariat in line with the pre-defined transition arrangements through the work of the Management Consultants together with the GoI Secretariat Organisation 2.1 Assigned UNOPS project manager to act as liaison with other stakeholders and facilitate coordination between this project and complementary projects managed by other agencies. |
| Activities | 1.1.1 UNOPS, together with other relevant stakeholders defines ToRs for the external management company 1.1.2 Submission of ToRs to GoI, Secretariat Director for approval 1.1.3 Approval of ToRs by GoI Secretariat General Publish Expression of Interest (EoI) on UN/ UNOPS website Alert companies with proven and current Iraq experience and relevant expertise to EoI Transmission of Request for Proposal to potential contracting companies based on positive responses to EoI Evaluation of received proposals by UNOPS with the participation of the ICI Secretariat and UNAMI Selection of management consultancy based on evaluation Engagement by UNOPS of selected management consultancy company to provide the services as specified in the ToRs, and as proposed in the company submission The engaged management consultancy company will identify one consultant to work with the Administrative and Technical Assistance Unit to establish Secretariat activities, as defined in the Compact Secretariat ToR (annexe A ) The management consultancy company will engage a pool of consultants to “shadow” the Programme Officers seconded from the relevant GoI ministries to the PPU on a part time basis. This activity will be undertaken in consultation with other stakeholders (UNDP/ WB) who have also contracted to provide expert advisors to the PPU The selected consultants will mentor the GoI officials inside the project duration to ensure that activities undertaken are in line with the overall Compact Secretariat objectives and principles. The consultants in both Administrative and Technical Support and in PPU will work with the GoI staff to ensure that transition to an Iraqi-led reconstruction model is on track and proceeding to schedule Assignment of part-time Project manager to follow and monitor the implementation of the project and initiate corrective action when required Establish links with other stakeholders (UN, development partners ) Follow-up on specific project activities and outcomes to ensure quality of service and timely delivery. |
| Procurement (major items) | None |

| Funds Committed | 2,628,102.54 USD | % of approved | 77% |
| --- | --- | --- | --- |
| Funds Disbursed | 917,551.46 USD | % of approved | 27% |
| Forecast final date | 31st December 2009 | Delay (months) |  |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 1 | n/a |
| Women |  |  |
| Children |  |  |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries | Population of Iraq |  |
| Employment generation (men/women) |  |  |
| Quantitative achievements against objectives and results |
| Output 1 Provide policy, program, technical and administrative support for the implementation of the International Compact with Iraq (ICI) by the identification and contracting of an external management company. |  |  |
| 1.1 Definition of Management Company ToR by UN and development partners and agreement to these by the Secretariat Director and Compact Steering Committee | 100 | % of planned |
| 1.2 Successfully implemented Management Company procurement process in line with UN procurement procedures | 100 | % of planned |
| 1.3 Engagement of selected company, according to UN and UNOPS procedures, by UNOPS to provide the required consultancy services as defined in the approved ToR | 80 | % of planned |
| 1.4 Support to the Administrative and Technical Support Unit from one full time management consultant and activities as defined in the ToR for the Secretariat | 80 | % of planned |
| 1.5 Recruitment of Management Consultants (pool of experts) with the specific skill sets as defined in ToRs to be responsible for “shadowing” the Programme Officers seconded from the GoI (Deputy Minister/ DG) sit in PPU | 30 | % of planned |
| 1.6 Necessary skills have been put in place to ensure Iraqi management of the Secretariat in line with the pre-defined transition arrangements through the work of the Management Consultants together with the GoI Secretariat Organisation | 80 | % of planned |
| Output 2 Support the selected service provider by acting as a liaison with other UN agencies, development partners and any other relevant stakeholders |  |  |
| 2.1 Assigned UNOPS project manager to act as liaison with other stakeholders and facilitate coordination between this project and complementary projects managed by other agencies. | 85 | % of planned |

Qualitative achievements against objectives and results during this reporting period

Output 1 UNOPS discussed the implications of the restructuring on this project also with various other stakeholders, including the Advisor to the DSRSG, the Director of the ICI Secretariat, the ICI Secretariat Advisor under this project, and UNAMI HRD. The agreed way forward is to propose a revision of Output 1.5 (now referred to as Output 1.5a), so that the project would provide expertise to specific Prime Minister’s Advisory Council (PMAC) Advisors, identified through a consultative process lead by the Director of the ICI Secretariat, and also be engaged in the re-drafting of the Compact document (including the revision of the benchmarks). The contract with the Management Consultancy was revised according to the recommendations of the stakeholder consultations and extended until December 31st 2009. Output 2 Advertisement, interviews and a recommendation for the selection of a new part time project manager was made.

Main implementation constraints & challenges (2-3 sentences)

The project objectives were not fully achieved because the ICI Secretariat structure initially envisaged in the Secretariat TORs has not been fully realized by the GoI counterparts. Subsequently, the Compact Secretariat has now been restructured with the Policy Planning Unit relocating to the Prime Minister’s Advisory Council (PMAC) and the Administrative and Technical Unit remaining with the Deputy Prime Minister. On 03 December 2008, UNOPS received an e-mail (attached) from David Shearer (the UNAMI DSRSG and Chair of the UNDG/ITF SC), requesting, in coordination with Thamir Ghadban (Head of the PMAC), that UNOPS extend the project until the end of 2009 and adjust the project’s objective to provide expertise (output 1.5) to be in line with the changed structure. While the consultative process described above has only been completed in the first week of February, specific requirements have already been identified and are assessed to be of high priority and in need for urgent implementation. These were still awaited upon as of 31st March 2009 but expected imminently.