- United Nations Development Group Iraq Trust Fund

- Project #:C9-22

- Date and Quarter Updated: 4th Quarter October – December 2008

| Participating UN Organisation: UNOPS | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Office of the Deputy Prime Minister |  |

| Title | Assistance for the Establishment of the Secretariat for the International Compact with Iraq (Compact Secretariat) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Iraq |  |  |  |  |
| Project Cost | USD 3,414,826- Funds received |  |  |  |  |
| Duration | 12 months |  |  |  |  |
| Approval Date (SC) | 4.10.07 | Starting Date | 10.10.2007 | Completion Date | Originally 09.10.2008 – extended to 10.04.2009 |
| Project Description | The project aims to provide assistance in establishing the Secretariat for the International Compact with Iraq (ICI). The Secretariat will be the Government of Iraq’s mechanism in charge of coordinating, monitoring and reporting on the implementation of the Compact. Support will be provided through the engagement of an external management consultancy to support the implementation of the ICI |  |  |  |  |

- Development Goal and Immediate Objectives

Effective, accountable and sustainable Iraqi mechanism for policy planning, program design, monitoring and evaluation to support the implementation of the ICI.

- Outputs, Key activities and Procurement

| Outputs | 1.1 Definition of Management Company ToR by UN and development partners and agreement to these by the Secretariat Director and Compact Steering Committee 1.2 Successfully implemented Management Company procurement process in line with UN procurement procedures 1.3 Engagement of selected company, according to UN and UNOPS procedures, by UNOPS to provide the required consultancy services as defined in the approved ToR 1.4 Support to the Administrative and Technical Support Unit from one full time management consultant and activities as defined in the ToR for the Secretariat 1.5 Recruitment of Management Consultants (pool of experts) with the specific skill sets as defined in ToRs to be responsible for “shadowing” the Programme Officers seconded from the GoI (Deputy Minister/ DG) sit in PPU 1.6 Necessary skills have been put in place to ensure Iraqi management of the Secretariat in line with the pre-defined transition arrangements through the work of the Management Consultants together with the GoI Secretariat Organisation 2.1 Assigned UNOPS project manager to act as liaison with other stakeholders and facilitate coordination between this project and complementary projects managed by other agencies. |
| --- | --- |
| Activities | 1.1.1 UNOPS, together with other relevant stakeholders defines ToRs for the external management company 1.1.2 Submission of ToRs to GoI, Secretariat Director for approval 1.1.3 Approval of ToRs by GoI Secretariat General - Publish Expression of Interest (EoI) on UN/ UNOPS website - Alert companies with proven and current Iraq experience and relevant expertise to EoI - Transmission of Request for Proposal to potential contracting companies based on positive responses to EoI - Evaluation of received proposals by UNOPS with the participation of the ICI Secretariat and UNAMI - Selection of management consultancy based on evaluation - Engagement by UNOPS of selected management consultancy company to provide the services as specified in the ToRs, and as proposed in the company submission - The engaged management consultancy company will identify one consultant to work with the Administrative and Technical Assistance Unit to establish Secretariat activities, as defined in the Compact Secretariat ToR (annexe A ) - The management consultancy company will engage a pool of consultants to “shadow” the Programme Officers seconded from the relevant GoI ministries to the PPU on a part time basis. This activity will be undertaken in consultation with other stakeholders (UNDP/ WB) who have also contracted to provide expert advisors to the PPU - The selected consultants will mentor the GoI officials inside the project duration to ensure that activities undertaken are in line with the overall Compact Secretariat objectives and principles. - The consultants in both Administrative and Technical Support and in PPU will work with the GoI staff to ensure that transition to an Iraqi-led reconstruction model is on track and proceeding to schedule - Assignment of part-time Project manager to follow and monitor the implementation of the project and initiate corrective action when required - Establish links with other stakeholders (UN, development partners ) - Follow-up on specific project activities and outcomes to ensure quality of service and timely delivery. |
| Procurement (major items) | The project hinges on the identification, selection and contracting of a management consultancy to support the Compact Secretariat team. This will be one contract with a maximum total value USD 1.9M UNOPS in the preparatory phase prepared and published an EoI to source potential service suppliers and sent out an RFP to nine companies The contractual agreement between UNOPS and the selected company has a duration of one year |

| Funds Committed | USD 764,340.24 | % of approved | 22% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 724,945.39 | % of approved | 21% |
| Forecast final date | 10.04.2009 | Delay (months) |  |

- Quantitative achievements against objectives and results

| Engagement of management Consultancy (1.1- 1.4) | Procurement process completed Contractual agreement agreed Full time consultant engaged | % of planned | 100% |
| --- | --- | --- | --- |
| Engagement of technical experts in line with requests from the Compact Secretariat (1.5, 1.6) | Terms of reference developed Candidates identified No technical experts engaged pending decisions from the Secretariat | % of planned | 30% |
| Establishment of UNOPS project office (2.1) | Project manager selected Lines of communication with international development partners established Mid –term quality assurance process with UNAMI scheduled | % of planned | 80% |

- Qualitative achievements against objectives and results

The project objectives were not fully achieved because the ICI Secretariat structure initially envisaged in the Secretariat TORs has not been fully realized by the GoI counterparts. This issue was discussed between the various stakeholders, incl. the Prime Minister’s Office, UNAMI, World Bank, and other international partners, and a Management Review was conducted by the Secretariat in summer 2008. The report with the findings was then analyzed and was further complemented by a UNAMI Assessment of the support provided by the ICI Secretariat (all relevant documents were attached to the Oct 2008 revision). Subsequently, the Compact Secretariat has now been restructured with the Policy Planning Unit relocating to the Prime Minister’s Advisory Council (PMAC) and the Administrative and Technical Unit remaining with the Deputy Prime Minister.

On 03 December 2008, UNOPS received an e-mail (attached) from David Shearer (the UNAMI DSRSG and Chair of the UNDG/ITF SC), requesting, in coordination with Thamir Ghadban (Head of the PMAC), that UNOPS extend the project until the end of 2009 and adjust the project’s objective to provide expertise (output 1.5) to be in line with the changed structure. Throughout January 2009, UNOPS discussed the implications of the restructuring on this project also with various other stakeholders, including the Advisor to the DSRSG, the Director of the ICI Secretariat, the ICI Secretariat Advisor under this project, and UNAMI HRD. The agreed way forward is to propose a revision of Output 1.5 (now referred to as Output 1.5a), so that the project would provide expertise to specific PMAC Advisors, identified through a consultative process lead by the Director of the ICI Secretariat, and also be engaged in the re-drafting of the Compact document (including the revision of the benchmarks). While the consultative process described above has only been completed in the first week of February, specific requirements have already been identified and are assessed to be of high priority and in need for urgent implementation.