# United Nations Development Group Iraq Trust Fund

# Project #:C9-23

# Date and Quarter Updated: March 2009

| Participating UN Organisation: UNFPA | Sector: Governance Sector |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Planning and Development Cooperation “MoPDC”/ Central Organization for Statistics and Information Technology “COSIT” |

| Title | Capacity Development in Census and Large- Scale Surveys |
| --- | --- |
| Geographic Location | Nationwide |
| Project Cost | Project Budget in US $: 7,841,127 UNDG ITF : 5,064,268 Govt. Contribution : 1,500,000 Agency Core UNFPA: 1,276,859 |
| Duration | 30 Months |
| Approval Date (SC) | 4 December 2008 | Starting Date | 1 November 2008 | Completion Date | 31 March 2011 |
| Project Description | The project aims at increasing national capacity to collect, analyze and use population data for policy formulation and planning with specific focus on data originated from census and large-scale population surveys. |

Development Goal and Immediate Objectives

Development Goal: The project facilitates availability of information and data to help in addressing 7 out of 8 goals of MDGs and Iraq NDS, through establishing a statistic system of continuous capturing process to follow up on policy implementation, draw attention to deviations that might happen and adjust procedures. Immediate Objectives: Increase capacity of the national statistical body, COSIT, to plan, implement, analyze and disseminate census and large-scale surveys. Strengthen the capacity of national partners, to monitor, advocate and communicate with general public on the importance of census and its results, as well as to use the population information for evidence-based advocacy and policy making.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Capacities of COSIT at national and governorate levels and collaborating national partners, are increased to plan and implement high quality and internationally recognised population and housing censuses and other large- scale surveys. Capacities of COSIT and national research centres, at national and governorate levels, are enhanced to conduct disaggregated analysis and evaluation of census and large- scale surveys data. Capacities of MoPDC and key line ministries (MoH, MoE, MoLSA, MoA, …..) at national and governorate levels are enhanced to disseminate and utilize disaggregated censuses and large-scale surveys data. COSIT’s Systems for ensuring census compliance with established scientific international standards are strengthened, including quality assurance and independent observation, monitoring and evaluation. |
| Activities | TOT workshops for COSIT and other related national partners in the areas of (Mass Media/ Census Advocacy and Public Sensitisation, Planning / Conducting Census Field work preparations, GIS & Cartography “Maps Using in Census field works”, GIS Systems “Update design of GIS to align with census needs and dissemination plans”, census desk and auto editing, data capture software applications, electronic design of census questionnaires, Census questionnaires template design, designing and creation of population, building and listing databases and using the scanner device in data capture system). Technical workshops for COSIT staff, higher census committee and other national institutions to review, finalize, develop, plan, monitor technical, managerial, capacity development plans and preparations for the project, in addition to census tools and the questionnaires. |
| Procurement (major items) | UNFPA facilitated the ICR Software procurement for 2009 Iraqi census. UNFPA Facilitated the procurement of Scanner device for 2009 Iraqi census. TOT specialized training courses to COSIT personnel according to Cooperation Protocol between COSIT and CAPMAS “Central Agency for Public Mobilization and Statistics”. UNFPA Procured Service providing Company through signing a service contract with American Express “AmEx” to provide and facilitate the logistics and accommodation of the COSIT trainees in Cairo, Egypt. |

| Funds Committed | Total Pos | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | Total AP vouchers | % of approved | 100% |
| Forecast final date | 31 March 2009 | Delay (months) | 0 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Others: COSIT Staff | 127 trainees | 20% |

| Quantitative achievements against objectives and results |
| --- |
| Increase capacity of the national statistical body, COSIT, to plan, implement, analyze and disseminate census and large-scale surveys. | TOT workshops for COSIT and other related national partners in the areas of (Mass Media/ Census Advocacy and Public Sensitisation, Planning / Conducting Census Field work preparations, GIS & Cartography “Maps Using in Census field works”, GIS Systems “Update design of GIS to align with census needs and dissemination plans”, census desk and auto editing, data capture software applications, electronic design of census questionnaires, Census questionnaires template design, designing and creation of population, building and listing databases and using the scanner device in data capture system). | % of planned 20% |  |
| Strengthen the capacity of national partners, to monitor, advocate and communicate with general public on the importance of census and its results, as well as to use the population information for evidence-based advocacy and policy making (quality assurance). | Technical workshops for COSIT staff, higher census committee and other national institutions to review, finalize, develop, plan, monitor technical, managerial, capacity development plans and preparations for the project, in addition to census tools and the questionnaires. | % of planned 38% |  |

Qualitative achievements against objectives and results

The implemented activities regarding capacity development for COSIT personnel enhanced and empowered COSIT Cadre with the required skills, knowledge and modern techniques in the field of census and large scale surveys to implement and manage such projects, now and in the future. The sustainability of the capacity development project is secured by adopting and applying quality assurance approach in the project phases by transferring acquired skills, knowledge and modern techniques.

Main implementation constrains & challenges (2-3 sentences)

The unstable security situation is the most constraint/challenge that could face the implementation of the project; therefore, we take into consideration such a challenge through establishing a risk management strategy.