CENTRAL FUND FOR INFLUENZA ACTION

2009 programme1 NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN or Non-UN Organization(s): International Civil Aviation Organization (ICAO) |  | UNCAPAHI Objective(s) covered: Contingency Planning for operational continuity during a pandemic |
| --- | --- | --- |

| Programme No.: CFIA/A-11 Programme Title: Cooperative Arrangement for the Prevention of Spread of Communicable Disease by Air Transport ATLAS No: (will be assigned by MDTF Office) |  | Report Number: 3 |
| --- | --- | --- |

| Reporting Period: |  | Programme Budget: |
| --- | --- | --- |
| 1 January – 31 December 2009 |  | CFIA: US$ 549,960 Other: US$ in kind |

| List Implementing Partners: |  | Programme Coverage/Scope: |
| --- | --- | --- |
| Participating UN or Non-UN Organization: WHO, OCHA Other International Organizations: IATA, ACI National (government, private, NGOs & others): Civil Aviation Authorities, Public Health Autorities and Airport Authorities of Participating Governments |  | Specify in which region and/or national coverage/scope of the programme: Africa |

| Abbreviations and acronyms: |  | Programme/Project Timeline/Duration |
| --- | --- | --- |
| List the main abbreviations and acronyms that are used in the report. CAPSCA: Cooperative Arrangement for the Prevention of Spread of Communicable Disease by Air Transport IATA: International Air Transport Association ACI: Airports Council International FAA: Federal Aviation Agency (USA). DGCA: Director General of Civil Aviation CAA: Civil Aviation Authority |  | Overall Duration: Overall start and end date of the programme/ project: March 2008 – December 2011 (envisaged) Original Duration: 12 months Original start and end date of the programme/ project March 2008 – March 2009 Programme/ Project Extensions Currently extended to March 2011 |

Narrative Report Format

1.  	Purpose

1.1 	The main outcomes and outputs of the programme are:

a.	The aviation sector will be capable of taking appropriate measures for preventing the spread of communicable diseases of international public health concern through air transport, in case an outbreak is declared.

b.	Airports and airlines in participating states and administrations will have developed the necessary aviation preparedness plans in compliance with WHO and ICAO guidelines on prevention of spread of communicable disease by air transport which will be considered in development of national general preparedness plans.

c.	The preparedness plans and arrangements in place at major airports for dealing with a pandemic will have been reviewed and their effectiveness assessed by project experts.

d.	Guidance and on the job training will have been provided to civil aviation, airports and airline personnel as well as to health officials involved, on the implementation of the aviation preparedness plan in case of a pandemic. A team of experts is thus established to provide ongoing advice on the subject and supply their expertise for the development of similar preparedness plans at other airports.

e.	Harmonization of plans and procedures and greater cooperation and coordination with global efforts, as well as with health and government authorities concerned in the prevention of the spread of communicable diseases.

  - The programme falls under objective 6 (continuity under pandemic conditions) of 	the 	UN Consolidated Action Plan and more specifically (paragraph 6.1 	“Contingency planning for continuity of operations during a pandemic including 	preparation for humanitarian actions under pandemic conditions (WHO alert 	phases 5 and 6).”

The programme is in line with the CFIA TOR and has received a grant 	of $399,960 plus $150,000 which was transferred from CAPSCA-Asia Pacific (CFIA-A5), a total of $549,960.

1.3	The main implementing UN and non-UN partners in this programme and their 	respective roles and responsibilities are:

- International Civil Aviation Organization (ICAO) which is the lead coordinator of preparedness planning effort in the aviation sector. It arranges seminars, workshops, Steering Committee and Regional Aviation Medicine Team meetings, conducts evaluation of airport preparedness plans and facilities and promotes cross organizational communication and collaboration.

- World Health Organization (WHO) which assists in the development of pandemic preparedness guidelines for aviation and ensures harmonization with International Health Regulations as well as participates in regional training workshops for the aviation sector and in airport evaluations.

- Airports Council International (ACI) which facilitates the development and implementation of detailed pandemic preparedness guidelines for airport operators and participates in related regional training workshops.

- International Air Transport Association (IATA) which facilitates the development and implementation of detailed pandemic preparedness guidelines for airlines and participates in related regional training workshops.

2.	Resources

  - Financial Resources:

$150,000 was initially transferred from CAPSCA-Asia Pacific (CFIA-A5) to CAPSCA Africa (CFIA – A11) and CFIA subsequently allocated $399,960 for the project.  Thus the total financial resources allocated to CAPSCA-Africa (CFIA-A11) is $549,960.  The project also relies on in kind contributions from States, expertise that is provided to the project without salary costs.

  - Human Resources:

- Dr. Anthony Evans, Chief of the Aviation Medicine Section in ICAO Headquarters is designated as the Project Manager and is supported in this regard by the ICAO Technical Cooperation Bureau. In addition WHO, IATA, ACI and other personnel from governmental organizations have participated in the meetings and workshops of the Programme.

- Three CAPSCA-Africa regional coordinators have been appointed, one from each of three participating States.

- The team leader/medical expert from the CAPSCA Asia Pacific project has been seconded by his government to work with the CAPSCA project and assists with the development of CAPSCA in all regions.

3.	Implementation and Monitoring Arrangements

3.1	The implementation mechanisms primarily utilized to achieve maximum impact 	include:

a.	Organizing and conducting with the participation of WHO, IATA, ACI and other parties concerned, seminars and workshops on aviation preparedness planning for civil aviation, airports, airlines and health personnel of participating countries.

b.	Providing technical guidance and explanations to the authorities concerned on the application of related ICAO Standards and Recommended Practices and guidelines and on International Health Regulations.

c.	Undertaking missions to states and administrations to develop, assess and evaluate the preparedness plans at major airports and airlines for prevention of the spread of communicable diseases through air transport.

d.	Promoting harmonization, coordination and cooperation among all stakeholders within each country and among the participating States and Administrations.

  - No procurements are involved.

  - Monitoring of the Programme is done by the following:

- The Project Manager at ICAO Headquarters, two focal points, one at each of the ICAO Regional Offices in Africa (Dakar and Nairobi) and three regional coordinators, who are seconded to this role by their State.

- The Steering Committee is composed of representatives of civil aviation, airports, airlines and health authorities in Participating States and administrations and other interested parties meets about once a year and discusses any difficulties encountered, lessons learned and further actions to be undertaken.  The first Steering Committee Meeting was held in Abuja in February 2009 and the second is planned for Nairobi during June 2010.

- The Regional Aviation Medicine Team (RAMT) which was established by the first Steering Committee Meeting has so far held one meeting, in October 2009 under the auspices of the South Africa Civil Aviation Authority.  The RAMT reviews ICAO, State and Airport Specific Guidelines and checklists from the operational point of view and proposes for adoption by the Steering Committee appropriate measures and procedures that may need to be applied by airports and airlines in their preparedness plan.

  - Four international airports been evaluated in Africa.  These are Lagos, Abuja (Nigeria), Johannesburg and Cape Town (South Africa). Further evaluation visits are planned.  A live exercise simulating the arrival of a passenger with a serious communicable disease was undertaken in Johannesburg in October 2009.

4.	Results

4.1	The programme has created awareness not only in its Participating States and Administrations but also in other States in the Region as well as in their major airports and airlines, about the need to develop a contingency aviation preparedness plan for implementation in case of an outbreak or pandemic. The workshops conducted, the Steering Committee and RAMT meetings as well as the evaluation missions, have created greater understanding of the relevant ICAO requirements and WHO International Health Regulations (2005) that can contribute to the prevention of the spread of communicable diseases by air transport and the measures that need to be taken.

  - Five States and Administrative Regions have joined the Project. These are: Nigeria, South Africa, Democratic Republic of Congo, Chad and Cape Verde. Furthermore the four additional States have expressed their interest in joining the project and have participated in most of the meetings organized within the framework of the project: Cameroon, Cote d’Ivoire, Ghana, Kenya.

  - Four International Airports have been evaluated. The airport evaluation visits ensured that aviation preparedness plans in the case of a pandemic outbreak, are in compliance with ICAO requirements and guidelines as well as with WHO International Health Regulations (2005). In addition on the job training was provided to national personnel in the development and implementation of pandemic preparedness plans at airports in their country.

  - The RAMT brings together experts, operational and medical personnel from several countries in the Region and from multinational agencies.  It provides the Steering Committee and the participating States and their airports and airlines a professional source of advice and guidance on arrangements and procedures applied under the preparedness plans in the region.

  - Other states, regional and international agencies and organizations, major airlines and airports as well as Public Health Departments have also participated in the workshops, Steering Committee and RAMT meetings or in visits to States. The involvement of these different entities and the evaluation visits to States and airports have had a catalytic effect in bringing together interested parties from many countries and regions of the world as well as the aviation and public health sectors within the participating states that has created awareness and promoted the production of harmonious preparedness plans that are in compliance with ICAO requirements and with WHO International Health Regulations (2005).

5.	Future Work Plan

The future workplan includes the following:

•	Increasing the number of States participating in the project.

•	Reviewing and evaluating Pandemic Preparedness Plans at major international airports of participating States that are not yet evaluated.

•	Providing professional guidance and advice to States on the effectiveness of arrangements and procedures adopted in the preparedness plans.

•	Ensuring that national experts on the development and application of Pandemic Preparedness Plans are kept informed of relevant new developments and regulations.

- Conducting further workshops / Steering Committee and RAMT meetings

•	Enhancing cooperation and coordination among all parties and states involved and harmonization of their Preparedness Plans.

•	No additional funds are anticipated to be needed for the present.