CENTRAL FUND FOR INFLUENZA ACTION

programme NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN or Non-UN Organization(s): UNWTO |  | UNCAPAHI Objective(s) covered: 5. Public Information and Communication to support behavior change 6. Continuity under pandemic conditions |
| --- | --- | --- |
| U |  |  |

| Programme No. A-4 Programme Title: Targeted communications for travellers, the travel industry, and tourist destinations |  | Report Number: Three |
| --- | --- | --- |
| ATLAS No: 55344 |  |  |

| Reporting Period: 1 January to 31 December 2009 |  | Programme Budget: |
| --- | --- | --- |
|  |  | CFIA: US$ 400,000.00 Other: US$ n/a |

| List Implementing Partners: |  | Programme Coverage/Scope: |
| --- | --- | --- |
| WHO, UNICEF; FAO, OIE, OCHA |  | Global |

| Abbreviations and acronyms: |  | Programme/Project Timeline/Duration |
| --- | --- | --- |
| AHI: Avian and Human Influenza TERN: Tourism Emergency Response Network IHR: International Health Regulations |  | Overall Duration August 2007 – April 2010 Original Duration August 2007 – July 2008 Programme/ Project Extensions First extension: June 2009 Second extension: April 2010 |

# NARRATIVE REPORT FORMAT

# Purpose

- The role of communications is vital to prepare, reduce and mitigate the impact of an AHI pandemic, especially for the tourism sector. UNWTO has been working towards this goal with limited resources. Developing and implementing a targeted tourism specific communications strategy, focussing on the existing platform www.SOS.travel allowing wide and timely information to be disseminated to this specific audience as well as a targeted communications campaign that will ensue to alert travellers worldwide plays a vital role in the minimizing the impacts of an AHI outbreak. SOS.travel is an online one-stop-shop where users can access the latest critical information and communication tools in anticipation of, or in response to, natural and man-made crises with potential impacts on tourism. The system aims to support crisis preparedness in the tourism sector and assist in rapid recovery from crisis situations. SOS.travel also serves as a valuable resource for travellers by providing in one place the tools and information they need in order to make informed decisions about their own safety and security, and to obtain assistance in case of an emergency.  It also serves as a hub of secure communication, facilitating the timely exchange of critical information between and among Tourism Emergency Response Network (TERN) members and participating International Organizations. Through the deployment of identification safeguards, the system enables executives in different organizations facing similar challenges to better coordinate their efforts and rapidly exchange information with the confidence that the information will only be read by the intended recipients.

- The UN Consolidated Action Plan clearly defined the need for strategic communication for awareness, social mobilization and behaviour change under objective 5 and continuity under pandemic conditions under objective 6 of the plan to which UNWTO’s proposal has conformed and was subsequently approved.

- Implementing agencies of objective 5 are WHO, UNICEF, FAO and OIE, while the lead agency of objective 6 is OCHA.

- Resources

Financial Resources:

- While the programme builds on the systems put into place thanks to the initial support of Microsoft in 2006, the full scope of the programmes activities and outputs, as outlined in the project proposal, are to be covered by the funds (US$ 400,000) received from  CFIA.

Human Resources:

- UNWTO recruited 2 communication staff members to headquarters to assist in the development and execution of the campaign.  Staff joined UNWTO in February 2008. For the remainder of programme extension period, initially through June 2009 and subsequently through April 2010, a new communication staff was hired to fill-in the position of a staff member who went on maternity leave.

- UNWTO recruited one senior communications consultant to assist in and contribute to the development of the strategy within the framework of UNWTO’s and UNSIC’s strategic objectives

- Support Staff financed and provided by UNWTO

- Implementation and Monitoring Arrangements

- During the first part of 2009, UNWTO actively provided regular targeted communications with core travel and tourism associations and its Tourism Emergency Response Network related to the situation of AHI.  With the outbreak of Influenza A(H1N1), all activities relating to the promotion of SOS.travel were, whenever contractually possible, stopped as the awareness of the platform was raised automatically to high levels. All efforts were immediately geared towards the tremendously increased targeted communications work taking place through the platform with end users, Member States and the TERN network.

- While regular internal and interagency network communications remain active, in response to the outbreak of Influenza A(H1N1), UNWTO coordinated regular teleconference meetings among TERN, the International Civil Aviation Organization (ICAO) and the World Health Organization (WHO), which is the leading UN-agency in response to the pandemic. These meetings provided a platform for targeted two-way communication between the Travel and Tourism Industry and WHO and thus allowed to receive the insight into the needs, views and concerns of the industry.

- The usual UNWTO standards for procurement and monitoring are applied to this project. Regular internal communication with all other departments, regional representations, affiliate Members and Senior Management ensure that all relevant project information is shared

- Results

  - Objective 5 (Public Information and Communication to Support Behaviour Change)

- Promotional materials were developed to promote the SOS.travel portal among the industry and the general public. These included posters with slogans relaying the main objectives of the website: dealing with pandemic threats, making better decisions and fostering sustainable tourism development (Annex I) ; Illustrative leaflets on SOS.travel, TERN alerting system and whatabout.travel web publishing tools (Annex II); and six promotional videos, of which two are currently in their final stage of development (http://sos.travel/resource.aspx?description=video). The videos were targeted towards both the industry and the end-users. They focus on the SOS.travel website in addition to promoting responsible tourism under the current pandemic situation. These videos are now being disseminated through social media outlets and in cooperation with other partners.

- Two consultation meetings on communications under pandemic circumstances with key stakeholders took place in January 2009 (Madrid, Spain) and February (Berlin, Germany) to expand the outreach of the campaign, to frame and disseminate the templates properly and to better prepare the industry facing pandemic crisis. The communication campaign consists of emotional components to address specific needs of end-users as well as cognitive information to meet special requirements of the top industry multipliers including TERN members. Several rounds of background interviews with trade and media were conducted to promote SOS.travel platform and frame the activities properly.

- In response to the Influenza A(H1N1) outbreak, TERN is constantly used as an effective multiplier of core messages that provided a two-way communication platform between the Travel and Tourism Industry and WHO. The group’s monthly, bimonthly and sometimes weekly teleconferencing provide an insight into the needs, views and concerns of the industry and help in building partnership and coordination among the different stakeholders in the sector.

- UNWTO actively provided regular targeted communications with the Influenza Focal Points in its Member States and with core travel and tourism associations and its Tourism Emergency Response Network (TERN). These communications, through regular situation updates, guidelines and best practices, encouraged responsible travel behaviour, ensured consistency and reduced uncertainty in information sharing by providing a balance of information to avoid complacency and overreaction.

- The regular coordination and communication effort in which UNWTO was involved at the Member State level helped in formulating core and consistent messages stressing the importance of staying vigilant while avoiding overreactions or adopting unnecessary measures in terms of travel and trade restrictions between the industry, the different stakeholders and the general public.

- Since the declaration of the influenza A(H1N1), membership of the TERN network has been constantly reviewed and expanded.

Objective 6 (Continuity under Pandemic Conditions)

- Our work helped to identify problems and the needs of the sector in a timely manner and contributed in many cases that issues did not develop further that could have had negative impacts on the travel and tourism sector.  This was also possible thanks to the good cooperation with WHO, ICAO, UNSIC and UNDP.

- Regular targeted two-way communication is vital for the continuity of the travel and tourism sector.

- Together with the results of our Review and Preparation Exercises, information and lessons learned were shared in a timely manner to the global travel and tourism sector.

- As mentioned before, UNWTO has fostered key partnership with the WHO, especially the IHR division, as well as with ICAO and TERN which consist of the following travel and tourism associations: Association of Asia Pacific Airlines (AAPA), Airports Council International (ACI), Association of European Airlines (AEA), American Hotel & Lodging Association (AHLA), American Society of Travel Agents (ASTA), Arab Tourism Organization (ATO), African Travel & Tourism Association (ATTA), Asocación Latinoamericana de Transporte Aéreo (ALTA), Caribbean Hotel and Tourism Association (CHTA), International Council of Cruise Lines (CLIA),  Canadian Tourism Commission (CTC), Caribbean Tourism Organization (CTO), European Travel Commission (ETC), Federation Internationale de l'Automobile (FIA), International Association of Amusement Parks and Attractions (IAAPA), International Air Transport Association (IATA), International Federation of Tour Operators (IFTO), International Hotel & Restaurant Association (IH&RA), International Shipping Federation (ISF), Meeting Professionals International (MPI), US National Tour Association (NTA), Pacific Asia Travel Association (PATA), SKAL International, Tour Operators’ Initiative for Sustainable Tourism Development (TOI), United Federation of Travel Agents Associations (UFTAA), United Nations World Tourism Organization (UNWTO), US Travel (UST), World Travel Agents Associations Alliance (WTAAA), World Travel and Tourism Council (WTTC), World Youth Student and Educational Travel Confederation (WYSETC).

- During the interactive training and simulation exercise at UNWTO’s headquarters in May, a group of selected officials from 20 Members States was extensively trained on instruments and strategies related to the SOS.travel platform and TERN. Special focus was given on the outbreak of influenza A(H1N1) and the specific coordination and communication needs arising from it.

- Future Work Plan

  - Objective 5 (Public Information and Communication to Support Behaviour Change)

- UNWTO will continue to collect, share and communicate the most up-to-date information, concerns and views from the network of Influenza Focal Points and TERN, and at the same time use the SOS.travel platform to disseminate timely and accurate information to the wide audience of travellers

- The activities against this funding line will end by April 2010, however, the approved project on Targeted Communications for Travellers, the Travel industry and Tourist Destinations – Phase II will allow to continue this essential two-way communications function for the travel and tourism sector for at least another 12 months as the current pandemic persists and the H5N1 threat continues.

Objective 6 (Continuity under Pandemic Conditions)

- To provide information, guidance and common messaging to ensure consistency to reduce economic, health and social impact on the tourism sector as well as to balance the information needs to avoid complacency and overreaction.

- Good inter-ministerial and cross-sectorial coordination has been proven to be very beneficial since the outbreak of the virus.  Continued two-way targeted communications with the industry, Member States and travellers will remain the highest priority of UNWTO to support the sector to reduce risks and mitigate the impacts of the pandemic.