|  | Pandemic Influenza Coordination (PIC) Emergency Services Branch OCHA Geneva |
| --- | --- |

Central Fund for Influenza Action - CFIA

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2009

| Submitted by: Michael Mosselmans, Director of Pandemic Influenza Coordination (PIC) team UN Office for the Coordination of Humanitarian Affairs (OCHA) Tel: +41 22 910 2778 e-mail: mosselmans@un.org |  | Country and Thematic Area(when applicable) Objective 6: Continuity under pandemic conditions: Southern Africa Region |
| --- | --- | --- |

| Programme No: 00067364 / CFIA – B10 MDTF Office Atlas No: Programme Title: OCHA Pandemic Influenza Contingency work programme for Southern Africa (CFIA B-10) |  | Participating Organization(s): United Nations Office for the Coordination of Humanitarian Affairs (OCHA) – Pandemic Influenza Contingency (PIC) Regional hub for Southern Africa region. |
| --- | --- | --- |

| Implementing Partners: All funds will be managed and spent directly by OCHA; activities will be implemented together with UN and humanitarian country teams and governments in Southern Africa region |  | Programme Budget (from the Fund): US$ 324,456 |
| --- | --- | --- |

Programme Duration (in months): 12 months Start date: 15 January 2009 End date: 31 Dec 2009 Original end date: 31 Dec 2009 Revised end date: 31 Mar 2010 Operational Closure Date: 31 Mar 2010 Budget Revisions/Extensions: OCHA – PIC fully expects to carry out all the CFIA-B10 activities stipulated in the project document for 2009. A no-cost extension was requested and approved.

NARRATIVE REPORT FORMAT

# Purpose

  - Background

The Pandemic Influenza Coordination (PIC) regional hub is located in the Office for the Coordination of Humanitarian Affairs (OCHA) Regional Office for Southern Africa. Its purpose is (a) to help UN country teams to prepare to protect staff health and safety; continue essential operations; and support Southern African national governments during pandemic; (b) working through UN country teams, to help national governments to prepare to mitigate the beyond health (economic, governance, humanitarian and social) impacts of pandemic; (c) to strengthen the readiness of UN humanitarian agencies and their partners in Southern Africa to meet the humanitarian needs of vulnerable populations during pandemic. To achieve these goals, PIC’s Southern Africa hub’s work is a combination of advocacy; measurement of the current level of readiness of national governments and UN country teams; practical help to enable national governments, UN and humanitarian country teams to prepare; and coordination of humanitarian pandemic preparedness actors at national and regional level, to promote synergy, avoid duplication and identify gaps in the region. The PIC regional hub was established in late 2006 and is covering 15 countries.

This project is an extension of OCHA-PIC’s existing programme, previously partially funded by Agreement reference CFIA/B-1. The official start and completion dates of the preceding contract were 1 October 2007 – 30 September 2008.

  - PIC’s outputs and key activities for Southern Africa project:

- UN and humanitarian country teams in Southern Africa are ready to continue operating in pandemic: Conduct table top and functional simulations to improve and test planning with UN and humanitarian country-based teams in Southern Africa.

- Humanitarian community in Southern Africa ready to respond in the event of a pandemic: Conduct simulations for Humanitarian Pandemic Preparedness initiative in priority countries. Encourage existing humanitarian coordination mechanisms to develop plans for their roles in pandemic.

- Regional coordination platform delivers improved regional coordination on pandemic preparedness: Convene and facilitate regional joint planning meetings with pandemic preparedness actors of the region. Develop who does what where information to help identify opportunities for collaboration

- Governments in Southern Africa are better prepared for non health impacts of pandemic: Advocate with governments in Southern Africa to include an influenza pandemic as a threat requiring multi-sector contingency planning. Advocate with national disaster management focal points to include pandemic in national disaster plans.

  - PIC’s key immediate objectives from the UNAHICAP objective 6: Continuity under pandemic conditions

6.1.1 Pandemic influenza preparedness plans built upon existing mechanisms for disaster preparedness, mitigation and response and – as much as possible – fully integrated into existing structures for disasters and crisis management

6.1.2 Stakeholders engaged in the facilitation of coherent strategies for pandemic preparedness and response, including in humanitarian settings, encouraging synergy

6.1.3 Assessment, tracking and monitoring of pandemic preparedness

6.1.4 Support to national pandemic preparedness planning

# Resources

2.1. Financial Resources:

This project is fully funded by CFIA grants without any other external donor contributions. OCHA – PIC fully fully expects to carry out all the CFIA-B10 activities stipulated in the project document for 2009.

During the reporting period, PIC’s regional hub in the Southern Africa region spent 68 % (US $ 221,717) of the total funds allocated by the CFIA of US $ US$ 324,456. A no-cost extension was requested.

During the implementation of this project, there were no major constraints in the mechanics of the financial process. The budget is US$324,456.

| Breakdown of CFIA funds received for B-10 project |
| --- |
| Category | Cost |
| Supplies, Commodities, Equipment and Transport | 0 |
| Personnel (Staff, consultants, travel and training) | 266,527 |
| Training of Counterparts | 0 |
| Contracts | 0 |
| Other Direct Costs | 16,500 |
| Sub-total | 287,129 |
| Indirect Costs | 37,327 |
| TOTAL | 324,456 |

2.2. Human Resources

This project has a total of two staff members: One international staff (Regional Planning Officer, P-4) and one national officer (NOA) based in Johannesburg, South Africa.

# Implementation and Monitoring Arrangements

A field-based Regional Planning Officer supported by a global coordinating team in Geneva conducted the programme implementation through country-level and regional engagement. There were clear measurable deliverables (such as simulations exercise conducted, online global preparedness tracking and guidance platform maintained; joint work planning meetings with pandemic preparedness actors held). PIC has been working on non-health humanitarian pandemic preparedness since 2006, engaging  with UN Country Teams, governments and other humanitarian actors in the Southern Africa region. PIC has implemented some efficiency savings to reduce its overall costs from 2008 to 2009.

The PIC programme addresses gaps in beyond-health and humanitarian pandemic preparedness in the Southern Africa region, as well as coordination amongst key regional actors. PIC maintains an online monitoring system, which consolidates information on the level of preparedness down to country level. Common prioritization amongst partners is agreed through a PIC-chaired regional coordination forum.

Preparedness action now could lead to significant reductions in the substantial economic, social and humanitarian impacts of a severe pandemic.

The programme outputs work towards coherence and synergy amongst humanitarian pandemic preparedness partners at regional level, whilst delivering improved preparedness planning amongst humanitarian country teams - who in turn support national authorities.

The needs of particularly vulnerable or marginalized groups are considered especially in dealings with UN and humanitarian county teams, where simulations and planning processes encourage managers to prioritize essential activities that must be continued during an influenza pandemic – for example support to refugees or malnourished children. OCHA advocates with Government partners the importance of planning for the humanitarian impact of pandemic on vulnerable communities and the importance of engagement with NGO and Red Cross/Red Crescent partners in this regard.

OCHA develops who does what where information, to help identify opportunities for collaboration – and provides a forum for strategic thinking by donor, NGO, Red Cross and UN actors on humanitarian pandemic preparedness priorities.

Engagement is managed through the OCHA Regional Office in Southern Africa, with PIC’s Regional Planning Officer reporting to the OCHA Regional Office Head on a day-to-day basis. PIC seeks, records and analyses feedback and evaluation of all its simulations and table-top exercises so as to identify areas for improvement.  Progress in preparedness is tracked via an online system managed by PIC: www.un-pic.org/web

There is a risk of waning interest in governments, national disaster bodies, international organizations, humanitarian organizations and UN country teams. The project is designed to confront this problem with its advocacy work.

Our approach is to encourage pandemic to be incorporated into existing national disaster plans, processes and structures so as to enhance sustainability. We also seek to articulate effectively the collateral benefits of pandemic preparedness to increase its attractiveness.

There is a risk that some Governments will not see the United Nations as their preferred source of support on pandemic preparedness. By producing quality outputs attuned to governments’ needs, we are developing a reputation for being a reliable source of assistance and advice.

There is a risk that a lack of funding for pandemic activity will constrain the ability of UN country teams to support national efforts. Our separate CFIA small seed fund for UN Resident Coordinators helps to mitigate funding constraints.

# Results

4.1. OUTCOME 1: 	UN and humanitarian country teams in Southern Africa more prepared to maintain essential operations and assist National Governments

A. ACHIEVEMENTS / RESULTS

In 2009, 4 simulations were held in Namibia, Botswana, Seychelles and Malawi. Plans were revised, antiviral medicines stockpiled and Business continuity plans developed.

The Namibia TTX involved some 20 participants from UN Agencies such as UNDSS, UNICEF, FAO, WHO, UNDP and UNRCO, as well as the local Red Cross.

The UNCT technical team attended the table top exercise for the Botswana Government. The Malawi TTX involved representatives of different UN Agencies, the Malawi Ministry of Health and the Malawi Disaster Management Department (in the Ministry of Home Affairs). The two key ministries’ participation was very useful to the UN Technical Group. The two ministries confirmed the support which their Government would require from the UN System in a worst-case scenario. UNCT Malawi agreed to revise the Contingency Plan (CP) as per the gaps identified during the TTX.

PIC provided guidance to UNCTs in the region in the finalization of their Pandemic Preparedness Plans. Constant communication was held with all UNCT Focal points on disseminating various guidelines and the PIC readiness framework to the UNCTs, assessing the UNCTs’ and National Governments’ pandemic readiness, and providing support to UNCTs in updating their pandemic influenza preparedness and response plans.

Due to the threat of the pandemic AH1H1, PIC Southern Africa briefed the Regional Directors Team (RDT) on the importance of supporting the process of preparedness plan revision. Letters were sent to all UN RCs in the region, requesting them to speed up the process of revising and implementing plans, and informing them of the availability of PIC in revising and testing plans through table-top exercises and functional simulations.

Regarding South Africa, PIC has permanent interaction with the UNCT in South Africa. Guidance and technical support have been given to the UNCT Technical Committee. PIC, UNICEF and WHO attend weekly meetings of the National Multisectoral Committee on Pandemic Influenza and give guidance and technical support to the South African Government in developing their response plan.

UNCT Focal Points were requested to update the PIC readiness tracker indicators for both UNCTs and National Governments.

- Training

In 2009, PIC Southern Africa took part in the “WFP Regional Training for Country Office Avian and Pandemic Influenza Focal points”. The training was attended by the UNCT South Africa Technical Committee on Pandemic Preparedness. Members of the Technical Committee provided similar training to their staff members. OCHA ROSA (Regional Office for Southern Africa) had its training in May 2009. Various UNCTs conducted training for their staff and dependents on prevention.

- Business Continuity Plan (BCP)

In 2009, PIC assisted the OCHA Regional Office for Southern Africa (ROSA) and the OCHA Country Office for Zimbabwe. The BCPs were implemented and the necessary materials and equipment purchased.

PIC also coordinated and supported Regional Offices, UNCTs and humanitarian actors to define their roles and responsibilities during pandemic and the development of UNCT Business Continuity Plans.

- Information sharing

PIC Southern Africa also developed and shared national-level fortnightly situation reports on pandemic preparedness with both UNCTs and National Governments.

B. PROGRESS AND PERFORMANCE INDICATORS

- A total of 13 Southern African countries (Angola, Botswana, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Swaziland, Seychelles, South Africa, Zambia and Zimbabwe) adopted the PIC Planning Framework for Pandemic Contingency Planning. (Achievement of 13 countries versus 5 targeted for the year – Target exceeded)

- 14 countries updated the data on their state of readiness on the PIC Tracker. (Target of 12 exceeded)

- 4 simulations were carried out from January to December 2009 in Southern Africa. (80% of targeted 5 simulations). Zambia and Mozambique were in the list of countries to carry out simulations in 2009 but due to various circumstances the planned simulations were postponed to early 2010.

4.2.	OUTCOME 2:	Governments, UN and Partners better prepared to support humanitarian response to a pandemic

A. ACHIEVEMENTS / RESULTS

- National Governments’ improved preparedness

In order to reach and involve disaster managers in Africa, PIC Southern Africa worked closely with UNISDR, OCHA regional offices and the African Union (AU) Commission to integrate Pandemic Preparedness into the Africa Regional Platform for Disaster Risk Reduction (DRR) agenda. PIC participated in the preparatory meeting and the Second Africa Regional Platform for DRR Consultative Meeting and made a presentation during the event from 3-4 May in Nairobi. PIC was able to meet the main actors, carried out advocacy and forged partnerships with disaster managers. For Southern Africa, 13 National governments revised their H5N1 preparedness plan by adapting them to the pandemic AH1H1. Others opted to develop a new AH1N1 preparedness and response plan. PIC and WHO Country Offices as the natural focal points within the UN System at national level gave technical assistance.

Partnership with IFRC: The partnership between PIC Southern Africa and the IFRC included information sharing and participation in events/workshops organized by the IFRC. PIC attended the Humanitarian Pandemic Preparedness workshop for National Red Cross/Crescent Societies and national disaster managers in the region held in Pretoria South Africa, in July 2009. PIC also supported the participation of disaster managers in the workshop. It was agreed with IFRC that they should coordinate the INGOs involved in pandemic preparedness.

PIC also had interaction in information sharing with OXFAM Great Britain, World Vision and Care on their own organizations’ pandemic preparedness. As a follow up, INGOs developed their own BCPs at national level and identified the support they could provide to National Governments.

In 2009, Regional UN Agencies and International NGOs (INGOs) had various meetings to discuss the regional contingency plans and information sharing on the status of readiness of each organization. PIC also attended Regional Inter-Agency Standing Committee (RIASCO) Meetings to give regular updates on progress made in the region, offer assistance, and make a presentation on “The UNIP and The Way Forward for Southern Africa” to regional humanitarian partners based in South Africa.

The UN Regional Office Task Force was reactivated to assess the status of UN Agencies’ preparedness, updated the list of critical functions, and discussed pandemic preparedness support to be given to countries.

In November 2009, PIC gave a presentation on the “Whole-of-society Approach” during a WFP workshop held in Zambia on pandemic preparedness for middle managers from various key sectors in the Zambia Central Government and from the Zambia National Red Cross Society. On that occasion, PIC met the National Coordinator and staff of the Zambia Disaster Management and Mitigation Unit to discuss pandemic preparedness and the “Whole-of-Society Approach”. One of the recommendations from the simulation training was the nomination of focal points in each key sector to coordinate sectoral business continuity planning.

B. PROGRESS AND PERFORMANCE INDICATORS

- Advocacy efforts were made at two meetings for regional organizations (RIACSO) and two regional organizations put pandemic preparedness on their agenda. (2009 target of 2 regional meetings and two regional organizations met).

4.3.	4.3. OUTCOME 3: Governments in restricted-capacity countries in Southern Africa improve their beyond-health preparedness for a sudden pandemic

A. ACHIEVEMENTS / RESULTS

After the human influenza outbreak in Mexico, PIC Southern Africa urged UNCTs and National Governments to rapidly revise their preparedness and response plans. PIC Southern Africa developed a matrix for assessing country pandemic readiness to enable the revision of existing pandemic preparedness plans both at UNCT and National Government level, provided the necessary technical support to the plan revision process, including BCP development, through WHO country offices and UN Resident Coordinators’ Offices in Angola, Botswana, Comoros, Lesotho, Malawi, Madagascar, Mozambique, Mauritius, Namibia, the Seychelles, South Africa, Swaziland, Zambia and Zimbabwe. Documents related to pandemic influenza preparedness were disseminated to UNCTs and National Governments. PIC supported National Governments through UN Technical Focal Points by disseminating guidelines for pandemic influenza preparedness planning, and engaged UNCTs and National Governments in the UNIP Process. All UNIP countries submitted their assessments of needs. Technical support (WHO, UNICEF and PIC) was given to the South African Government in the development of its communication strategy on H1N1. 13 countries out of 14 (not Comoros) requested technical assistance.

In January 2009, PIC Southern Africa met, in Botswana, the country’s Disaster Management Department (in the Office of the President) and Ministry of Health to advocate the importance of the “Whole-of-society Approach” to pandemic preparedness. It was agreed that a TTX for the Botswana Government, the UNCT and the Botswana-based SADC secretariat was to be held on 22 April 2009. PIC also initiated discussions with the SADC Secretariat to integrate pandemic preparedness into the Regional Health and Population Strategy. The planned TTX took place, as scheduled, on 22 April in Gaborone, Botswana, facilitated by PIC and involving the Botswana Government, UN Agencies, embassies and international organizations based in Botswana. A week after the TTX, the Government of Botswana revised its contingency plan as per the findings of and recommendations from the TTX.

In early May, PIC Southern Africa met the Director-General of the Seychelles Department of Risk and Disaster Management (DRDM - in the Office of the President) to discuss the way forward for the Seychelles. It was then agreed that a TTX was to be organized with the Seychelles National Platform for Disaster Reduction under the leadership of the Seychelles Disaster Risk and Management Secretariat (also in the Office of the President). The TTX – a multisectoral one - was preceded by a field visit to various disaster management operation centres in the country and by an Emergency Preparedness and Response Workshop. In July, PIC Southern Africa met the Department of Risk and Disaster Management (DRDM), Ministry of Health & Social Development and WHO Liaison Office (ensuring UN Coordination in the country) to explain further the “whole-of-society” approach. PIC had a special session with the DRDM to brief its staff on the “whole-of-society” approach and the role and responsibilities of disaster management institutions in pandemic influenza. On 09 July, the multisectoral TTX on pandemic influenza was organized in the Seychelles with technical support from PIC and WHO, under the chairmanship of the Permanent Secretary in the Vice President’s Office and the Director-General of the DRDM. The small UNCT in Seychelles also participated in the TTX. As some private sector members had been able to develop BCPs, their experience was used to train other sectors.

In mid-August, OCHA-PIC Southern Africa and UNICEF technical Hub based in Johannesburg participated to the WHO Africa Regional Conference on H1N1 held in South Africa, attended by over 300 delegates from African Ministries of Health and WHO Country Offices. The Conference provided a forum to review preparedness and response plans, and share information and experience on surveillance, communication, case management and infection control, laboratory and research and vaccines.

During the same WHO Regional Conference, PIC Southern Africa held separate meetings with Government Officials from Angola, Botswana, the Comoros, Madagascar, Malawi, Mauritius, the Seychelles and Zimbabwe, to discuss progress and responses made by their National Governments. It emerged from the meetings that: the Angola plan had been revised and covered non-health issues; the Botswana plan had been revised just after the TTX in April; the Comoros plan had been revised but not finalized yet; the Madagascar plan had been revised and adopted on 28 July, and Government BCP was to be developed; the Malawi plan had been revised but needed to be tested; a Mauritius simulation had been carried out in June to test its new plan; the Seychelles plan had to be finalized; and the Zimbabwe plan had been revised but not finalized.

In August, PIC Southern Africa met with South Africa’s National Disaster Management Committee (NDMC) to discuss its leadership of pandemic preparedness and response beyond the health sector. It was agreed that the National Plan was not sufficient because each Provincial Government’s operations were independent from Central Government and available resources were not the same. NDMC proposed that plans ought to be developed in the most H1N1-affected provinces of Gauteng and Western Cape, stressing that Disaster Management Departments in the two provinces required more capacity and finance. In October, PIC had another meeting with South Africa’s National Disaster Management Committee (NDMC) to discuss the involvement of other key sectors in pandemic preparedness planning. The meeting was followed by another meeting in November. The South African government agreed to give priority to pandemic influenza and cholera preparedness for 2010 and a budget has been allocated to the Ministry of Health.

In September, PIC facilitated, in Madagascar, a National Training Workshop on Whole-of-Society Approach and Business Continuity Planning. Participants were from various key ministries, the UN System, INGOs and the Private sector. Madagascar’s National Office for Risk and Disaster Management (BNGRC in French) was to coordinate the implementation of the road map of BCP development from October to December 2009. Further technical guidance was given to Madagascar and the Seychelles. PIC attended the national BCP committee in Madagascar in which the Energy and Water company presented its business continuity plan.

In September, a TTX for the Zambia National Task Force on H1N1 was held in Zambia. PIC Southern Africa provided guidance to the National Government and UN RC’s Office on the organization of the TTX. Gaps were identified.

In October, PIC Southern Africa gave a presentation at an OCHA Regional Workshop on Disaster Preparedness to brief Southern African disaster managers and partners on progress made and the way forward in the Southern Africa region. The same month, PIC Southern Africa gave a presentation on pandemic preparedness and the role of PIC during the commemoration of the International Day for Disaster Reduction in South Africa, attended by some 200 disaster managers from South Africa and neighbouring countries (Madagascar, Mauritius, Mozambique, Tanzania, the Seychelles and Zimbabwe).

B. PROGRESS AND PERFORMANCE INDICATORS

Four briefings and presentations were made to Governments and regional bodies (target of 4 met). Fourteen disaster management focal points were lobbied (target of 8 exceeded), as well as five meetings for regional organizations (target of 4 exceeded). 13 National Governments revised their pandemic preparedness and response plans, pre positioned antiviral medicines and strengthen communication to the population.

4.4. QUALITATIVE ACHIEVEMENTS AGAINST OUTCOMES AND RESULTS

- Following intensive advocacy efforts by PIC Southern Africa, targeting UNCTs and National Governments, including National Disaster Management Authorities (NDMAs) in the 14 Southern African countries covered, the region began to pay attention to pandemic influenza. UNCTs were very active in supporting National Governments to develop response plans and build their capacities.

- Most of the countries shifted gradually from a health-dominated approach to pandemic influenza preparedness to a beyond-health, whole-of-society perspective. In line with this, they started to give NDMAs – rather than National Health Departments – a coordinating role, and revised their Contingency Plans (CPs) to develop Integrated Pandemic Influenza Contingency Planning.  Such momentum was sustained by the H1N1 threat which prompted National Governments to develop response plans quickly to respond better to the pandemic in stocking antiviral drugs, putting in place measures at their borders and developing communication strategies to raise public awareness .

- This situation prompted UNCTs in Southern Africa to urgently revise their pandemic preparedness and response plans, including BCP. Regional situation reports and updates with inputs from UNCTs were developed to enhance information sharing in the region.

- UNCTs and National Governments in the region adjusted their H5N1 plans to the new H1N1 virus and operationalized these plans. Some countries initiated the development of BCPs. However, efforts by UNCTs and National Governments, including government stockpiling of drugs, were constrained by limited financial resources and competing priorities.

- Advocacy work was carried out with the Southern Africa Development Community (SADC) to consider updating the Regional Avian and Human Influenza Preparedness and Response Plan and increasing interaction and cooperation between its Disaster Risk and Management Technical Committee and Avian and Human Influenza Technical Committee.

- At the beginning of the pandemic influenza 2009 A H1N1, South Africa and Madagascar are the only countries which can carry out laboratory tests on Influenza A in the region and the South Africa Laboratory expected to be overwhelmed if a pandemic hits the region. During the reporting period, few countries managed to upgrade their laboratories to be able to carry out PCR tests. H1N1 cases were confirmed in most Southern Africa countries, except the Comoros. Cases and deaths were confirmed in the following countries: Angola (13 confirmed cases), Botswana (23 confirmed cases), Lesotho (54 confirmed cases), Madagascar (16 confirmed cases), Mauritius (69 cases and 8 deaths), Malawi (4 confirmed cases), Mozambique (30 confirmed cases with 2 deaths), Seychelles (3 confirmed cases), Namibia (68 confirmed cases with one death), South Africa (11,729 confirmed cases with 91 deaths), Zambia (49 confirmed cases) and Zimbabwe (12 confirmed cases).

# Future Work Plan

PIC submitted a project worth US$ 1,485,000, including Southern Africa and 4 other PIC regional hubs, for 2010, which was approved by CFIA Committee on 14 December 2009. PIC’s goal is to protect vulnerable groups from the impacts of a pandemic. PIC’s work involves: (1) working with UN Country Teams to help National Governments in restricted-capacity developing countries improve their “whole-of-society” readiness for pandemic; and (2) helping UN and humanitarian country teams to be more ready to maintain essential operations, assist National Governments and deliver humanitarian assistance in a pandemic.

# Abbreviations & Acronyms

| AU: | African Union |
| --- | --- |
| BCP: | Business Continuity Plan |
| BNGRC (French acronym): | National Office for Risk and Disaster Management (Madagascar) |
| CFIA: | Central Fund for Influenza Action (UN) |
| CP: | Contingency Plan |
| DRDM: | Department of Risk and Disaster Management (The Seychelles) |
| DRR: | Disaster Risk Reduction |
| IFRC: | International Federation of Red Cross and Red Crescent Societies |
| INGO: | International NGO |
| NDMA: | National Disaster Management Authority |
| NDMC: | National Disaster Management Committee (South Africa) |
| OCHA CO: | OCHA Country Office |
| OCHA ROSA: | OCHA Regional Office for Southern Africa |
| RDT: | Regional Directors Team (UN) |
| RIACSO: | Regional Inter-Agency Coordination Support Office (UN) |
| RIASCO: | Regional Inter-Agency Standing Committee (UN) |
| SADC: | Southern Africa Development Community |
| TTX: | Table-Top Exercise |
| UNCT: | UN Country Team |
| UNIP: | Urgent Needs Identification and Prioritization (UN) |
| UNISDR: | United Nations International Strategy for Disaster Reduction |

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

E.g. Priority Area for the Peace building Fund; Thematic Window for the Millennium Development Goals Fund (MDG-F); etc.

The start date is the date of the first transfer of funds from the MDTF Office as Administrative Agent.

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

The indirect support cost, which is calculated as a percentage of the programme budget sub-total (1-8), should be in line with the rate or range specified in the CFIA TOR, MOU and LOA. The Management Committee encourages keeping management support costs at 7 percent level