|  | Pandemic Influenza Coordination (PIC) Emergency Services Branch OCHA Geneva |
| --- | --- |

Central Fund for Influenza Action - CFIA

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2009

| Submitted by: Michael Mosselmans, Director of Pandemic Influenza Coordination (PIC) team UN Office for the Coordination of Humanitarian Affairs (OCHA) Tel: +41 22 910 2778 e-mail: mosselmans@un.org |  | Country and Thematic Area(when applicable) Objective 6: Continuity under pandemic conditions Global – with a hub in Geneva and regional offices in Bangkok, Dakar, Nairobi, Cairo and Panama. |
| --- | --- | --- |

| Programme No: 0067360 / CFIA - B6 MDTF Office Atlas No: Programme Title: OCHA PIC Work Programme |  | Participating Organization(s): UN Office for the Coordination of Humanitarian Affairs (OCHA) |
| --- | --- | --- |

| Implementing Partners: UN Country Teams |  | Programme Budget (from the Fund): US$ 2,475,000 |
| --- | --- | --- |

Programme Duration (in months): 12 months Start date: 15 January 2009 End date: 31 December 2009 Original end date: 31 December 2009 Revised end date: 31 March 2010 Operational Closure Date: 31 March 2010 Budget Revisions/Extensions: OCHA – PIC fully expects to carry out all the CFIA-B6 activities stipulated in the project documents. A no-cost extension was requested and approved due to possible financial constraints for funding pandemic activities in 2010.

NARRATIVE REPORT FORMAT

# Purpose

  - Background

The Pandemic Influenza Coordination team is located in the Office for the Coordination of Humanitarian Affairs (OCHA) in Geneva. Its purpose is (a) to help UN country teams to prepare to protect staff health and safety; continue essential operations; and support national governments during pandemic; (b) working through UN country teams, to help national governments to prepare to mitigate the beyond health (economic, governance, humanitarian and social) impacts of pandemic; (c) to strengthen the readiness of humanitarian agencies to meet the humanitarian needs of vulnerable populations during pandemic. To achieve these goals, PIC’s work is a combination of advocacy; measurement of the current level of readiness of national governments and UN country teams; practical help to enable national governments, UN and humanitarian country teams to prepare; and coordination of humanitarian pandemic preparedness actors at national, regional and headquarters level, to promote synergy, avoid duplication and identify gaps. PIC has seven regional planning officers, based in OCHA regional offices, who organize regional platforms to coordinate pandemic preparedness activities in Asia/Pacific; Caribbean/Latin America; Central Asia/Eastern Europe; Eastern Africa; Middle East/North Africa; Southern Africa; and West Africa respectively. PIC was established in late 2006.

  - PIC’s outputs and key activities:

- UN and humanitarian country teams ready to continue operating in pandemic: Conduct table top and functional simulations to improve and test planning with UN and humanitarian country-based teams, agency headquarters and governments;

- Virtual platform to ensure monitoring of preparedness and the sharing of relevant tools and guidance maintained: Maintain online global preparedness tracking and guidance platform;

- International humanitarian community ready to respond in the event of a pandemic: Conduct simulations for Humanitarian Pandemic Preparedness initiative (H2P) partners in priority countries;

- Established humanitarian coordination mechanisms ready for pandemic-specific implementation: Encourage existing humanitarian coordination mechanisms,  at global, regional and country levels, including clusters, to develop plans for their roles in pandemic;

- Humanitarians in Pandemic (HiP) working group improves interagency coordination for humanitarian pandemic preparedness: Convene and facilitate the joint work planning of the IASC-based ‘Humanitarians in Pandemic’ working group.

- Regional coordination platforms deliver improved regional coordination on pandemic preparedness: Convene and facilitate joint planning meetings with pandemic preparedness actors at regional level;

- Governments in developing countries are better prepared for non health impacts of pandemic: Advocate with governments to include an influenza pandemic as a threat requiring multi-sector contingency planning;

- UN wider emergency planning improved through maximum use of PIC approaches: Together with IASC colleagues, promote the incorporation of influenza pandemic planning into other multi-hazard contingency planning;

- Roll out of standardized OCHA business continuity planning supported: Work with OCHA field offices to put in place their own multi-hazard business continuity plans.

  - PIC’s key immediate objectives from the UNAHICAP objective 6: Continuity under pandemic conditions

6.1.1 Pandemic influenza preparedness plans built upon existing mechanisms for disaster preparedness, mitigation and response and – as much as possible – fully integrated into existing structures for disasters and crisis management;

6.1.2 Stakeholders engaged in the facilitation of coherent strategies for pandemic preparedness and response, including in humanitarian settings, encouraging synergy;

# Resources

2.1. Financial Resources:

This project is an extension of OCHA-PIC’s existing programme referenced as CFIA/B-1, previously funded by the CFIA (USAID Grant). In 2009, the above-mentioned project was mainly funded by CFIA (USAID grant) and the UK Government (DFID) in addition to contributions received from Australia for PIC’s activities in the Asia Pacific region and Canada for PIC’s activities in Western Africa.

This is the breakdown of funds committed by donors in 2009:

CFIA (USAID Grant): US $ 2,475,000

UK (DFID): 	        US $    922,569

Australia:	        US $    158,980

Canada: 		        US $      57,875

OCHA–PIC fully expects to carry out all the CFIA-B6 activities stipulated in the project documents for 2009. Given the greater pandemic funding prospects for 2009 than 2010, and the US decision to reduce UN agency funding for 2010, we moved forward a small proportion of our 2009 grant into the 2010 calendar year, so as to balance the monthly expenditure on our donor funding, so as to be able to continue to deliver full services and support to requesting countries and achieve agreed goals in 2010 as well as in 2009.

During the reporting period, PIC spent 96 % (US $ 2,370,124) of the total funds received from CFIA (USAID grant) of US $ 2,475,000.

During the implementation of this project, there were no major constraints in the mechanics of the financial process. This is the breakdown of the CFIA funds received for B-6 project:

| Breakdown of CFIA funds received for B-6 project |
| --- |
| Category | Cost |
| Supplies, Commodities, Equipment and Transport | 46,500 |
| Personnel (Staff, consultants, travel and training) | 1,928,000 |
| Training of Counterparts | 25,000 |
| Contracts | 0 |
| Other Direct Costs | 191,000 |
| Sub-total | 2,190,500 |
| Indirect Costs | 284,500 |
| TOTAL | 2,475,000 |

2.2. Human Resources:

The UK Government (DFID) has seconded to OCHA PIC the Director to lead the team and UNSIC has seconded to OCHA  a Senior Pandemic Planning Adviser through UNOPS. This project has a total of 20 staff member (9 international and 11 national staff) based in Geneva, Cairo, Bangkok, Nairobi, Dakar and Panama as follows:

International staff members (9)

P-5 – Regional Planning Officer, Asia Pacific

P-4 – Field Manager, Geneva

P-4 – Regional Planning Officer, Eastern Europe / Central Asia

P-4 – Regional Planning Officer, West Africa

P-4 – Regional Planning Officer, Middle East / North Africa

P-4 – Regional Planning Officer, East / Central Africa

P-4 – Regional Planning Officer, Latin America and the Caribbean

P-3 – Information Management / Humanitarian Affairs Officer, Geneva

P-2 – Desk Officer, Geneva

National staff members (11)

GS-4: Geneva (1)

NOA & GS-4: Asia Pacific (2)

NOA & GS-2: West Africa (2)

NOA & GS-2: Middle East / North Africa (2)

NOA & GS-3: East / Central Africa (2)

NOA & GS-5: Latin America and the Caribbean (2)

# Implementation and Monitoring Arrangements

Field-based Regional Planning Officers supported by a global coordinating team in Geneva conducted programme implementation including country-level and regional engagement. There were clear measurable deliverables (such as simulation exercises conducted, online global preparedness tracking and guidance platform maintained; joint workplanning meetings with pandemic preparedness actors held).

Preparedness action undertaken could now lead to significant reductions in the substantial economic, social and humanitarian impacts of pandemic. The proposed programme outputs have sought coherence and synergy amongst humanitarian pandemic preparedness partners at all levels, whilst delivering improved preparedness planning amongst humanitarian country teams - who in-turn supported national authorities - and OCHA field offices.

PIC’s procurement was undertaken by OCHA through UNOG for the Geneva-based team and through UNDP for PIC regional hubs based on UNOG and UNDP procurement procedures

PIC’s on-line global preparedness tracking system, simulations and meetings held at different levels in HQ and in the field have been critical in monitoring, assessing and incorporating lessons learned from one region to another.

PIC’s assessment of the state of global pandemic preparedness shows that low income countries have suffered from a lack of resources, skilled personnel and competing priorities which has led to low levels of preparedness.

To reflect evolving needs in the light of the H1N1 pandemic, PIC changed its priorities in the second half of 2009 and  channeled its resources to support preparing the poorest countries to face the impacts of H1N1.

# Results

4.1. PIC’s core team (Geneva)

PIC Geneva assisted the Resident Coordinator (RC’s) Office in Egypt in organizing and delivering a functional simulation to test the UNCT's Pandemic Plan.

PIC completed the OCHA Geneva ‘Crisis & Continuity Management Plan” –covering Business Continuity, Pandemic Preparedness, and Crisis Management.

PIC participated in a WHO-hosted meeting in Copenhagen which established a strengthened coordination mechanism between the World Bank, WHO, CDC, OCHA, ADB, CAREC and NAMRU3 for pandemic preparedness activities in Europe and Central Asia.

PIC represented the United Nations at the French Government’s functional pandemic simulation in Paris.  The event tested the recently revised national pandemic plan.

PIC Geneva participated in the H2P Operations Committee, the H2P Food & Livelihoods working group, and the H2P country plan template-working group.

PIC met with US AFRICOM to share plans to ensure that respective efforts are coherent and coordinated.

At IOM’s retreat of regional and field-based staff, PIC delivered a presentation on its work and recommended areas for PIC-IOM collaboration.

PIC hosted a 2-day retreat of the HiP (Humanitarians in Pandemic) inter-agency group.  The event was well attended by representatives from UN agencies, the Red Cross Red Crescent Movement, NGOs, USAID and US AFRICOM.  Participants discussed a variety of topics – including a joint advocacy strategy to raise the profile of the pandemic issue within respective organizations, minimum pandemic preparedness requirements for humanitarian agencies, incorporation of pandemic into the civil military and cluster agendas, planning for a regional simulation, and ways to ensure the sustainability of current pandemic preparedness efforts – and agreed on a number of follow-up activities.

PIC finalized the annual progress report on the Declaration on Humanitarian Cooperation in Pandemic Preparedness and Response and it was sent out to heads of participating agencies in conjunction with UNSIC and IFRC.

PIC delivered presentations on maintenance of essential services during a pandemic and integration of pandemic preparedness into existing national disaster management planning at International Civil Defense Organization (ICDO) training sessions for Directors of national Civil Defence Departments.

PIC held a retreat on 27-28 May with its six regional officers, as well as colleagues from FAO, IFRC, IOM, UNSIC, WFP and WHO. The retreat looked at challenges to effective inter-agency collaboration to promote pandemic preparedness in the field and how agencies can most effectively work together to overcome them.

PIC visited Bangkok from 30 March - 2 April for the annual workshop of Asia Pacific UN country team avian and pandemic influenza focal points convened by UNSIC Bangkok. PIC gave 3 presentations, on multi-sectoral pandemic preparedness, on UN country team pandemic contingency planning and on the IFRC/USAID humanitarian pandemic preparedness initiative.

PIC participated in a EU-UN workshop in Brussels, Belgium, to exchange best practices on business continuity planning.

PIC helped to facilitate a simulation exercise at a UK Government-led conference at Wilton Park from 8-10 June on the international system's approach to pandemic preparedness and response. Participants at the conference agreed to promote energetically the need for multi-sectoral preparedness.

PIC participated in a WHO meeting in Tunis, Tunisia, to help develop new simulation and training packages for Governments to support the new WHO pandemic preparedness guidelines.

During the OCHA briefing to ASEAN Permanent Missions in Geneva on 16 April, PIC briefed on its collaboration with the ASEAN Secretariat on assessing multi-sectoral pandemic preparedness across the region.

Working with WHO and IFRC, PIC prepared a rapid assessment of the global state of pandemic readiness for the UN Secretary-General, for use at his meeting with donors on 6 July, at which he appealed for resources for accelerating pandemic readiness.

PIC helped to organize a meeting in New York between UNICEF, PIC, UNSIC, IFRC, InterAction, Save and American Red Cross to discuss how the UN, Red Cross and NGOs can most effectively work together to accelerate pandemic preparedness efforts.

PIC attended a WFP logistics cluster meeting in Rome, at which the logistics cluster developed standard operating procedures for how to deliver logistics and food interventions in the event of a severe pandemic.

PIC visited Addis Ababa from 28-29 April and made presentations to 90 representatives of African humanitarian NGOs and Red Cross National Societies about how best to prepare for the possible impending influenza pandemic.

PIC attended a meeting hosted by PACOM, AFRICOM and WFP in Rome, Italy, for militaries from 30 African, Asian and Pacific countries to discuss how developing country militaries should best prepare for their role in a pandemic. PIC presented on the role of the UN system in a pandemic, on the whole of society approach to pandemic preparedness, on the role of the military in a pandemic and on humanitarian assistance during a pandemic. At the end of the 5-day meeting, militaries present felt better placed to develop appropriate plans for their potential roles.

PIC attended a USAID-led Inter-Agency meeting in Washington, USA, to discuss the respective contributions agencies can make toward accelerating levels of preparedness in the weakest countries.

PIC finalized a paper providing advice to Governments on how to prioritize amongst non-health essential service workers for provision of H1N1 vaccine, under the umbrella of WHO's programme to supply the 95 neediest countries with H1N1 vaccine.

PIC represented the UN on the Humanitarian Pandemic Preparedness Operations Committee in Washington on 14-15 October. Discussion covered the role of humanitarian partners in the current H1N1 vaccination effort, the future direction of the USAID-funded programme in 2010 and 2011, and the appropriate balance of effort between helping countries deal with H1N1 versus preparing countries for a more severe pandemic.

PIC visited Annecy, France, on 11 November for talks with AED, Core Group, IFRC and USAID about our respective current approaches to H1N1 response and opportunities for collaboration.

PIC held discussions with the CERF Secretariat about preparing the CERF to be available in a severe pandemic. It was agreed that key UN humanitarian agencies could prepare standardized proposals for CERF funding that could serve as a baseline to speed up CERF disbursement in such a scenario.

PIC chaired a meeting of the interagency humanitarians in pandemic working group on 11 December. It was attended by IFRC, Save, Core Group, AED, UNICEF, USAID, UNHCR, UNSIC, World Vision, Africom and UNFPA. It discussed the balance of effort between current H1N1 and preparing for a future more severe pandemic; and the direction of humanitarian pandemic preparedness into 2010.

#### 4.2. PIC’s regional planning officer for Europe and Central Asia (Geneva)

PIC went on mission to Hungary to work with IFRC, UNHCR and WHO to assess Hungary's level of pandemic preparedness and to assess Hungary's capacity to support other countries in the region - and to work with UN agencies in Hungary to upgrade their pandemic planning.

PIC delivered a presentation on the Whole-of-Society approach and conducted a TTX in Russian at the WHO workshop on pandemic preparedness in Ashgabat, Turkmenistan.

PIC Regional Planning Officer for Europe and Central Asia (ECA) conducted a joint mission with WHO in Kyrgyzstan on 5-9 October focusing on follow-up to the UNIP process and a multi-sector simulation was undertaken with regional public health officials.

PIC ECA met with Government officials in Belarus on 12-16 October to advise on multi-sector planning and preparedness.

On 11-19 November in Tajikistan, PIC ECA participated in a joint mission with UNDP sponsored by REACT.  The aim of that mission was to improve overall awareness and planning among the NGO community.

4.3. PIC’s regional hub in Asia & Pacific (Bangkok)

PIC’s regional hub in Asia and the Pacific gave a presentation on “Multi-Sectoral Pandemic Preparedness” at the Pandemic Preparedness Conference organized by the Centre for Non-Traditional Security Studies at the S. Rajaratnam School of International Studies in Singapore.

PIC’s regional hub for Asia and the Pacific gave 2 presentations about the "Whole-of-Society" approach and the "UN system approach" for multisectoral pandemic preparedness planning at the Workshop on the revised WHO guidance on pandemic influenza preparedness and response in Fukuoka, Japan.

PIC’s Asia hub discussed with the Thai Ministry of Public Health (MOPH) coordination of an ILO Pandemic Influenza project in the workplace, focused on advocating the need for pandemic preparedness and Business Continuity Plans (BCP), and on training trainers for implementation in Cambodia, Lao PDR, Malaysia, Indonesia, Thailand, and Vietnam. The Thai Ministry of Public Health is finalizing a Business Continuity Plan package, which will be used as a tool for both government and private enterprises.

PIC’s Asia hub delivered a presentation on the "Whole-of-Society" approach for multisectoral pandemic preparedness at the Pandemic Influenza Subject Matter Expert Exchange in Puerto Princessa, Philippines, organized by US PACOM and the Defence Forces of the Philippines; and provided faciltiation support for the provincial Government and Disaster Management Agency.

PIC Bangkok provided in-country support to UNCT Lao PDR for a Pandemic TTX.  PIC staff facilitated one of the 4 groups. 14 UN agencies participated in the Tabletop exercise.

PIC joined an ASEAN team to assess Indonesia's levels of pandemic preparedness from 1-5 June, using a methodology that PIC helped ASEAN to develop. Actions to improve Indonesia's preparedness were identified.

PIC in Asia and Pacific region has briefed Singapore Business Association on issues related to Influenza A H1N1 2009, the pandemic threat and the preparedness action and priorities that need to be undertaken by Governments, private sector, civil society, NGOs and others.

On 11 December, PIC Asia Pacific (AP) facilitated a pandemic tabletop simulation exercise for the Myanmar UNCT.

On 11 November in Bangkok, UNSIC and PIC AP made presentations to regional UN partners on the revision of the Consolidated UN System Action Plan for Contributions of the UN System and Partners (UNCAPAHI), and on progress with Urgent Support for Developing Countries’ Responses to the H1N1 Influenza Pandemic (UNIP) .

On 12 October, PIC Regional hub in Asia and Pacific region (AP) presented on “Multi-sector Pandemic Preparedness Planning: Requirements and steps’’ during the National awareness raising workshop to protect business and employees from pandemic human influenza organized by the Ministry of Human Resources and ILO in Malaysia

On 4-6 November 2009 in Bangkok, PIC AP presented the “United Nations simulation experience” to government health officials from Cambodia, Indonesia, Lao PDR, Malaysia, Philippines, Singapore, Thailand and Vietnam to share experience in the design and conduct of UNCT simulation exercises.

On 9-10 November, PIC AP presented the first results of the online survey on the impact of pandemic (H1N1) on business operations to the 4th APEC Business Advisory Council (ABAC) in Singapore.

The 1st Asia Europe Foundation (ASEF) Steering Committee Meeting took place on 16 Nov 2009 in Malaysia.  21 participants attended from ASEAN Secretariat, Asia-Europe Foundation, European Commission, Japan, IFRC, IOM, UNSIC, WHO/WPRO and Nestle. PIC AP presented on the possible pandemic impact on different sectors and planning requirements and steps to be taken by governments to prepare accordingly; and about the Whole of Society approach. PIC AP also explored the opportunity for future collaboration between Asia and Europe involving various stakeholders.

4.4. PIC’s regional hub in Central & East Africa (Nairobi)

PIC’s regional hub for East and Central Africa supported a tabletop simulation exercise for the Burundi UNCT that was carried out in Bujumbura with participation from Burundi military officials, UN agencies and NGOs.

PIC’s regional hub for East and Central Africa participated in a workshop held to follow up gaps identified during the Zanzibar regional simulation in December 2008.  It involved participants from Kenya, Uganda, Rwanda, Burundi and Tanzania (including national Heads of Veterinary services, lead Human Health officials, government officials and private sector). Follow-up measures include field exercises on pandemic simulation across country borders, revision of contingency plans and continued advocacy to governments on support to AHI.

PIC Regional hub in Central & Eastern Africa (CEA) participated in the regional United States Africa Command pandemic simulation exercise in Uganda 18-23 October. Its purpose was to strengthen the ability of regional actors to respond in a severe pandemic. This regional simulation was attended by IFRC, WHO, UNHCR, UNOCHA, IOM, WFP, AU, USAID – OFDA, and senior military staff from Kenya, Uganda, Rwanda, Burundi and Tanzania.

PIC’s Regional Hub in Central and East Africa was closed on 31 December 2009 due to financial constraints and lack of buy-in from countries in that region which are continuously affected by complex emergencies and do not consider pandemic as their top priority. This closure of PIC’s Nairobi hub will increase regional coverage and responsibilities of Regional Planning Officers based in Cairo, Johannesburg and Dakar.

4.5. PIC’s regional hub in West Africa (Dakar)

PIC’s regional hub for West Africa co-facilitated a Functional Simulation that was held simultaneously in both Togo and Benin and was facilitated jointly by 2 teams composed of staff from PIC-OCHA, WFP and UNICEF.

PIC’s regional hub for West Africa supported the Guinea Bissau UN Resident Coordinator (RC)’s Office’s participation in a government-organized TTX.  PIC also reviewed the state of government and UNCT pandemic preparedness.

PIC regional hub in West Africa attended ICAO’s Abuja Airport Evaluation, the CAPSCA (Cooperative Arrangement for the Prevention of the Spread of Communicable Diseases through Air Travel) regional Steering Committee Meeting, and a Nigeria UN country team (UNCT) AHI Coordination meeting in Abuja.

On 9-12 November, PIC WA facilitated a tabletop simulation exercise in order to validate the feasibility of the national pandemic response plan in Nigeria.

On 7-12 December in Ghana, PIC WA gave a presentation on the Whole of Society approach during a workshop organized by US Africa Command for Western African planners from Ghana, Benin, Togo, Burkina Faso, Nigeria, Senegal, Mali and Liberia.

PIC’s Regional hub in West Africa (WA) gave a presentation on the concept of a whole society response, the need for enacting multi-sectoral networks and different ways of conducting exercises during a simulation exercise for H2P implementing Red Cross Societies from Ghana, Gambia, Senegal, Nigeria, Mali and Benin.

On 18-21 November in Senegal, PIC WA facilitated a tabletop simulation exercise in close collaboration with IOM and the Senegal National Red Cross Society. The exercise focused on collaboration amongst players at community level (political administration as well as humanitarian workers) with assistance to migrating populations as a special concern.

4.6. PIC’s regional hub in Middle East, North Africa and Central Asia (Cairo)

On 7 September, the PIC regional hub in Middle East, North Africa and Central Asia (MENACA) made a presentation on multi-sectoral and business continuity planning during a training course organized by IOM on health promotion, human influenza and business continuity planning in Jordan.

4.7. PIC’s regional hub in Latin America and the Caribbean (Panama)

The PIC regional hub for Latin America and the Caribbean facilitated a TTX for the Dominican Republic UNCT.  The exercise involved participants from WHO, WFP, ILO, UNAIDS, UNDP, UNFPA, IOM, FAO, UNICEF, UNDSS, most of the directors of the agencies, and the RC.

PIC Latin America delivered a TTX at a Redhum retreat to update the Redhum team on AHI and Pandemic preparedness, to raise awareness about the topic, and to help them visualize their role in a pandemic situation.

PIC’s regional hub in Latin America and the Caribbean attended the 4th Interagency Communication meeting on Avian & Pandemic Influenza in Mexico City.  The other agencies that participated in the meeting were UNICEF, IICA, PAHO, UNFPA, UNIC, PANAFTHOSA, World Bank, and IOM.

PIC Latin America participated in a regional aviation medicine seminar where Pandemic Preparedness was a main topic. ICAO and IATA organized this seminar, with the participation of civil aviation authorities, airlines medical personnel, airport authorities, UNWTO and WHO.

PIC Latin America participated in a National Workshop on Pandemic organized by SINAPROC, as part of preparation for the tabletop exercise on pandemic influenza. The aim of the meeting was to raise awareness among the institutions that form the COE (Centro de Operaciones de Emergencia). The meeting featured participants from Social Security, Ministry of Trade and Industry, Immigration, National Comptroller's Office and Civil Aeronautics.

PIC Latin America facilitated a desktop simulation exercise as part of a training held at the Regional Training Center in Health based in Panama City (the 8th Course on influenza in a series of trainings that this center offers, with the support of CDC, to professionals of different areas of the medical and veterinarian national services for the Central American countries and some Caribbean countries).  The purpose of the training was to highlight non-medical interventions, the importance of interlinkages between interventions in all sectors of society, and the urgency to enhance those elements that allow the functioning of society during pandemic and other major crises.

On 23-27 November, PIC LAC visited Costa Rica to meet partners and discuss their multi-hazard and multi-sectoral pandemic preparedness process.

On 1-4 December in Peru during an ICAO workshop, PIC gave a presentation on pandemic preparedness to stakeholders within the air travel industry. While in country, PIC met with FAO and the Andean nations committee (CAN) representative to discuss future collaboration.

On 26-27 November, PIC LAC presented the global and regional situation and highlighted the whole-of-society approach and BCP during an IOM workshop on Pandemic Preparedness for migrant populations. This workshop aimed to bring together stakeholders from the international community, national authorities and community members from Panama, Nicaragua and Costa Rica, to discuss communication and counseling in pandemic.

# Future Work Plan

PIC has submitted a project proposal for continuation of this project into 2010 for US$ 1,485,000, which was approved by the CFIA Committee on 14 December 2009.

##### Outputs, activities and performance indicators for PIC’s 2010 project

Output 1: Influence and assist national governments to plan for pandemic beyond the health sector

Indicator: 15 national governments develop stronger plans for how key sectors will continue critical services in pandemic

Output 2: Influence and assist regional bodies to plan for pandemic beyond the health sector

Indicator: 7 regional events promote regional cooperation in multi-sector pandemic preparedness. 7 regional institutions put multi-sector pandemic preparedness planning of their Member States on their agendas.

Output 3: Influence national disaster management actors to include pandemic in national disaster management plans

Indicator: 15 national disaster management organizations add pandemic to their agendas

Output 4: Stimulate successful beyond health multi-sector whole of society pandemic preparedness interventions through the PIC/UNSIC/WHO Urgent Needs Identification and Prioritization process

Indicator: 20 whole of society interventions funded by donors through the UNIP achieve their stated objectives

Output 5: Stimulate effective new beyond health multi-sector whole of society pandemic preparedness actions through PIC-managed UNDP-administered multi donor Central Fund for Influenza Action seed fund

Indicator: 15 projects funded by the CFIA fund achieve their stated objectives.

Output 6: Track state of national and UNCT pandemic readiness

Indicator: 50 updates made to PIC’s national and UN country team tracker systems

Output 7: Disseminate PIC chapter in new WHO pandemic preparedness guidance

Indicator: Dissemination plan agreed with WHO and successfully executed

Output 8: Work with ICRC and US Africa Command to develop an advocacy paper on the role of the military in pandemic

Indicator: Advocacy paper on role of the military in pandemic agreed by IASC-based Humanitarians in pandemic group

Output 9: Influence clusters to plan for pandemic

Indicator: 4 clusters issue guidance to country teams on humanitarian response to pandemic

Output 10: Influence country level IASC contingency plans to include pandemic

Indicator: 15 country IASC contingency plans include planning for the humanitarian impacts of pandemic

Output 11: Support incorporation of pandemic preparedness into multi-hazard business and operational continuity plans.

Indicator: 15 UN country teams incorporate pandemic preparedness into multi hazard BCPs

Output 12: Agree how CERF will be used in pandemic

Indicator: Agreement with CERF Secretariat how CERF will be used in pandemic

Output 13: Conduct focused exercises, drills and simulations with clear objectives and results

Indicator: 20 exercises, drills and simulations conducted for which 3 or more clear follow-up actions are implemented

Output 14: Stimulate concrete outcomes from IASC-based Humanitarians in Pandemic working group

Indicator: 5 concrete results implemented from HiP work plan

Output 15: Produce who does what where data for IASC partners where requested

Indicator: 5 positive feedbacks from partners on WWW data

Output 16: Improve tools to support revising, testing, assessing, monitoring and tracking UNCT and government pandemic preparedness capacities

Indicator:  3 improved tools

A high priority for PIC in 2010 will be to support partner UN agencies to seek to facilitate implementation of the urgent needs of the 77 countries with least capacity set out in the ‘Urgent Needs Identification and Prioritization’ report. In particular, PIC will support facilitating the implementation of the ‘whole of society’ needs identified in this report, and help to support monitoring and tracking of financial contributions to this agenda, ongoing and planned activities and  performance against objectives.

# Performance Indicators (optional)

This is a report on progress against the annual project performance indicators:

Outcome I: UN and humanitarian country teams worldwide ready to maintain essential operations and assist their national host governments

- From January to December 2009, 38 simulations were conducted (95% of target of 40 simulations in 2009).

- From January to December 2009, a total of 14 countries adopted the PIC planning framework for their pandemic contingency plan (100% of target of 14 countries).

- From January to December 2009, a total of 82 countries updated the data on their state of readiness on the PIC website (Exceeds target of 70).

Outcome II: Governments in restricted capacity developing countries improve their beyond-health preparedness for a sudden pandemic

- From January to December 2009, a total of 49 briefings and presentations were made to governments, partners and regional bodies (Exceeds target of 25)

- 69 national disaster management focal points were lobbied from January to December 2009 (Exceeds target of 50).

Outcome III: Governments, UN and partners better prepared to support humanitarian response in a pandemic

- From January to December 2009, 3 cluster leads put pandemic preparedness on their agenda. (75% of target of 4 cluster leads in 2009)

# Abbreviations and Acronyms

ABAC		APEC Business Advisory Council

ADB		Asian Development Bank

AED		Academy for Educational Development

AFRICOM	United States Africa Command

AHI			Avian and Human Influenza

AP			Asia Pacific

APEC		Asia Pacific Economic Cooperation

ASEAN		Association of South East Asian Nations

ASEF		Asia Europe Foundation

AU			African Union

BCP		Business Continuity Planning

CAN		Committee of Andean Nations

CAPSCA	Cooperative Arrangement for the Prevention of Spread of Communicable disease through Air Transport

CDC		Centre for Disease Control

CEA		Central and Eastern Africa

CERF		Central Emergency Response Fund

COE		Centre of Emergency Operations

ECA		Europe and Central Asia

DFID		United Kingdom Department for International Development

HiP			Humanitarians in Pandemic

H2P			Humanitarian Pandemic Preparedness

IASC		Inter-Agency Standing Committee

ICAO		International.Civil.Aviation.Organization
ICDO		International Civil Defence Organization

ICRC		International Committee of the Red Cross

IFRC		International Federation of Red Cross and Red Crescent Societies

ILO			International Labour Organization

IOM		International Organization for Migration

MENACA	Middle East North Africa and Central Asia

MOPH		Ministry of Public Health

OCHA		Office for the Coordination of Humanitarian Affairs

OFDA		USAID Office for Foreign Disaster Assistance

PACOM		United States Pacific Command

PIC			Pandemic Influenza Coordination team

RC			Resident Coordinator

TTX		Table Top Exercise

UNAHICAP	United Nations Avian and Human Influenza Consolidated Action Plan

UNCT		United Nations Country Team

UNDSS		United Nations Department for Safety and Security

UNFPA		United Nations Fund for Population Activities

UNHCR		United Nations High Commissioner for Refugees

UNIC		United Nations Information Centre

UNIP		Urgent Needs Identification and Prioritisation

UNOG		United Nations Office Geneva

UNSIC		United Nations System Influenza Coordinator

UNWTO	United Nations World Tourism Organization

WA			West Africa

WFP		World Food Programme

WPRO		World Health Organization Western Pacific Regional Office

WWW		Who is doing What Where

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

E.g. Priority Area for the Peace building Fund; Thematic Window for the Millennium Development Goals Fund (MDG-F); etc.

The start date is the date of the first transfer of funds from the MDTF Office as Administrative Agent.

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

The indirect support cost, which is calculated as a percentage of the programme budget sub-total (1-8), should be in line with the rate or range specified in the CFIA TOR, MOU and LOA. The Management Committee encourages keeping management support costs at 7 percent level

E.g. for the UNDG Iraq Trust Fund and the MDG-F.