# United Nations Development Group Iraq Trust Fund

# Project #: D2-02

# Date and Quarter Updated: December 2008

| Participating UN Organisation: UNFPA, UNOPS, WHO, UNICEF | Sector: Health and Nutrition Sector |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health (MOH) |

| Title | Emergency Obstetric Care (D2-02) |
| --- | --- |
| Geographic Location | Ninewa, Diyala, Salah-El-Din, Al-Anbar, Baghdad, Babel, Al-Muthanna, Al-Qadissia, Thi-Qar, Basrah, Duhok, Sulaimaniah, Najaf, Kerbela, Ta'meem, Wasit, Missan, Erbil. |
| Project Cost | US$ 12,603,477 |
| Duration | June 2004 – December 2008 – extension requested until 31 August, 2009 |
| Approval Date (SC) | 6 May 2004 | Starting Date | July 2004 | Completion Date | Jan 2007 |
| Project Description | This project aims at supporting safe motherhood in Iraq within the context of Primary Health Care and higher levels of referral. It aims to support the regeneration of a comprehensive set of health care activities that are needed in order to ensure and provide emergency obstetric care (EOC) services in Iraq. Thus contributing to the reduction of maternal mortality rates (MMR), one of the main national priorities as reflected in the MOH National Health Strategy |

# Development Goal and Immediate Objectives

| Development Goal The reduction of maternal mortality through improved quality of health services Immediate Objectives 1. Enhanced quality of maternal health services 2. Improved skills of service providers |  |
| --- | --- |

# Outputs, Key activities and Procurement

| Outputs | Maternity wards in 21 major hospitals rehabilitated and equipped to the benefit of over 4 Million Iraqi women in reproductive age 700 service providers from MOH and NGOs trained |
| --- | --- |
| Activities | - Rapid assessment to verify and update needs (MOH, WHO, UNFPA) - Training of trainers (TOT) and refresher training to cover urgent capacity development needs (MOH, UNFPA, WHO). - Rehabilitation and equipping of maternal wards (UNFPA). - Re-establishing surveillance system for maternal health (MOH, UNFPA, WHO, UNICEF). - Re-establish referral system (MOH, UNFPA, WHO, UNICEF) - Strengthen national training capacities (MOH, UNFPA, WHO, UNICEF) |
| Procurement | - 42 ambulances were purchased and transferred to the MOH to be provided to the 21 rehabilitated sites, two ambulances per each site. - 3 monitoring vehicles (US $91,970) - 3 armoured vehicles (US $ 474,743) - 6 ambulances were purchased, 3 of which will be delivered to the additional sites in the northern region of Iraq upon completion of their rehabilitation, and the other 3 will be delivered to serve the southern marshlands, delivery is estimated to take place in Jan 2009. - 4 Ambulances were purchased to be delivered to the southern marshes areas to serve the districts hospitals and PHC's in the underserved marshland of southern Iraq, delivery estimate is April 2009. - 3 Mobile Health Units were purchased; these units constitute part of the EmOC support program to the marshlands, delivery estimate is June 2009. - 198 anatomical models containing advanced child birth simulators, gynaecological simulators, maternal and neonatal birthing simulators, fetal baby models with umbilical cord and placenta for vacuum delivery. These items were purchased to assist the trainees who attended the cascade trainings (US $ 92,378) - Medical equipment and supplies (US $ 3,740,306) were purchased and transferred to the MOH to equip the 21 rehabilitated sites; another batch of equipment (US $515,000) was purchased and was delivered to Erbil in June 2008 to equip the three newly rehabilitated sites. |

| Funds Committed | 11,015,820 | % of approved | 100 |
| --- | --- | --- | --- |
| Funds Disbursed | 8,380,818 | % of approved | 100 |
| Forecast final date | 31 August 2009 | Delay (months) | 32 |

# Quantitative achievements against objectives and results

| Rapid Needs Assessment conducted | Needs assessment conducted evaluating the actual needs for medical equipment, supplies, medicines and drugs | % of planned | 100 |
| --- | --- | --- | --- |
| Refresher and TOT training, and strengthening national capabilities. | - TOT in EOC for 36 physicians and nurses conducted - 24 MOH staff were also provided with TOT on “Surveillance of Maternal Health and Referral System” - 338 doctors and statisticians were locally trained by trainers previously trained on Surveillance and Referral Systems at the National Training Center of Egypt (NTI). This brings the total number of MoH personnel trained to 1411 against the originally planned 700. - UNFPA had provided the MOH with anatomical models that were used to assist in the cascade trainings undertaken inside Iraq. | % of planned | 200 |
| Rehabilitation and equipping of maternal wards | - The rehabilitation of Obstetric Wards was completed for 20 out of 24 planned hospitals to be rehabilitated. - for the completed sites medical equipment, ambulances, and medical supplies were purchased over the period of 3 years 2005-2007, those items were stored at the MOH warehouses and were distributed according to a distribution plan that was agreed upon with the MOH. - Contracts for Rehabilitation of the additional sites in the northern governorates of Erbil were signed; an amendment to the agreement with UNOPS was signed to enable UNOPS from committing the required funds for the rehabilitation of the new sites. - Medical equipment, ambulances and supplies were procured; the final delivery estimated time will be June-July 2009. | % of planned Ongoing Ongoing | 80 |
| Re-establishing Surveillance and Referral system for maternal health | -Study tour for a group of Iraqi officials has been organized to benefit from regional experiences in the area of Surveillance and Referral; the study tour took place in June 2008 for a group of MOH officials. | completed |  |

# Qualitative achievements against objectives and results

The maternity wards already rehabilitated under the project and equipped with modern medical equipment, supplies and essential drugs/medicines as well as the numerous capacity building activities provided to their service providers have greatly improved the quality of maternal health services provided to Iraqi women at reproductive age within their catchments areas. A further extension has been requested to enable UNOPS from delivering the sites that have been contracted for in December 2008 to the MOH; the rehabilitation process is still ongoing and expected to be completed by June/July 2009, the expansion of the activities to include the 3 northern governorates’ selected hospitals and Primary Health Care Centers further contributes to the coverage of the project’s outputs. These short-term outputs (enhanced quality of maternal health services and improved skills of service providers) positively contribute to the project’s outcome, achievement of which and the resultant impact is yet to be realized.