- United Nations Development Group Iraq Trust Fund

- Project Summary Sheet

| Participating UN Organization: WHO | Cluster: D-Health and Nutrition |
| --- | --- |
| Govt. of Iraq Line Ministry Responsible: Ministry of Health |  |

- Programme/Project Number: D2-05

| Title | Emergency Public Health Assistance for Iraq-Strengthening Non-Communicable Diseases and Mental Health |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Location | Iraq (Nationwide) |  |  |  |  |
| Project Cost | US$ 11,000,000 |  |  |  |  |
| Duration | September 2004 – June 2008 |  |  |  |  |
| Approval Date (SC) | 22 Aug 2004 | Starting Date | October 2004 | Completion Date | Original: September 2005 Revised : 30th June 2008 |
| Project Description | The aim of the Programme is to improve Non-Communicable Disease control and to promote Mental Health Care (NCD& MH) through the PHC system and other components of care with a focus on community outreach programmes and community involvement. |  |  |  |  |

- Development Goal and Immediate Objectives

Non Communicable Diseases: The developmental goal is to reduce morbidity and premature mortality attributed to chronic non-communicable diseases. This meets the global goal: Prevention of chronic diseases by 2015 and the new goal presented by WHO report prevention of chronic diseases as vital investment to reduce death rates from all chronic diseases by 2% per year over and above existing trends during the next 10 years. The program contributes to the UN Millennium Development Goals (MDG) through both Goal 6 (Combating major diseases, mainly HIV/AIDS, malaria, and other diseases) and Goal 1 (Eradication extreme poverty and hunger). The program is also linked to the five national areas for action within the National Development Strategy which includes: - Meeting urgent needs and improving services: - Addressing shortages in medicine and urgent supplies. - Strengthening diseases surveillance system. - Meeting the most urgent rehabilitation needs. - Strengthening results based management. - Developing and implementation of reconstruction. - Developing standards for rehabilitation and new construction. - Training and capacity building. - Strengthening capacity in public health and related areas. - Training in clinical skills. - Mobilizing resources. - Improving information on current status and needs.

- Outputs, Key activities and Procurement

| Outputs | Non Communicable Diseases(NCDs); 1. Assessment of the prevalence of NCDs risk factors in the Iraqi Community. 2. Establishment of a system for a screening system for Diabetes and Hypertension and Integration of NCDs in PHC facilities. 3.Strengthening NCD recording and reporting at PHC level. 4. Improvement of Cancer registry activities and develop a program on early detection of Breast Cancer. 5. Develop a program for the control of blindness, particularly blindness due to avoidable causes, by integrating primary eye care services into PHC system and conducting a baseline data on the prevalence of avoidable blindness. 6. Establish baseline data on the prevalence of violence and injuries in Iraq. 7. Establish a multi-sectoral policy for promoting physical activities in Iraq. |
| --- | --- |
| Activities | Non-Communicable Diseases: - Planning for community survey on rapid assessment for causes of avoidable blindness - Supply 22 community eye care units with necessary equipment. - Provision of diagnostic and therapeutic equipment and supplies for NCDs and Ophthalmic diseases. - Upgrade capacity building in all areas of NCD, screening of Hypertension and Diabetes Mellitus, cancer, violence, rheumatic fever, Blindness and primary eye care including internal and external workshops and fellowships. - Distribution of manuals and guidelines on the treatment of HT and DM. - Initiation of the work of screening system for early detection of Hypertension and Diabetes in 43 selected PHCs all over Iraq.. - Establishment of a multisectoral committee to develop a national strategy for promotion of physical activity. - Publishing national cancer registries. - Capacity building in CanReg 4 program for cancer registry staff. |
| Procurement (major items) | Major procurements taken place in the area of control and blindness at all levels and early detection of Hypertension and Diabetes. |

- Situation as of 30/09/2008

| Funds Committed | 10,807,240 | % of approved | 98.0% |
| --- | --- | --- | --- |
| Funds Disbursed | 9,941,564 | % of approved | 90.% |
| Forecast final date | 30 June 2008. | Delay (months) | 6 months |

- Quantitative achievements against objectives and results:

| Development of case record for major chronic NCDs at PHC centers | Completed | 100% of planned |  |
| --- | --- | --- | --- |
| Planning for rapid assessment for avoidable blindness | In progress | 100% of planned |  |
| Supply of 22 community eye care units with essential equipment. | In progress | 90% of planned |  |
| Upgrade capacity building in all areas of NCD, cancer, Rheumatic fever, Violence, Blindness and primary eye care, cancer registry in the form of National training activities, external workshops and fellowships. | In progress | 90% of planned |  |
| Printing of manuals and guidelines. | Completed | 100% of planned. |  |
| Initiation of the work of screening system for early detection of Hypertension and Diabetes in 43 selected PHCs all over Iraq, - Provision of supplies and equipment. - Conducting pilot project - Initiation of work | - Completed - Completed - In progress | 100% 100% 75% |  |
| Establishment of a multisectoral committee to develop a national strategy for promotion of physical activity | Completed | 80% |  |
| Publishing national cancer registries | Completed | 100% |  |

- Qualitative achievements against objectives and results

Non Communicable diseases: NCD prevention and control has received an appreciable attention and support from the MOH and WHO that had contributed to the recognizable achievements in this field. The stepwise approach is considered as an introduction to NCD prevention and control activities, mainly focussing on development of baseline data, investment and upgrading the available resources through internal and external training, and procurement of necessary supplies and equipments. The 1st stepwise chronic NCD risk factors surveillance survey in Iraq has been completed; its report is published and widely distributed. In reponse to the recommnedation of the said survey, active steps, the screening system for hypertension and diabetes at selected PHC centers was initiated in 43 PHCs all over Iraq which aimed at early detection of HT and DM in a pilot trial to establish a nationwide sytem all over the country. Guidelines for the management of hypertension and diabetes for PHC physicians were printed and distributed. The integrated NCD case records were prepared by MOH. Active steps towards revitalisation of cancer registry taken place. Progressive efforts continue to integrate primary eye care into PHC services. The process of rapid assessment of avoidable blindness will soon start in 4 Iraqi district to come out with the 1st baseline data on the causes of avoidableblindness which will shed the light on the road map towards prevention and control of blindness in Iraq.