# United Nations Development Group Iraq Trust Fund

# Project # D2-11

# Date and Quarter Updated: 4th Quarter for October- December 2008

| Participating UN Organisation: WHO | Sector: Health and Nutrition |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health |

| Title | Emergency Medical Oxygen Supply and Production (Project recently reprogrammed for Emergency Humanitarian Response) |
| --- | --- |
| Geographic Location | No specific location (Implementation coordination is done at central level but beneficiaries are located all over the country) |
| Project Cost | US$ 2,824,760 |
| Duration | 9 September 2005-30 November 2006, suspension of activities and then resumption from 10 April 2008- 31 December 2008 and an extension from 31 December 2008 to 31 march 2009. |
| Approval Date (SC) | 1 September 2005 | Starting Date | 9 Sept 2005 | Completion Date | 31 March 2009 (see extensions under “Duration”) |
| Project Description | The original project (a quick impact project) aimed at providing medical oxygen to all hospitals in Baghdad, Mosul and Kirkuk governorates to meet their six month oxygen needs. The project was meant to be implemented as a temporally measure, the time for the MOH to find a suitable solution for long term oxygen supply system. The project sought also to provide a reliable, sustained and long term arrangements for an uninterrupted oxygen supply in Iraq through installation of 3 medium size oxygen production plants/units (1 in Baghdad, 1 in Basrah and 1 in Diwaniyah) as a pilot project to be expanded to the entire country with government own resources. However, following several obstacles which have been previously reported, the project component regarding the procurement and installation of the three oxygen plants, the implementation of the project was interrupted in November 2006 and a decision by WHO to return the remaining funds was taken in March 2007. Yet, because of urgent needs faced by the country, particularly in March- April 2008, the Ministry strongly recommended the use of available funds for emergency humanitarian response. Based on the Ministry’s requested, the DSRSG, Chairperson of the UNDG ITF Steering Committee approved on 10 April 2008 the project scope change but put the strict condition that the project will have to be completed by 31 December 2008. Details regarding the four main activities to be implemented under the revised project are given under section key activities below. |

# Development Goal and Immediate Objectives

The main development goal and immediate objectives of the project remain almost the same as in the initial project. These include two aspects: Increase access to quality health intensive care services especially for vulnerable groups and increase emergency preparedness and response capacity to deal with emergencies; Reduce disability and mortality, including maternal and less than 5 mortality rate due to the lack basic emergency medicines, including oxygen and other anesthetics among patients requiring emergency health care.

# Outputs, Key activities and Procurement

| Outputs | Timely response to emergencies in intensive care units through better access to needed emergency medicines and supplies Improved outcomes of visits to hospital emergency units with reduced morbidity and mortality |
| --- | --- |
| Activities | Under the reprogrammed project there are four main activities planned which are: Provision of a list of emergency medicines and supplies requested by the MOH. Replacement of some of the basic life support equipment and supplies in a number of ambulances Capacity building (training of trainers) on professionals involved in emergencies with focus on workers involved in first aid and ambulance management and blood transfusions Review and updating the report resulting from the nation wide survey on first aid and medical gases services which was conducted early 2006 but could not be finalised for dissemination. |
| Procurement (major items) | Emergency medicines and supplies, equipment and supplies for ambulances. |

| Funds Committed (31 Dec 08) | US$ 2,104,986 | % of approved | 75 |
| --- | --- | --- | --- |
| Funds Disbursed (31 Dec 08) | US$ 711,779 | % of approved | 25 |
| Forecast final date | 31 March 2009 | Delay (months) | 37 |

# Quantitative achievements against objectives and results

| Provision of medical oxygen to hospitals in Baghdad, Mosul and Kirkuk | Completely achieved | % of planned | 100 |
| --- | --- | --- | --- |
| Review and update the report on national survey on first aid and medical gases | The process of the review of the report has been discussed and raw data collected during the survey are being compiled. | % of planned | 40 |
| Provision of a list of emergency medicines and supplies requested by the MOH | Most of items which were requested by the MOH have been procured and the first shipments were delivered during the period under review. | % of planned | 70 |
| Replacement of some of the basic life support equipment and supplies in a number of ambulances | The MOH has reviewed the list of needs for ambulances and current needs focus on supplies. These are currently being procured through the international market. | % of planned | 50 |
| Capacity building (training of trainers) on professionals involved in emergencies with focus on workers involved in first aid and ambulance management and blood transfusions | The training on basic and advanced life support techniques have been completed in November 2008. A total number of 29 health professionals (nurses and paramedics) have completed the training courses which were done through the Jordan Civil Defence Directorate. The training on blood safety programmes at the Jordan Directorate for Blood Banks is ongoing. The first batch of 5 professionals has completed the training and the second batch is half way of the training at the time this report is compiled. | % of planned | 70 |

# Qualitative achievements against objectives and results

The sustained oxygen supply which was provided to hospitals covered by the programme has improved the quality of intensive care health services and has increased emergency preparedness and response capacity for these hospitals to deal with emergencies. This has contributed to the reduction of avoidable mortality and morbidity among patients undergoing surgery procedures or under resuscitation due to injury or shock. The survey to assess countrywide first aid and medical gases services conducted early 2006 has helped the MOH and other partners to gain a better understanding of the gaps and needs in medical oxygen services and ambulances. Some of the gaps were addressed through the procurement of new ambulances. The process of updating the report is currently challenged by lack of institutional memory as most the staff who participated to the survey are no longer working in the Ministry of Health. This has been has been discussed during the mission of WHO International team in Baghdad in June 2008 and a follow up mission is contemplated in February 2009. Regarding the procurement process of items requested by the Ministry of Health, there are three separate lists of 9 anaesthetics, 42 sutures of different types and 10 types of external fixators for which Purchase orders have been issued except for the fixators for reasons which have been explained in the previous update. A new invitation to bid for external fixators was issued and offers are being analysed. In addition to the above mentioned items which are being procured through international tendering, an emergency local procurement of about 11,000 quadruple blood bags valued at about $ 97,000 which are badly needed by the National Blood Transfusion Center (NBTC) is under process. Out of the above quantity, 5,000 quadruple bags will be given back to the Ministry of Health in Jordan to reimburse the loan earlier given to the Ministry of Health Iraq in May 2008 through WHO Iraq Office in response to acute shortages of blood bags during the violence that occurred throughout the country but mainly in Basrah and Baghdad. While the implementation of the project is progressing well, a request for extension of three additional months to allow the complete delivery of contracted goods was rendered necessary as most of suppliers require three to four months to ship the requested items.