EIGHTH Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: WHO (lead Agency) UNICEF |  | Old Cluster: D Health and Nutrition |
| --- | --- | --- |
|  |  | New Sector: Health and Nutrition SOT |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| D2-24 Cholera outbreak, early detection and mortality reduction |  | 1 |

| Reporting Period: |  | Project Budget: USD 4,433,172 |
| --- | --- | --- |
| 1 January – 30 June 2008 |  | WHO received: USD 3,469,718 UNICEF received USD 963,454 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| MoH |  | National Coverage |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| AWD Acute Watery Diarrhea DoH Directorate of health CDC Center for Disease control CPHL Central Public Health laboratory FETP Field Epidemiology Training program IMR Infant mortality Rate IRCS Iraq Red Crescent Society MDGs Millennium Development Goals MoH Ministry of health NDS National Development Strategy NIDs National Immunization days PHCU Primary Health Care Unit UNICEF United Nations Children Emergency Fund WHO World Health Organization |  | One year, February 2008 to January 2009 |

# NARRATIVE REPORT FORMAT

# Purpose

  - a.	Provide the main objectives, outcomes, outputs of the programme/project

Outcomes: Contribute (by the end of 2008) to the reduction of infant and child morbidity and mortality:

    - IMR reduction from 101/1000 in 1998 to 51/1000

    - Under 5 mortality from 126/1000 in 1998 to 63/1000

The key immediate objectives are:

- Assist MoH in updating and implementation of the cholera preparedness and response plan including all governorates with special focus on Baghdad, Basra, Suleimaniyah, Kirkuk and Erbil.

- To ensure adequate availability of emergency supplies sufficient for proper investigation and management of up to 20,000 hospitalized and 200,000 out patient cholera cases.

- To ensure that key health personnel in all governorates have the required capacity for cholera surveillance and case management especially for high risk groups.

- To increase awareness of the general public and health staff on diarrhoea prevention and control measures with special focus on cholera.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq

- MDGs

- Iraq NDS

- ICI

This project is in line with the UN Iraq assistance strategy and the UN Health Cluster matrix, as cholera early detection, proper management will reduce morbidity and mortality from cholera and hence contribute significantly to the achievement of the National Development Strategy and MDGs by preventing disease and reducing mortality and morbidity especially among women and children, and contributing to poverty reduction and development efforts

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

- The responsibility of health and well being of Iraqi people falls on the MoH, but it is recognized that the actions undertaken by other ministries also have a great impact on successful implementation. Hence, WHO/UNICEF works closely with Ministries of: Education, Higher Education, Environment, Municipalities and Public Works, Agriculture, Interior, Finance and Planning.

- Through the programmatic approach adopted by the UN in Iraq, WHO as the leading agency in health, works in close collaboration with all the other Health Cluster members including UNICEF, WFP, UNFPA, UNIDO UNOPS, IOM and UNIFEM. This collaboration occurs at the planning and implementation stages to ensure consistency and continuity and to prevent overlapping.

- WHO as the leading agency in the health and nutrition cluster acts as the secretariat for the Health Sector working group Biweekly meetings. These meetings are led by the MoH with the [participation of the international organizations and donors. During these meeting different policies are discussed, proposals are endorsed.

- WHO’s major implementation partner is the Ministry of Health. All WHO programs are implemented by MoH staff, with the active participation -especially in the area of monitoring and capacity building- of WHO national staff in Iraq who is considered experts at international levels.

- WHO is also working with UNICEF, Ministry of Enviroment, Medical schools and the other key health related line ministries and works in close collaboration with the UN Health Cluster members.

- UNICEF is mainly responsible for ORS and chlorine tablets, equipment procurement and social mobilization.

- FETP and medical schools are mainly responsible for review of AWD and cholera surveillance activities.

- Human Resources

a.	National Staff & Consultants: Provide the number and role (operation/programme)

11 technical officers, 2 logistics officers and 2 administrative assistant(WHO) and for UNICEF 2 staff based in Erbil and 5 contracted facilitators as well as 3 staff in Amman (1 technical officer and 2 programme assistants).

b.	International Staff: Provide the number and role (operation/programme)

3 technical officers (WHO) and for UNICEF 2 technical officers based in Amman.

- Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

The Ministry of Health (MOH) is the main government partner with the primary responsibility for implementing this project. It is fully in charge of management, implementation of the overall project through the Directorates of Health (DOHs) in the governorates, hospitals and PHCs at lower levels. In close coordination with MOH and UN Health Cluster partners WHO technical officers and UNICEF Project officers, backed up by contracted facilitators based in Baghdad and in other governorates as well National Officers in Erbil and Basra. They are all responsible for supporting planning and overseeing project implementation, ensuring procurement and timely delivery of required supplies. The monitoring activities for this project include field visits as well as regular meetings with DOHs staff in all governorates, and the preparation of periodic reports. WHO and UNICEF staff in Erbil, Basra, Baghdad and Amman, in coordination with MoH, prepares and finalizes all technical and financial reports. In addition, all the provided support is coordinated with WHO through the UN Health Cluster, whereby WHO provides overall technical as well as some financial support for routine and accelerated activities.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

UNICEF and WHO has a well established procurement procedure; this is as well an element of programme support. Usually the procurement is done through UNICEF Supply Division in Copenhagen and WHO supply division in Cairo; based on a long-established international competitive bidding procedure and delivered to Baghdad under international insurance coverage. WHO technical and logistic officers and UNICEF-contracted facilitator usually verifies the receipt of the supplies at MoH/EPI Ware House in Baghdad. Sometimes under request of MOH, UNICEF/WHO assists with distribution (through separate contract) of these equipment/supplies to governorates/DOH level. UNICEF-contracted monitors, and WHO technical officers and logistic officers; through their regular monitoring visits, will confirm distribution of these supplies to end-user locations, i.e. health facilities and reports on their use.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The monitoring system in place is usually through the MOH/DOH/PHC on the government side which is complemented by WHO technical officers and UNICEF contracted facilitators who in collaboration with MOH/DOH staff carry out regular visit to various facilities to oversee the implementation of cholera preparedness and response activities and collect relevant data for monitoring the progress in the implementation of cholera preparedness and response activities. Another mechanism is through the review of reports compiled by PHC, DOH and MOH on AWD incidence, water quality and other information related to cholera preparedness and response In collaboration with WHO and other cluster D members regular discussions meetings within the cluster as well as MOH CDC/CPHL officials are held on how to incorporate lessons learned to assure effective and improve cholera preparedness and response services.

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

The results of the joint WHO/MoH missions to review the cholera preparedness and response activities in the provinces of Babil, Salah Aldin; Diwanyia, Wasit; Missan, Najaf, Kerbala, Anbar, using a structured questionnaire which was carried out in August and September 2008 were immediately circulated in September 2008. The review shows:

- Enough stocks of drugs, supplies and laboratory reagents are available at all levels.

- Hospital and health center staff has good capacity to manage diarrhoea cases.

- AWD and water quality surveillance system in the 8 provinces has a good capacity in detecting, reporting and immediately responding to any cholera cases/out breaks.

Nevertheless, there is a need to further strengthen the programme to reduce the miss use of intravenous fluids and advocate for more reliance on Oral rehydration for the management of mild and moderate dehydration. There is also need on more focused social mobilisation campaign to raise knowledge about the importance of home treatment of water and personal and food hygiene.

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- National cholera preparedness and response plan updated and implemented.

- Strengthened diarrhoeal disease surveillance system all over the country with special focus on Baghdad, Basra, Suleimaniyah, Kirkuk and Erbil.

- Health facilities equipped with cholera emergency supplies (drugs, IV fluids, chlorine tablets antiseptics and laboratory supplies, chemicals and reagents) sufficient for the proper investigation and management of up to 20,000 hospitalized cases and 200,000 out patient acute watery diarrhoea/cholera cases.

- Enhanced capacity of 3,000 key health personnel in the mostly affected governorates on diarrhoea case management and prevention.

- Strengthened social mobilisation and advocacy campaigns including media for the general public and health staff on diarrhoea prevention and control.

- Cholera cases were early detected; swiftly reported to the provincial and central authorities. A well coordinated, strong and rapid out break response activities were conducted that succeeded in controlling the out break and minimizing the number of cases and preventing an explosive out break taking into consideration the country wide shocking situation of water supply and sewage disposal.

- The national health authorities hesitated at the beginning of the out break to share data with WHO, however, following strong advocacy by WR and WHO technical staff among concerned Ministers including Minister of health, prime minister's office. MoH is now sharing with WHO the needed data about the cholera morbidity and mortality on daily basis.

- Supported the capacity building of more than 1000 PHC managers and health education staff working at health education corners in main PHC through out Iraq.

- Equipped mobile health education teams in all governorates with laptop and projectors with generators to be used for community education in remote areas

- Supported the development of 10 TV spots on different key messages in and through MOH contract broad cast the messages through local media channels .the messages are also broadcasted through the local Tv channels in High risk areas including Babyl .

- In collaboration between MOH, and MOE, a teacher training package on hygiene promotion was developed and more than 1000 teachers were trained in 341 schools those were rehabilitated through UNICEF funds around 15 governorates , the training package included training on cholera prevention and Avian influenza prevention ., in addition more than 1000 teachers were also included from other schools .

- Supported production of Kurdish TV spots , animations and songs for children which is aired through the local channels on daily bases with support of MOH KRG .

- Community level interventions and social mobilization efforts are also intensified in high risk areas through a group of women volunteers trained to conduct house to house education and through mobile health campaigns at high risk areas as well as distribution of IEC materials .UNICEF supported 100 women volunteers and 45 young people educators ,more than 10 mobile campaign in high risk areas and mobilizing more than 150 religious people .

- Supported a rapid KAP assessment on existing cholera preventive measures knowledge and practices among care givers in Baghdad Rissafa and El Karch . The assessment aimed to identify key messages to be used in the communication campaign and main channels for communication. The results will also be used to monitor progress against objectives at the end of the year Quarterly  monitoring reports are provided to UNCEF and WHO.

- Central ministerial monitoring is also supported through more than 33 on spot visits to PHCs and community level interventions in high risk areas by health education department.

- Monitoring at governorates level was also ensured through UNICEF chief facilitator system to ensure timely and quality implementation.

- Four million Zinc tab. For management of acute watery diarrhea, 10 million WPT and 1 million sachet of ORS – new formula have been procured to be delivered in the thired quarter of 2008.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

The cholera out break was quickly detected, immediately reported, prompt and effective out break response activities were carried out and succeeded up to now in controlling and containing the out break..

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

Bad security condition is still prevailing and harmfully affecting health services provision. Nevertheless, Iraqi health staff maintain their performance through modifying scenarios to complete their work e.g. working in holidays, joining two or three out break response teams to finish the work in one place peacefully and rapidly then shift to other one Additionally, sometimes delivery of essential supplies including intravenous fluids from central level to other DoHs has been a major challenge.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

All people – without distinction of gender, race, religion, political belief, economic or social condition, has a right to equal access to the needed services.

The success of the AWD surveillance system was due to the intensive effort done in capacity building for surveillance staff at all levels. Advocacy (specially for decision makers) and social mobilization by all partners and actors at all levels and their solidarity in ensuring that all cases  of  AWD are immediately reported and properly managed and professionally investigated reduced morbidity and mortality and reduced the magnitude of the out break.

Provision of needed supplies, drugs, laboratory reagents and chemicals and their immediate availability through out the health system with special attention to high risk areas and population ensured equal opportunities to health care irrespective of gender, race, and religion, and political belief, economic or social condition

- Future Work Plan

  - Summarize the projected activities up to the end of December 2008 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

UNICEF

1. Create a net work of community educators through:

a. Mobilizing  religious people, counsel members, municipality staff  and women groups; through training , community coordination meetings and orientation sessions .

b. Supporting district level coordination meetings among  district counsel, tribe leaders school teachers  and other community leaders , this committee is tasked to  monitoring through  visits to schools , community education , monitoring water resources and distribution of IEC materials

c. Conducting mobile health education campaigns to high risk and hard to reach areas in all governorates.

2. Support national media campaign including development of 4 posters and 2 educational leaflets and supported the distribution to schools, PHC, market and mosques.

3. Coordination with MOYS to mobilizing 500 young people as advocates within their communities and the youth centers and more than 2000 university students at different governorates .

4. Coordination with MOLSA to conduct orientation sessions to staff working in kitchens of children institutions in all governorates, and more than 300 staff working at public restaurants and food shops.

5. Procurement of ORS, WPT and Zinc tablets “the quantity will be decided jointly with MOH”.

6. Provide logistic support including transportation services for the mobile health teams, surveillance teams and for cargo services.

7. Support monitoring at governorates level UNICEF chief facilitator system to ensure timely and quality implementation.

It is expected that pending activities will be completed during the first quarter of 2009 (extension approved till end of March 2009).

WHO

- Continue support to capacity building and advocacy activities among policy makers, clinicians and other health staff regarding their role in early preparedness and response to cholera case/s  as well as strengthening laboratory capacity.

- Continue Support weekly active surveillance visits to all hospitals to monitor the incidence of AWD.

- Continue provide laboratory kits, reagents and chemicals to the national and sub-national cholera and water quality laboratories.

- Through it technical staff in Iraq, Amman and Regional Office, continues monitoring of AWD  and water quality surveillance systems..

- Continue monitoring progress towards containment and control of the current cholera out break.

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Highlight any new challenges/constraints, mitigation strategies and lessons learned during the reporting period and monitoring processes and assessments, evaluations and studies undertaken/published in the period. Attach documents.

- Attach any available photos relevant to the project.