United Nations Development Group Iraq Trust Fund 

Project #:E3-04
Date and Quarter Updated: 30 September 2008 (3rd Quarter)
	Participating UN Organisation:  UNDP

	Sector: WatSan

	Government of Iraq – Responsible Line Ministry: Mayoralty of Baghdad/Baghdad Water Authority




	Title
	Emergency Rehabilitation of Karama Water Treatment Plant – Line I

	Geographic Location
	Baghdad City

	Project Cost
	US$ 2,955,875

	Duration
	14 months extension obtained to November 2008 in April 2008

	Approval  Date (SC)
	29.08.2005
	Starting Date
	November 2005
	Completion Date   
	January 2007

	Project Description
	The rehabilitation of Karama Water Treatment Plant (WTP) Line I will increase the plant’s production by 40% and bring the total plant’s output back to the pre 1990 capacity of 35 MGD. The sustainability of the project will be ensured by improving the managerial and technical capabilities of the staff at the plant, in addition to selected staff from the Baghdad Water Authority (BWA) and the Mayoralty of Baghdad (MoB).


Development Goal and Immediate Objectives
	1. Increase production of Karama Water Treatment Plant in Baghdad by 10 MDG

2. Increase reliability and long term operation of Karama water treatment plant

3. Water Quality monitoring and testing laboratory of the plant capable of conducting daily, weekly and monthly tests according to international testing standard procedures.


Outputs, Key activities and Procurement

	Outputs
	1.1. Production increased by additional 10 MGD of potable water.

2.1 The reliability and long-term operation of the whole of Karama water treatment plant is improved by 40%.

2.2 The staff of MoB, BWA and Karama WTP has the capacity to manage the potable water system.

3.1 A functioning Water laboratory.

3.2 Staff trained in water testing techniques

	Activities
	1.1.1 Procurement of materials and labour for rehabilitation and renovation of Karama W.T.P. Line I to its design capacity of 10 MGD.

2.1.1 Procurement of sand filter media for one-year operation.

2.2.1 Management development of the staff of the laboratory, the staff at the plant, the staff of the Baghdad Water Authority and Baghdad Mayoralty.

2.2.2 The management and staff of MoB, BWA and management of Karama W.T.P. will be trained on technical and operating skills.

3.1.1 Supply of materials and equipment for the laboratory’s water quality testing equipment and sand filters for one year’s operation

3.1.2 Provision of training in Water Analysis

	Procurement

(major items) 
	· Procurement of materials and labour for rehabilitation and renovation of Karama W.T.P. Line I to its design capacity of 10 MGD.
· Procurement of sand filter media for one-year operation
· Consultancy Services
· Works Contract 


	Funds Committed 
	US$ 2,636,838 (As of 21/9/2008)
	% of approved
	89

	Funds Disbursed
	US$ 1,542,584 (As of 30/9/2008)
	% of approved
	52

	Forecast final date 
	October 2008
	Delay (months)
	21


Quantitative achievements against objectives and results 

	Rehabilitation by local contractor
	Physical work implementation ongoing.
	% of planned
	90

	Drawings, manuals and test certificates
	Receipt of final deliverables for Phase II of the consultancy assignment: Bills of quantities verification for subsequent dispatch as part of the bidding documents.
	% of planned
	100


	Training of Trainers
	Capacity assessments completed and bidding process ongoing.

	% of planned
	60


Qualitative achievements against objectives and results 

	Complete design of the rehabilitation works required have been agreed and the kick-off meeting for works was held 21-28 October 2007.
Spares and equipment arrived on site in November 2007. Most project elements commenced site work and achieved almost 80% progress to date. During this reporting period, the following achievements have been noted:
· Completion of the chlorine building, water tank and the repair of the Alum unit and exterior walls-HPPS line I.
· Receipt of the chlorinator and the leak absorber systems No. 1 at the site of Umm Qasr port.
· Third Party Inspection (TPI) completed for the chlorinator system No.2 and dispatch was authorized.

· Shipment of the water pumps.


	


