# United Nations Development Group Iraq Trust Fund

# Project: 53651

# Date and Quarter Updated: 15th January 2009, 4th Quarter – October to December 2008

| Participating UN Organisation: UN Office for Project Services (UNOPS) | Sector: Cluster E – Infrastructure Rehabilitation (WATSAN) |
| --- | --- |
| Govt of Iraq – Responsible Line Ministry : Ministry of Municipalities and Public Works (MMPW) |

# Programme/Project Number: E3 – 10

| Title | Rehabilitation of water distribution Networks in Al-Bat'ha and Al-Nasser town Changed to Rehabilitation of Water Distribution Networks in Al-Bat’ha and Al Rifai’e town. |
| --- | --- |
| Geographical Location | Thi-Qar/ Nasiriya District and Al-Rifa'ie District |
| Project Cost | US$1,529,051 |
| Duration | 10 months originally, extended up to 21 months |
| Approval Date (SC) | 26 April 2007 | Starting Date | April 2007 | Completion Date | January 2008 – Original (Extended to 31st December 08) |
| Project Description | Repair and rehabilitation of the existing water distribution networks and extension of the distribution network to serve new areas. |

# Development Goal and Immediate Objectives

The Development Goal of the project is to contribute towards improvement in the public health of the inhabitants by increasing the availability of safe drinking water. The key objectives are to: Establish a sustainable, cost-effective and financially viable project by restoring the existing water distribution network to become functionally efficient. Improve the operational efficiency of the existing water distribution network to significantly enhance the quality and quantity of water supplied to the population. Introduce new technology by providing new techniques and best practices and advance type of material available for use.

# Outputs, Key activities and Procurement

| Outputs | Improvements to the health status of the population Increase in the quantity of water available through reduction in network losses Improvement to the quality of water through prevention of cross contamination. Improved accessibility to safe water Reduction in the number of hospital cases Job opportunities for over 150 construction workers per day. |
| --- | --- |
| Activities | Repair & replacement of approx 10km of the existing water distribution network in both towns Extensions to the existing water distribution network by nearly 20Km in both towns to serve 35,000 people in Al Rifai’e and Al Bat’ha. Modifications to the existing water distribution network with controlled zones Training on simple leak detection and repair techniques. |
| Procurement (major items) and on site activities | The project has been awarded to M/s Dubai Contracting Company for implementation of the project. Procured High Density Polyethylene pipes (HDPE) along with required fittings. Completed laying of entire length of PE pipes in both the towns. Completed providing of house service connections in both the towns. |

# Situation as of 31/12/2008

| Funds Committed | 1,239,070 | % of approved | 81.03 |
| --- | --- | --- | --- |
| Funds Disbursed | 1,077,736 | % of approved | 68.2 |
| Forecast final date | December 2008 | Delay (months) | 12 months |

# Quantitative and qualitative achievements against objectives and results

| Site preparations and contact awarding for civil work | Survey and design document of the civil works with full specifications was finalized. A contractor to install and rehabilitate the water mains pipes for both sites was chosen and awarded. Mobilization of material, manpower and equipment was fully completed. | % of planned | 100 |
| --- | --- | --- | --- |
| Procurement of pipes and fitting | The procurement of High Density Polyethylene pipes (HDPE) were concluded in addition to the entire related PE fittings. All pipes and fitting were strictly crosschecked against the ISO 9001/other certification from the International Organization for Standardization and were approved | % of planned | 100 |
| Civil work and rehabilitation | Al-Bath’a Town Fully completed the implementation of entire project work. Al-Refai’e Town Fully completed the implementation of entire project work. | % of planned | 100 |
| Training | Bidding process for selecting appropriate training centres was completed and the contract awarded to M/s Engicon. UNOPS had invited the Supervisory Technical/Management and Skilled/operation staff in Thi-Qar/ Nasiriya District and Al-Rifa'ie District water departments on 14 September 2008 regarding a training programme on Water Network Management. Despite UNOPS on ground efforts to expedite the governmental formalities in collecting the nominated participants names; the water authorities didn’t respond. UNOPS requested again on 27 October 2008 for the name of the participants and new dates were assigned for training, nevertheless, we got no response from the relevant authorities Since the project was ending and no reponse was received from the authorities; the training was cancelled. | % of planned | Cancelled |

# Further qualitative achievements against objectives and results

Several technical meetings were conducted in ThiQar water directorate to set the plans for a smooth implementation process. UNOPS staff met regularly with all stakeholders to ensure smooth coordination, monitoring and evaluation of the implementation of the project activities. At certain stages within the implementation process, the progress was slowed down due to the illegal construction of extensions to buildings neighbouring to the foot path (under which the pipeline is being laid). In addition to that, several security turbulence in the south had completely halted all implementation activities of the project. Finally the overall assigned project milestones were completed and was handed over to the relevant authorities on the 19th December 2008 .