World Health organisation

Six monthly progress report FOR Water Quality Control and Surveillance in Iraq PHASE II

# Summary

| Participating UN Organisation: |  | Cluster: |
| --- | --- | --- |
| WHO & UNICEF |  | Cluster E: Infrastructure Rehabilitation |

| Project No. and Project Title: |  | Project Location/Region/Province: |
| --- | --- | --- |
| E3-11: Water Quality Control and Surveillance in Iraq Programme Phase II |  | Iraq, Nationwide |

| Reporting Period: |  | Report no: |
| --- | --- | --- |
| 1st July 2007 – 31st Dec 2007 |  | 2 |

| Counterpart organisations / implementing partners: |  | Project cost: |
| --- | --- | --- |
| Ministry of Environment; Ministry of Municipalities and Public Works; Mayoralty of Baghdad. |  | US$ 4,297,643 |

| Abbreviations and acronyms: |  | Project Duration: |
| --- | --- | --- |
| MDG: Millennium Development Goals MOEv: Ministry of Environment MMPW: Ministry of Municipalities and Public Works MOB: Mayoralty of Baghdad WHO: World Health Organization UNICEF: United Nations Children Fund WQC: Water Quality Control and Surveillance |  | 12 months (extended 6 months). |

# Purpose

Main objectives and outcomes expected as per approved Project/Programme/project document:

The main objectives of the project are as follow: Strengthen the capacity of Ministry of Environment, Ministry of Municipalities and Public Works and Mayoralty of Baghdad at central, governorate and district levels in terms of planning, implementation and monitoring, concentrating on improving technical and managerial capacities of laboratories and the staff responsible for water and waste water quality control. Empower the Ministry of Environment, Ministry of Municipalities and Public Works and Mayoralty of Baghdad to ensure the provision of potable water and the enforcement of the rules and regulation related to the protection of the water resources from pollution. Raise public awareness among communities for the protection and preservation of water resources. The expected outcomes are as follow: Water quality surveillance system supported, where a comprehensive water quality program is implemented throughout the country. Technical and managerial capacity of about 1120 professionals dealing with water quality monitoring enhanced. Sustainable water quality laboratories affiliated to the Ministry of Environment and Mayoralty of Baghdad in addition to water and wastewater laboratories under the umbrella of the Ministry of Municipalities and Public Works fully furnished and equipped with essential equipment for quality testing. Laboratory Information Management System strengthened for the entire water quality laboratories network as a tool for efficient monitoring and decision making. Four hygiene awareness campaigns related to water born diseases targeting high risk areas implemented.

Reference to how the programme/project relates to the UN Assistance Strategy to Iraq and how it aims to support international and national development goals (revised National Development Strategy Dead Sea July 2005) including the Millennium Development Goals and other goals as pertinent:

The Programme contributes to the following Millennium Development Goals (MDGs), to: Halve, by 2015, the proportion of people without sustainable access to safe drinking water and basic sanitation; Reduce by two thirds the mortality rate among children under five. It also relates to the UN Assistance Strategy within “Rehabilitate and develop the country’s social, economic, financial, physical and institutional infrastructure to ensure sustainable livelihoods and durable solutions to displaced populations in the country.” Furthermore, it relates to the National Development Strategy, through Goal 6 which is to “Achieve universal access to safe drinking water and sanitation” and to Target 8 in the Strategy which is to “Ensure that all people have sustainable access to safe drinking water and improved sanitation.”

Main international and national implementing partners involved their specific roles and responsibilities in project implementation and their interaction with the agency:

The main international and national partners involved in the implementation of the project components are World Health Organization (WHO) United Nations Children Fund (UNICEF) Ministry of Environment ( MOEv ) Ministry of Municipalities and Public Works (MMPW) Mayoralty of Baghdad (MOB) Both WHO and UNICEF are providing technical, logistic and financial support for the implementation of the project components, WHO have three sub-offices in Iraq (Baghdad, Basra & Erbil) while UNICEF have two in (Basrah & Erbil) in addition to focal points in the other governorates. WHO has about 75 national staff (technical and supporting staff) working inside Iraq in addition to 30 technical and supporting staff working in its temporary office in Amman. The WHO Regional Office in Cairo and WHO Headquarters in Geneva and the Centre of Environmental Health Activities have a well known expertise in the area of water quality control and surveillance which work as an asset during the implementation of the project. Similarly UNICEF has 25 national staff inside Iraq supported by 36 engineers and monitors hired through an institutional contract. Coordination at the national level is undertaken closely with the Ministry of Environment, Ministry of Municipalities and the Mayoralty of Baghdad's technical staff during the project implementation, the coordinator with the focal points for the project have to travel between selected governorates to ensure proper implementation of the project and to carry out visible on the spot monitoring. The project manager, with the assistance of a UNICEF National Officer work with their counterparts at both technical and managerial levels, setting, in accordance with the technical unit the specification for all the equipment and supplies, and follow the WHO's Regional Office and UNICEF’s Supply Division in the process of procurement and facilitate the implementation of the TOT activities outside Iraq, in addition to the responsibility for periodic reporting on the progress of the implementation of the activities. Both are in direct contact with the Ministry’s staff at different levels and with WHO and UNICEF national staff via different means of communication, mainly through video conferencing to ensure the proper and smooth implementation of the project activities.

# Resources

Financial Resources

Total funds provided, disbursed and committed:

The total project budget approved by UNDG Trust Fund Steering Committee was US$ 4,297,643 (US$ 2,700,895 for WHO & US$ 1,596,748 for UNICEF), earmarked from the EC. Funds were received on the 27th December 2006 – the official start date of the project. The implementation of the project components are according to the plan and against the budget line for each component. Project expenditure as of 31st Dec 2007: S/N Item Description Approved Budget Committed Disbursed 1 PERSONNEL 264,000 198,966 198,966 2 CONTRACTS 468,000 427,358 129,374 3 TRAINING 895,000 525,790 475,790 4 EQUIPMENT 2,090,000 2,070,788 346,781 5 SUPPLIES & COMMODITIES 113,000 28,350 0 6 MISCELLANEOUS (Should Not Exceed 3% of Total Budget) 114,900 94,000 84,323 7 SECURITY (Should Not Exceed 2% of Total Budget) 76,600 61,900 56,345 8 AGENCY MANAGEMENT SUPPORT (including Monitoring & Reporting) 7% 276,143 270,363 234,708 9 PROGRAMME/PROJECT BUDGET TOTAL 4,297,643 3,649,165 1,526,287

Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s):

During the reporting period no variations from the approved budget took place.

Explain programme/project expenditures within the 10 budget categories, including security expenditures:

The majority of the amount spent is dedicated for the procurement of laboratory equipment and supplies for different labs affiliated to MOEv, MMPW and MoB. The expenditure for trainings covers the cost of transportation and daily allowances for the participants in addition to the cost of training materials and handouts. In relation to the amount dedicated for contracts, the funds are to cover the cost of renovation and rehabilitation of the existing laboratories. While the amount committed for personnel is to cover the cost of the staff responsible for implementation and monitoring the work progress. As far as security expenditure is concerned, the expenditure is for the cost of supplies shipment security from Amman to Iraq.

Indicate other funding sources, if applicable:

Other additional resources which are being used in the implementation of the project, which are not included in the mentioned budget include: Logistics and administrative facilities of WHO/UNICEF such as videoconferencing, which particularly in the context of the security situation in Iraq, have been key to coordination and interaction with the MOEv, MOMPW and MOB. Technical support and backstopping received from the regional and headquarters offices outside the agency management support framework; Additional MOEv, MOMPW,MOB, UNICEF and WHO personnel involved in the project implementation, monitoring, evaluation and reporting.

Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable:

UNICEF submitted an extension in project duration and budget revision request on 11th December 2007 as follows: Extension of project duration is requested due to the following reasons: Delays in finalizing and certifying the BoQs for rehabilitating the proposed sewage labs by the government (activity 1.1.3). Three contracts for rehabilitation are signed and the work has started. To ensure cost effectiveness, UNICEF took and additional step for purchasing laboratory supplies through exploring the regional capacity and costs. Some purchase orders were issued (activity 2.1.1). Agreeing on a unified approach for the implementation of the Laboratory Information and Management System (LIMS) was the major activity that consumed the majority of the available time. Hardware components were supplied and the bids for implementing the software were initiated (activity 2.1.2). Movement of funds between project budget components: The total cost for rehabilitating the proposed sewage labs exceeded UNICEF estimates as per the received quotations from bidders. Some funds had to be moved from activities where surplus amount is expected to cover salaries for the extended period.

Project expenditure for the period from 1st January to 22nd June 2008:

The projected expenditure for the coming six month staring from January is expected to be around US$ 2,656,000 Million.

Human Resources

National Staff: Provide details on the number and type (operation/programme)

Three national officers' full time and one project assistant part time, who are responsible for the operation and implementation of the project components in coordination with the counterparts, also they are monitoring the progress of implementation versus workplan. They are almost in daily contact with the focal points from the MOEv, MMPW and MOB by different means of communication in addition to the regular meeting on the ground.

International Staff: Provide details on the number and type (operation/programme)

One International staff member who is responsible for the whole management of the project. He is in regular contact with both the national staff and their counterparts through different means of connectivity such as e-mail, phone, video conferencing and meeting in Amman.

# Methods of Operating

Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

The delivery mechanism adopted is as follow: WHO/UNICEF in consultation with their counterparts prepared the technical specifications for the neccessary water analysis equipment and supplies. WHO/UNICEF in consultation with MOEv, MMPW and MOB technical staff assessed the chemicals and other laboratory reagents needed for water quality analysis. The procurement is progressing through the procurement section at either WHO/UNICEF country, regional and Headquarters offices as shown in the below diagram. WHO/UNICEF in consultation with the counterparts, facilitate the implementation of training of trainers programs outside Iraq where the participants become trainers for the technical staff. WHO in consultation with their counterparts, design and support the implementation of hygiene awareness programs for the community leaders. UNICEF in consultation with counterparts, design and support the implementation of the internal training programmes inside Iraq. In terms of the rehabilitation works, WHO in coordination with MOEv prepared all the drawings, bill of quantities and the bidding documents. MOEv announced the tender in an Iraqi local newspaper, after recieving offers from local contractors the offers went through multiple committees (Bid opening, analysis and review committee), then were doublechecked by WHO at the field level and at WHO temporary office in Amman to ensure that all processes went through according to both WHO and MOEv rules and regulations. During the commencement of the work, both WHO and MOEv engineer, supervise and monitor the work, and a weekly report supported by photos is received from WHO engineer who conducts daily monitoring on the progress of work. UNICEF applies a similar mechanisim for rehabilitation where BOQs are jointly prepared with the government, while the anouncement and biding takes place in Amman. Work is jointly supervised by the government and UNICEF.

Provide details on the procurement procedures utilized and explain variances in standard procedures.

The diagram below illustrates the steps followed by both agencies to procure and deliver the requested laboratory equipment and supplies. Inside Iraq, this approach was used in many of WHO/UNICEF projects and it is considered one of the success stories in terms of implementation approaches.

Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

WHO and UNICEF focal points (national staff and hired engineers and monitors) inside Iraq follow-up the implementation of the project components and monitor the progress of all the activities on the ground and prepare a visit report in addition to the weekly and monthly reports which are supported by photos from the filed. WHO and UNICEF offices in Amman receive feed back on regular basis from Iraq for analysis and decision making. In addition, there is a task force committee composed of MOEv, MMPW, MOB, WHO and UNICEF which meets on a monthly basis to discuss and follow up the implementation progress of the project components and find solutions for any obstacles facing the progress of the workplan.

Report on any assessments, evaluation or studies undertaken.

WHO/UNICEF in consultation with MOEv, MMPW and MOB technical staff assessed the chemicals and other laboratory reagents needed for water quality analysis. Similar assessments were undertaken to the laboratories identified for rehabilitation. Bills of quantities were jointly prepared by WHO/UNICEF staff and representatives from the relevant government authority.

# Results

Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs and during the six month reporting period.

During the reporting period, the project outcomes are almost progressing according to the plan of action agreed upon between all key partners (MMPW, MOEv, MOB, WHO and UNICEF) during the technical meeting which was held in Amman on 28-29 Jan 2007 and the outcomes expected in the project proposal. However, some delays occurred in the following activities: The procurement process, due to modification in the specification of some requested equipment and supplies. Awarding the contract for the renovation of the existing laboratories. The implementation of some training of trainers outside Iraq due to change or delay in the nominations from the line ministries. The implementation of LIMS due to delayed unifying, finalizing and approving the parameters used by line ministries included in the software.

Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

Covered in 4.3

Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

The key implementation activities illustrated in the table below, derived from the Project Proposal, have been used to guide the implementation of the programme. Key implementation activity Status 1 Rehabilitating some of the existing water & wastewater quality control laboratories The extension of the MOEnv Central Water Quality Control Laboratory in Hay Al-Andalus/Baghdad is progressing according to the work plan with a 40% completion rate. Extension work at MOEnv Central water quality control Lab. The Rehabilitation work of three sewage labs in Najaf, Ninevah and Diwaniya governorates is ongoing, with an average completion rate of 20%. 2 Procurement of 8 mobile laboratories for MoEnv, MMPW and MoB Technical specifications for the mobile laboratories including the equipment have been finalized in coordination with the technical staff from MOEv, MMPW and MOB. The procurement process has been finalized by WHO Regional Office. It is expected that the delivery will take place during April 2008. 3 Equipment, lab. supplies and reagents for Ministry of Environment Water quality control laboratories Technical specifications for the equipment and laboratory supplies including the laboratory reagents have been finalized in coordination with the technical staff from MOEv, MMPW and MOB. The procurement process has been finalized by WHO/UNICEF Regional & Head Quarter Offices. Some supplies have been received by the end users such as the laboratory reagents, glassware and part of the equipment. Approximately 60%.of planned achievements have been accomplished in this area Sanitary technicians testing drinking water 4 Development of human capacity among laboratory managers, technicians and sanitarian professionals through training and workshops 10 decision makers from MOEv, MMPW and KRG participated in a technical meeting in Amman with the participation of both WHO and UNICEF to discuss and set a plan of action for the implementation of project components. 84 technicians trained outside Iraq as trainers on sophisticated laboratory equipment such as Gas Chromatography and Mini API through 8 training sessions, the mentioned figure represents 100% of the planned activity. 670 lab technicians trained inside Iraq on different lab techniques by those trainers who received training outside Iraq. The number of trainees represents 90% of the planned activity. Lab. Technicians participated in TOTs outside Iraq 5 Establish Laboratory Information Management System (LIMS) Two technical meetings conducted in Baghdad in participation with all key partners (MOEv, MMPW, MOB, UNICEF and WHO) discussing the essential needs for LIMS (Hardware & Software) and to identify the parameters to be included in the software. Bidding process to select specialized company was completed. Offers from 4 competent companies have been received and analyzed. Selection of the winning company is in process. 6 Implement a hygiene education campaign, with special attention to the high risk areas in terms of water born diseases A hygiene education campaigns targeting community leaders and school teachers in 8 governorates namely ( Baghdad, Najaf, Kut, Basra, Dewanya, Erbil, Thi-Qar and Missan ) have been completed; where 4000 school teachers and community leaders participated in the campaigns, the said figure represent 100% of the planned activity. Awareness material such as leaflets, booklets and posters are under preparation. School teachers receiving training on hygiene awareness/Erbil Sep.2007

Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

There have been some noticeable delays related to the following areas: Finalization of the BoQs for the rehabilitation of the sewage laboratories as the government did not provide a list of locations where intervention is required. Difficulty to obtain consensus on the parameters to be included in the Laboratory Information and Management System (LIMS). This issue has been solved through meetings in Baghdad and Amman.

List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results:

The main national partners involved in the implementation are the MOEv, MMPW, MOB and local contractors. The role of the local authorities is to coordinate with WHO and UNICEF to set the specifications for the needed equipment and supplies, and to implement the training activities inside the country and to ensure the enforcement of rules and regualtions related to the water quality control. In addition, they are required to implement the water quality monitoring program to ensure that the water delivered to the end users is tested and its within the Iraqi National Standard for Drinking Water. The local contractors are responsible for the rehabilitaion of the MOEv Central Water Quality Control Laboratory and the wastewater quality control labs according to the specification set by MOEv and MMPWE and both WHO and UNICEF. The rehabilitation work is supervised by both WHO/UNICEF site engineers on the site who usually monitor the implementation progress and document the progress through daily,weekly and monthly reports supported by photographs. Both WHO and UNICEF focal points were in almost daily contact with line ministries (MOEv, MMPW and MOB), in addition to adhoc visits to the water quality control laboratories to monitor and provide technical advice to ministries staff. Monthly meetings were conducted to update them on the implementation status of the project components. In addition, one meeting was conducted in Amman between WHO/UNICEF and high official delegations from the line ministries to set the work plan for the implementation of the project components. The good coordination and continuous cooperation between all key players (MOEv, MMPW, MOB, WHO and UNICEF) has led to smooth implementation of the major activities which as a consequence will have positive impact on the performance and functionality of the water quality monitoring system and will lead to more precise diagnosis of the pollution sources and will help the decision makers to choose the best available solutions.

Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment:

In general, the project affects many cross cutting issues. In terms of the environment, the project is targeting the protection of water resources from pollution through good diagnosis mechanisms. As a result it will have a positive impact on the environment. In terms of gender, the project will benefit all water consumers (men, women and children) and with regards capacity building there was a conscious gender balance. In relation to human rights, one of the primary goals of WHO and its Member States is that “all people, whatever their stage of development and their social and economic conditions, have the right to have access to an adequate supply of safe drinking water”. In terms of employment creation, the rehabilitation works and local procurement and transport of goods will create approximately 1600 job opportunities. In terms of public participation, the hygiene campaign was based purely on public participation.

# Future Work Plan

Priority actions planned for the subsequent reporting period to overcome constraints, build on achievements and partnerships, and use the lessons learned during the previous period:

The priority actions for the subsequent reporting period will concentrate on the finalization the shipment of the remaining laboratory equipment and supplies, in addition to the finalization of the rehabilitation work within the laboratory facilities, also focus will be on completion of the LIMS and the remaining training sessions. It is expected that the planned project components will be implemented within the project time frame (by June 2008).

Indication of major adjustments in the strategies, targets or key outcomes and outputs:

As the project implementation is progressing according to the agreed modified work plan with all key partners, therefore, no adjustments are needed at this stage.

# Text boxes

MOEv, MMPW, MOB, WHO & UNICEF

Implementation cycle

WHO/UNICEF IRAQ

MOEv, MMPW

MOB

Technical unit / WHO/UNICEF IRAQ

Acknowledgment on safe receipt from Line Ministry

Confirm on functioning and running of equipment From Line Ministry

Abroad training on lab techniques and maintenance – nomination by Line Ministry

Processing of procurement

Delivery of consignments

Commissioning, installation and on-site training – follow-up MOEv, MMPW & MOB /WHO/UNICEF

Yes

NO

Is there any remarks or additional requests?

Submission of final Lists of requirements for equipment and supplies

Drafted list of equipment and supplies need for the WQC labs including lab reagents