# United Nations Development Group Iraq Trust Fund

# Project #: E4-01

# December 2007/4th Quarter 2007

# Project Summary Sheet

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Electricity |

| Title | Emergency Supply of Equipment to Electricity Sector in Iraq and Support to Essential Humanitarian Services |
| --- | --- |
| Location | Nation-wide |
| Project Cost | US$11,999,810 |
| Duration | 12 months (extended until 31 October 2007) |
| Approval Date (SC) | 3 May 2004 | Starting Date | August 2004 | Planned Completion Date | 31 Oct 2007 |
| Project Description | To respond to the immediate humanitarian needs of the war-affected Iraqi people through ensuring reliable and safe electricity supply to key load centers throughout the country and essential humanitarian services such as hospitals and water pumping stations in the central and upper south regions. In addition, this project is focused on re-establishing part of the capacity building capabilities of the Ministry of Electricity- MoE (former Commission of Electricity) through refurbishing and reequipping three of their training centers and organizing refreshment training courses for selected technical trainees. |

# Development Goal and Immediate Objectives

Development objective: To respond to the immediate humanitarian needs of war-affected Iraqi people through ensuring reliable and safe electricity supply to all consumer categories, in particular key humanitarian essential services. Immediate objective 1: Key parts of the Iraqi electricity national grid continue to operate, thus ensuring the overall integrity of the grid. Immediate objective 2: Essential humanitarian services in the central and upper south regions of Iraq continue to provide services to the population. Immediate objective 3: The capacity of the MoE in providing basic technical training to its staff restored.

# Outputs, Key activities and Procurement

| Outputs | Output 1: Urgently required equipment and spare parts installed in key parts of the national Output 2: The electrical facilities of essential humanitarian services operational and supported by sufficient backup generation capacity. Output 3: Three MoE training centers fully refurbished and reequipped and the technical capacities of selected trainers enhanced. |
| --- | --- |
| Activities | electricity grid. Activity 1.1 Assessing and prioritizing the needs of equipment and spare parts. Activity 1.2 Procuring and delivering the identified priority equipment and parts. Activity 1.3 Undertaking the necessary repair works and replacements. Activity 2.1 Assessing and prioritizing the needs of generators, ancillary items and repair Activity 2.2 Procuring, delivering, installing and commissioning the generators Activity 2.3 Undertaking the necessary repair works. Activity 3.1 Assessing the needs of the training centers and refurbish and reequip as needed. Activity 3.2 Assessing the requirements for enhancing the capacities of selected trainers. Activity 3.3 Provide refresher training courses for selected trainers. |
| Procurement (major items) | Transformers and Generators |

# Situation as of 31/12/2007

| Funds Committed | US$ 11,999,810 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 11,999,810 | % of approved | 100% |
| Forecast final date | December 2007 | Delay (months) | 28 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | The last shipments of transformers was received and accepted in Baghdad. Installation of over 150 small diesel generators in critical humanitarian facilities have been completed all over Iraq, with a focus on the South. In Umm Qasr, major enhancements in the electricity distribution network have been realized. | % of planned | 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Several hand-over activities are under way and the project will be financially closed. | % of planned | 90% |
| Training of Trainers | Ten electrical engineers from six distribution directorates of the Ministry of Electricity have been trained in Jordan. Training courses in Jordan and Egypt for more than 60 engineers of the Ministry of Electricity took place in July and August 2006. | % of planned | 100% |
| Pre-shipment inspection. |  | % of planned | 100% |

# Qualitative achievements against objectives and results

The project has met its many objectives