# United Nations Development Group Iraq Trust Fund

# Project #66979: E4-02

# Date and Quarter Updated: 1 January-31 March 2009

# 1st Quarter 2009

| Participating UN Organisation: UNDP | Sector: E- Infrastructure/ERDSOT |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Electricity |

| Title | Rehabilitation of the National Dispatch Centre in Baghdad-Stage 2 |
| --- | --- |
| Geographic Location | [National Project with physical building in Al-Ameen District in Baghdad and 41 Remote Terminal Units located within 15 Governorates. ] |
| Project Cost | US$ 11,947,978 |
| Duration | 62 months |
| Approval Date (SC) | 8 May 2004 | Starting Date | May 2004 | Completion Date | [July 2009] |
| Project Description | To respond to the humanitarian needs of the war-affected Iraqi people through ensuring reliable and safe electricity supply to essential basic services such as water supply, hospitals, sewage treatment plants and other community services through improved management and control of the electricity system. |

Development Goal and Immediate Objectives

Enhanced adaptability to monitor and remotely control major power generation plants and 400 kV substations as well as 132kV tie-line substations, enabling their efficient and effective interaction with the National Dispatch Centre for reliable system control and management of the national electricity grid.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | 1.1 Installed state-of-the-art RTU’s with associated peripherals at 19 major power plants, all existing 400 kV and 132kV tie-line substations |
| Activities | 1.1.1 Finalize the technical specifications of the RTUs and associated sub-systems to be included and integrated in the SCADA/EMS bid document 1.1.2 Manage the implementation contract and supervise the installation and commissioning of the SCADA/EMS system in relation to scope identified in November 2006. |
| Procurement (major items) | SCADA and EMS System hardware and software for NDC Baghdad Remote Terminal Units (RTUs) to be installed at field locations |

| Funds Committed | March 2009 | % of approved | 97.70 |
| --- | --- | --- | --- |
| Funds Disbursed | March 2009 | % of approved | 97.42 |
| Forecast final date | July 2009 | Delay (months) | 30 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | National project affects many |  |
| Women | National project affects many |  |
| Children | National project affects many |  |
| IDPs |  |  |
| Others | 42 engineeers with MoH |  |
| Indirect beneficiaries |  |  |
| Employment generation (men/women) |  |  |

| Quantitative achievements against objectives and results |
| --- |
| Spare parts and equipment |  | % of planned | 100 |
| Computing equipment |  | % of planned | 100 |
| Drawings, manuals and test certificates | Further functionality test of SCADA system required. | % of planned | 92 |
| Training of Trainers | Training on database population | % of planned | 100 |
| Handover of equipment | System updated to the latest version. | % of planned | 95 |
| Remote terminal units erected | 43 remote units delivered 28 remote units connected to NDC Prioritize remote units connection when/as security and MoE capacity allows | % of planned % of planned | 100 65 |
| Training for field support at terminal units |  | % of planned | 5 |
| Computer system SCADA running and capacity built | Software commissioned First run of application completed | % of planned | 90 |
| EMS running and capacity built | EMS needs EMS software updating | % of planned | 100 |

Qualitative achievements against objectives and results

43 Remote Terminal Units (RTUs) were delivered, 41 of which were set up with part cable connection. At some sites, setting up, wiring and termination to the process could not be done due to security issues and lack of communication links, preventing changeover. Inventory checks were made for all accessible sites. Training of six (6) MoE engineers on basic RTU maintenance and six (6) on advanced maintenance in Mannheim Germany, plus six (6) in Vasteras, Sweden, and two (2) MoE engineers on SCADA Hardware/Software in USA. Training of five (5) MoE personnel on database population and database maintenance in Houston, United States. To address the unavailability of critical downstream components, UNDP negotiated and issued Contract Amendment No 1 which reduced the original contract scope by limiting field works, but added support to database population and training in Amman.. The NDC software development system (PDS) replica was installed and commissioned to the UNDP Office in Amman on 4 March 2007 to enable training of MoE personnel in Amman. Three (3) MoE engineers were trained on system hardware and software maintenance as well as main SCADA functionalities. The first SCADA workshop was completed by mid March 2007. The PDS replica system was re-configured to be prepared for the first Energy Management System (EMS) training workshop during April and May 2007 at the UNDP Office in Amman involving five (5) MoE engineers/trainees. A further SCADA training workshop was held in July/August 2007 in Amman. The main database was completed during a workshop in Amman in March 2008. After discussions with the Contractor regarding the methods for software updating, a proposal was sent to MoE on 7 May 2008. On 21 May MoE informed UNDP regarding progress on microwave communication links and indicated preferences for future training and support by UNDP. Training workshops including ten (10) participants covering EMS applications and the Dispatcher Training Database were completed on 9 October 2008. First running of software applications and the Dispatcher Training System was initiated in October 2008. Six RTUs were fully tested and four prepared for testing in February 2009. Updating of software was completed during 1st Quarter 2009. Field support training workshops being prepared. Followed-up on contractor's submission of field support workshops and software upgrading during 1st Quarter 2009. Negotiations were conducted with the contractor for training workshops to be conducted in Amman and tentatively agreed the costs of each training workshop (total 5) and the timing 1st Quarter 2009. Revised training workshops proposal was submitted to MoE whom requested that courses be prioritized 1st Quarter 2009. Total 28 RTUs have been connected to the system with 14 tested and functional and another 14 scheduled for testing which is a significant increase during 1st Quarter 2009. Updated the power system model/single line diagrams, etc required for conducting the final training workshops in Amman during 1st Quarter 2009.

Main implementation constrains & challenges (2-3 sentences)

This project is nationwide with highly complicated logistics and security of significant concern. To ensure that the grid is fully functional, rural areas need to be prioritized. The MoE needs to ensure that trained staffs are available for the life of the project and participation achieved at all levels. This project has had to pick up additional mandates not realized by other agencies/development partners. Communication links and the establishment of Regional Control Centres (by other projects) and their supporting infrastructure are a priority to complete this project.

# Footnotes

UNDP and the contractor agreed on an approach to complete the project to the extent possible.  Due to technical difficulties, the CFN network did not become available. Ongoing delays have impacted on available project funds and the full completion of the project will be subject to the availability of communications networks, completion of Regional Control Centers and supporting infrastructure plus additional funding.

Ongoing delays have impacted project funds and the full rehabilitation will be subject to the availability of communications networks, completion of Regional Control Centres and supporting infrastructure plus additional funding.