# United Nations Development Group Iraq Trust Fund

# Project #: E4-02

# Date and Quarter Updated: 1 October-31 December, 4th Quarter 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Electricity |

| Title | Rehabilitation of the National Dispatch Centre in Baghdad - Stage 2 |
| --- | --- |
| Location | Al- Ameen District in Baghdad for National Dispatch Centre (NDC), Remote Terminal Units (RTUs) for Power Stations and major Substations in 15 Governorates |
| Project Cost | US$ 11,947,978 |
| Duration | 2.5 years extension requested till July 2009 |
| Approval Date (SC) | 08 May 2004 | Starting Date | May 2004 | Completion Date | November 2006 (original date) |
| Project Description | To respond to the humanitarian needs of the war-affected Iraqi people through ensuring reliable and safe electricity supply to essential basic services such as water supply, hospitals, sewage treatment plants and other community services through improved management and control of the electricity system. |

# Development Goal and Immediate Objectives

1 Enhanced adaptability to monitor and remotely control major power generation plants and 400 kV substations as well as 132kV tie-line substations, enabling their efficient and effective interaction with the National Dispatch Centre for reliable system control and management of the national electricity grid.

# Outputs, Key activities and Procurement

| Outputs | 1.1 Installed state-of-the-art RTU’s with associated peripherals at 19 major power plants, all existing 400 kV and 132kV tie-line substations. |
| --- | --- |
| Activities | 1.1.1 Finalize the technical specifications of the RTUs and associated sub-systems to be included and integrated in the SCADA/EMS bid document 2.1.1 Manage the implementation contract and supervise the installation and commissioning of the SCADA/EMS system in relation to scope identified in November 2006. |
| Procurement (major items) | SCADA and EMS System hardware and software for NDC Baghdad Remote Terminal Units (RTUs) to be installed at field locations |

| Funds Committed | US$ 11,571,024 | % of approved | 96.85% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 11,328,602 | % of approved | 94.82% |
| Forecast final date | July 2009 | Delay (months) | 30 |

# Quantitative achievements against objectives and results

| Spare parts and equipment Computing equipment |  | % of planned % of planned | 100% 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Further functionality test of SCADA system required. | % of planned | 92% |
| Training of Trainers | Training on database population. | % of planned | 100% |
| Handover of equipment | Software needs final version update. | % of planned | 95% |
| Remote terminal units erected | 43 remote units delivered 8 remote units connected to NDC Prioritize remote units connection when/as security and MoE capacity allows | % of planned | 100% 20% |
| Training for field support at terminal units |  | % of planned | 0% |
| Computer system SCADA running and capacity built EMS running and capacity built | Software commissioned First run of application completed EMS needs EMS software updating | % of planned % of planned | 90% 10% 10% |

# Qualitative achievements against objectives and results

43 Remote Terminal Units (RTUs) were delivered, 38 of which were partially installed. At 80% of sites final connection to NDC has not been made. Erection, wiring and termination to the process could not be done due to security issues and lack of communication links, preventing changeover; Inventory checks were made for all accessible sites; Training of 6 MoE engineers on basic RTU maintenance in Mannheim Germany and 2 MoE engineers on SCADA Hardware/Software in USA. Training of 6 ME engineers on advanced RTU maintenance has been conducted in Mannheim, Germany and Vasteras, Sweden; More than 100 Iraqis have been employed and benefited from learning by doing under this project; Training of 5 MoE personnel on database population and database maintenance in Houston, United States; The NDC software development system (PDS) replica was installed and commissioned to the UNDP office in Amman on 4 March 2007 to enable training of MoE personnel in Amman; 3 MoE engineers were trained on system hardware and software maintenance as well as main SCADA functionalities. The first SCADA workshop was completed by mid March 2007; The PDS replica system in Amman has been used for SCADA and EMS for the preparation of database; The main database was completed in March 2008; Reference lookup tables for links to Regional Control Centres were completed in September 2008; The Dispatcher Training (DTS) database was completed in September 2008; Preparations were made for further technical support to assist MoE to complete outstanding field works. First running of software application October 2008; Training workshop covering EMS application held October 2008.