# United Nations Development Group Iraq Trust Fund

# Project #: E4-02

# Date and Quarter Updated: 1 July 2008 - Q2 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Electricity |

| Title | Rehabilitation of the National Dispatch Centre in Baghdad - Stage 2 |
| --- | --- |
| Location | Al- Ameen District in Baghdad for National Dispatch Centre (NDC) Power Stations and major Substations in 10 Governorates for Remote Terminal Units (RTUs) |
| Project Cost | US$ 11,947,978 |
| Duration | 2.5 years |
| Approval Date (SC) | 03 May 2004 | Starting Date | May 2004 | Completion Date | December 2008 |
| Project Description | To respond to the immediate humanitarian needs of the war-affected Iraqi people through ensuring reliable and safe electricity supply to essential basic services such as water supply, hospitals, sewage treatment plants and other community services. |

# Development Goal and Immediate Objectives

1 Enhanced adaptability to remote control and monitoring of major power generation plants and 400 kV substations as well as 132kV tie-line substations, enabling their efficient and effective interaction with the NDC for reliable power management over the national electricity grid.

# Outputs, Key activities and Procurement

| Outputs | 1.1 Installed state-of-the-art RTU’s with associated peripherals at 19 major power plants, all existing 400 kV and 132kV tie-line substations. |
| --- | --- |
| Activities | 1.1.1 Finalize the technical specifications of the RTUs and associated sub-systems to be included and integrated in the SCADA/EMS bid document 2.1.1 Manage the implementation contract and supervise the installation and commissioning of the SCADA/EMS system. |
| Procurement (major items) | SCADA System Remote Terminal Units (RTUs) |

| Funds Committed | US$ 11,403,581 | % of approved | 95.44% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 11,010,561 | % of approved | 92.15% |
| Forecast final date | December 2008 | Delay (months) | 23 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | RTUs Computing equipment | % of planned | 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Further functionality test of SCADA system by the contractor. | % of planned | 92% |
| Training of Trainers | Training on database population. | % of planned | 70% |
| Pre-shipment inspection | Some handover documents outstanding. | % of planned | 90% |

# Qualitative achievements against objectives and results

43 Remote Terminal Units (RTUs) were delivered, 38 of which were erected with 62% cable connection. In some sites, erection, wiring and termination to the process could not be done due to security issues and lack of communication links, preventing changeover. Inventory checks were made for all accessible sites. Training of 6 ME engineers on basic RTU maintenance in Mannheim Germany and 2 MoE engineers on SCADA Hardware/Software in USA. Training of 6 ME engineers on advanced RTU maintenance has been conducted in Mannheim, Germany and Vasteras, Sweden More than 100 Iraqis have been employed and benefited from learning by doing under this project.