Ninth Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: United Nations Development Programme |  | Old Cluster: E Infrastructure Rehabilitation |
| --- | --- | --- |
|  |  | New Sector: ERDSOT |

| Project No. and Project Title: E4-08 Rehabilitation of Units Nos. 1,4, and 6 at Taji Gas Power Station |  | Report Number: ATLAS Project Number: UNDG 66981 UNDP Iraq 38906 ATLAS Award Number: UNDG 54981 UNDP Iraq 35999 |
| --- | --- | --- |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 July – 31 December 2008 |  | US$ 25,891,860 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Participating UN Organizations: UNDP Other International Organizations National (government, private, NGOs & others): Hitachi Limited Japan, Ministry of Electricity |  | Baghdad Governorate, Taji Coverage area national with focus on Baghdad and Central Iraq |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| MoE; Ministry of Electricity HTC: - Hitachi Limited, Japan AVT: Audio Video Teleconferencing System GPS: Gas Power Station MW: Mega Watt |  | Original programme/project duration.24 months till 22 June 2006. Timeline extended till Nov. 2008. Project operationally closed August 2008. |

# NARRATIVE REPORT FORMAT

# Purpose

a.                Key Immediate Objectives:

1. The generating capacity, availability and reliability of Taji Gas Power Station (Units Numbers. 1, 4 & 6) increased.

2. The plant management and staff able to operate and maintain the units in accordance with international standards.

Outputs:

1. Gas Units Number 1, 4 & 6 at Taji GPS rehabilitated with increased operational reliability.

2. Selected essential spare parts supplied to Taji GPS, which will be available in stock for emergency repairs and routine maintenance, in order to improve the reliability of generation.

3. Trained a substantial number of plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and in turn, train other junior technical personnel (engineers and technicians).

b.	  Relevance to the following benchmarks: UN Assistance Strategy for Iraq, MDGs,  NDS and ICI

UN Assistance Strategy for Iraq: UN Cluster 4 Infrastructure and Results Matrix Housing:

There is an articulated need for efficient operation, management and maintenance of an electricity network with increased availability to the population through rehabilitation of the grid and overall electric generation capacity. This sector further elaborates that the Ministry of Electricity has the  ability to increase capacity, repair and maintain power generation.

The relevant excerpt from the 2006-2007 UN Assistance strategy for Iraq is as follows:

- UNCT Goal 2: Assist in the provision of basic services and promotion of community development and participation:

- Cluster Outcome 2.6: Rehabilitation and governance of infrastructure at local level.

- E3: Increased availability of electricity, particularly to rural and low income areas.

Programme outputs:

-Generation capacity enhanced;

-Technical and management capacity enhanced;

-Power plant equipped with sufficient spare parts and operation;

-Maintenance Manuals and drawings for ready reference in efficient operation and maintenance.

UN Millennium Development Goals (MDG): MDG 7 Target D; by 2020, to have achieved significant improvement in the lives of at least 100 million slum dwellers.

Iraq National Development Strategy: The Rehabilitation of Taji GPS is based on Pillar 2 10 that prioritizes increasing electricity generation and distribution to meet current and projected needs. Within the document it is acknowledged that there is a shortage caused by numerous problems such as sabotage, looting, lack of security for workers, lack of training and obsolete technologies. It is also acknowledged that Baghdad accounts for over 40% of the Iraqi power load. One of the planned goals on page 38 refers to two actions specific to this project which are: 1) reconstruct power network, increase power generation and guarantee a continuous supply and 2) update power distribution.

The International Compact with Iraq (ICI): The rehabilitation of Units to generate electricity at Taji Gas Power Plant links into several components of the ICI. Section 4 Realising the Vision-the Socio-Economic Context in point 2; Revitalize the private sector particularly through the creation of an enabling environment; and point 3; improve the quality of life starting with the provision of basic services. This is further elaborated in the section 4.5 Energy (Oil, Gas and Electricity) page 20-21.

4.5 Energy Goal is: “The Government will develop an energy sector that meets Iraq’s needs and maximizes the benefits of hydrocarbons for all Iraqis and reinforces national unity and institutions.”   The   Government of Iraq will develop an Energy Master Plan on the basis of an Energy Balance…for the electricity sector, the Government will formulate a plan for least cost development of the power system…. The Taji Gas Power Plant links directly into these actions which are activities within the larger UNDP infrastructure projects.

- Human Resources

a.	National Staff & Consultants:  None.

b.	International Staff:  One (1) shared with Mosul GPS Rehabilitation Project

- Methods of Operating

a.	Implementation mechanisms primarily utilized

Due to the prevailing security situation and restrictions placed on the movement of UN staff over the majority of Iraq, in addition to the unique security conditions in Taji, local contractors and a team of engineers were hired by Hitachi to carry out rehabilitation works at site. Eight (8) Engineers were trained in Japan who in turn carried out the plant assessment assignment which assisted in quantifying material and services. One Technical Adviser (Iraqi) was trained with the specific duties for supervision at site which lead to successful rehabilitation works. The local workers hired by the sub-contractor were provided on the job training while at work.

These trainings have ensured quality rehabilitation works, and fostered the readiness of the power station staff for similar rehabilitation and maintenance operations in future.

b.	Procurement procedures utilized .

Procurement is  undeertaken through a competitive process by the experienced UNDP-Iraq Procurement Office which follows agency procurement procedures. The UNDP-Iraq Office has demonstrated that performance over the last few years and was a major asset on which this project has capitalized and benefited.

In this project Hitachi was the original equipment supplier, therefore, a waiver was sought / approved by CAP and ACP from competitive bidding.

c.	Details on the monitoring system(s)

When the implementation was on-going, works were monitored regularly. A web camera system was installed both in the office of Hitachi in Amman and on the site of work. This facilitated day to day discussion and also the web camera could be taken to the precise point of work for close monitoring. This system was active throughout the working time of the day. This ensured that the sub-contractors for rehabilitation works complied with the instruction and acceptable procedures of electrical, mechanical, control and other works.

In addition, UNDP’s technical team were fully engaged in closely monitoring throughout the implementation phase.

The implementing agents are paid by UNDP based on predetermined milestones, which are independently verified by UNDP’s Project Manager upon receipt of payment request invoices from the contractor. Payments are subject to the progress of works and the submission of all supporting documentation by the contractor including monthly progress reports, before, during and after photographs of the works, etc.

Progress was confirmed by UNDP facilitating the holding of three party meetings in Amman which were attended by Hitachi, MoE/ Mosul and UNDP.

d.	Report on any assessments, evaluations or studies undertaken

Initially unit specific technical assessment was carried out with the help of trained staff. This assessment was further discussed with MoE and Plant Engineers to fully evaluate the condition of the units based on the operational and maintenance experience. This had helpd in finalizing the scope of works and essential spare parts required for implementating the rehabilitation project. During the implementation phase, before start of work on each of the two turbine units, as a matter of technical procedure, assessment of performance of the unit was carried out. At the end of repair, evaluation was done and certificates of completion issued. Post monitoring evaluation of the Units will continue until March 2009 within the next reporting period.

Assessment of Needs conducted in late 2003

Results of Field Survey for Needs and Opinions of the Poor in Iraq by Khalid Hantoush Sachet (Sept 2008) identified that the need for electricity was the most requested need at 22.3% out of 11,198 families represented in ten (10) Governorates.

- Results

  - Key outputs achieved in the six month period

1.1 Works on conversion of Unit Number 1 and Unit Number 6 from gas to liquid fuel were completed and the Units1 and 6 were energized to produce 38 MW. The conversion was additional work  and has provided a significant increase to the electricity grid. Unit Number 4 remains completed and can be commissioned with the availability of gas. 100% complete.

1.1 The defect liability period of Unit Number 4 completed. This matter was discussed with Hitachi and a conditional certificate of final completion was issued for Unit Number 4 was issued. Certificate of final completion was issued for Units Number 1 and 6. 100% complete.

2.1 Approximately 175 tons of spare parts and equipment were procured and arrived at site or store. 100% complete.

All drawings, manuals and test certificated issued. 100% complete.

3.1 Twelve (12) Taji Site Engineers received extensive training at the manufacturer’s facility in Japan to become trainers. One (1) Iraqi Technical Adviser trained in Japan, increasing national capacity for rehabilitation and commissioning. Forty (40) un-skilled/semi-skilled workers were provided with “on the job” training. Forty (40) to sixty (60) persons of local communities in Baghdad were employed during rehabilitation and commissioning. 100% complete.

This project initiated operational closure during this six month period with the successful additional works for liquid fuel and the 38 MW increase on the electric grid.

This project is currently in operational closure phase and final reports being prepared. 90% complete.

  - Progress made toward the achievement of specific medium-term outcomes  .

Units 1, 4 & 6:

- All the contracted rehabilitation works were completed on all  three units.

- Subsequently, all the pre-commissioning tests which were possible without availability of gas were completed but energizing Unit 4 was not possible due to non availability of gas fuel. After discussion with MoE and Hitachi, a provisional substantial completion certificate was issued and signed by both parties (UNDP and Hitachi) deducting the work portion which related to energizing the unit and which could not be done due to non availability of  gas at the station. The following tests could not be carried out:

  - AVR dynamic characteristic and synchronization test.

  - Load Operation Test (as per contracted scope of work.)

  - Reliability Test (as per contracted scope of work.)

At a later stage, when the works on Unit Number1 were reaching completion, MoE was able to arrange liquid fuel instead of gas. Hitachi / UNDP assisted in the conversion of the Unit Number 1 to burn liquid fuel instead of gas. After carrying out the conversion and performing all required pre-commissioning tests, Unit 1 was energised. With the success of Unit 1 the decision was made to additionally convert Unit Number 6 which has been converted and all required pre commissioning test completed with Unit 6 energized and between the two, producing 38 MW of electricity satisfactorily.

Most of the financial obligations have been released, upon achieving milestones as per contract, paving the way towards operational and financial closure.

After completion of the defect liability period, a final completion certificate for the project has been issued and financial obligation, releasing 5% retention.  Additionally, the release of performance security has been completed.

Since the repairs to the pipe line supplying gas to the power plant could not carried out due to security reasons, unit no.1 and 6 were converted to operate on liquid fuel. The conversion was carried out as additional work carried out at the request of MoE, and commissioned. Later when gas became available the units were tested on gas firing also. At present the units are capable of operating on both the fuels i.e. gas and liquid.

Unit No.4 was not converted to gas as MoE did not request this  due to the amount of    work involved and the fact that liquid fuel forwarding pumps and equipment were  not available. The unit was, however, tested on gas when the gas became available and now the unit is operative.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

Geographical isolation coupled with difficult security conditions make communication and planning on this technically complex project extremely difficult. HTC have employed technically capable local subcontractor in Iraq provided training to an Iraqi technical advisor for the project and opened a representative office in Amman. UNDP-Iraq had carried out the supervision and monitoring / project management on regular basis by an International Project Manager / Technical Advisor, located in Amman.

UNDP has facilitated MoE/HTC/UNDP cooperation. UNDP facilitated meetings and conduct both bi and tri party discussions by means of satellite audio visual equipment. In addition installation of web cameras and conference facility assisted in the execution of the job.

Throughout the implementation phase, this project remained under security threat. On several occasions, delays were incurred because of the general security situation, unexpected curfew and harm caused to subcontractors’ employees. The most tragic incident occurred on 14 January 2007 when four (4) subcontractor employees at Taji were kidnapped and murdered approximately 15 Kilometers from the power plant. Work was suspended for several weeks and resulted in a two-month delay to substantial completion.

The original implementation modalities, which were planned during the preparation stage of the project in the latter part of 2003, were no longer valid as the security situation evolved. New implementation modalities were adopted, where MoE Engineers played a larger role in overseeing the installation works. All achievements of milestones were confirmed by the station engineers at different stages.

Establishment of a camp at the work site, with essential facilities and food for the staff, accelerated the speed of work and mitigated the risk of daily transportation of staff to and from the site. This also increased work time per day.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

As a consequence of the restrictions placed on the movement of UN staff in Iraq, UNDP Iraq sought other ways to overcome the situation on the ground in order to reach the target populations and succeeded in the required intervention at the power plant. Hence, a strong partnership was developed with line ministries and station management. This arrangement allowed UNDP to assess the local institutions’ capacities for project implementation and to support counterparts in identifying their major priorities. New implementation modalities were adopted with the MoE Engineers playing a larger role in overseeing the installation of work which has built capacity for future sustainability.

These de-facto partnerships with beneficiaries and contractors are a flexible and efficient operational modality in Iraq’s difficult conflict environment.

Close collaboration with beneficiaries and contractor allowed for a revised implementation strategy to take account of the concerns of all, adapting optimally to the security situation, the bottlenecks of world markets and the needs of the Iraqi people.

Key Partnerships:   Ministry of Electricity and Hitachi Limited Japan.

Inter-Agency Collaboration: There was limited inter-agency collaboration due to the very specialized nature of the works.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Direct Beneficiaries: Since the power station is connected to National Grid System as such, the entire population of Iraq would benefit  from the additional MegaWatts of power.  If run in isolation, about 150,000 inhabitants residing in Baghdad and the Central Region would benefit.

During rehabilitation stage, the project provided employment to skilled and semi skilled workers plus general labour. About forty (40) –sixty (60) persons were employed at different stages of works. Furthermore, numerous employment opportunities will be created as a result of restoration of the power supply.

Project implementation indirectly resulted in:

-Generated commercial activity and employment opportunities for national contractors;

-Created and sustained employment opportunities within MoE;

-Enhanced the employment terms, conditions and future opportunities through the capacity building of relevant MoE staff;

-The availability of increased electricity in Baghdad and Central Region will provide an incentive for economic development and serves as a pre-requisite for private sector development.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- The project will have final ITF and technical reports completed

-Operationally and financially closed.

- Six Monthly Performance Indicators Assessment

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1 The humanitarian needs of the war-affected Iraqi people by ensuring the supply of reliable and safe electricity to permit operation of essential humanitarian services such as water supply, hospitals, schools, sewage treatment plants and other community services responded to. |
| IP Output 1.1 Gas Units 1, 4 and 6 at Taji GPS rehabilitated with increased operational reliability. | Indicator 1.1.1 Implementation of scheduled rehabilitation works to three (3) turbine units; 1, 4 and 6. | Unit 1 Poor condition, limited output; Unit 4 Not Working rotor damaged; Unit 6 Poor condition, limited output; | 50 MW of electricity becomes available. Reduce further deterioration of units. | Unit 1 running at 18MW satisfactorily on gas/oil. Exceeded commitment; Unit 4 Energize as gas becomes available; Running at 15-18 MW depending upon gas pressure. Unit 6 Running at 18-19MW satisfactorily on gas/oil. Exceeded commitment. | Inspection visits and verifications made by UNDP engineers or consultants in close co-operation with Taji GPS engineering staff. Careful verification made by UNDP engineers in close co-operation with Mosul GPS engineering staff. This was achieved through three party meetings held during and after the completion of rehabilitation works. The last meeting was held on 14th-15th. January 2008. The achievement of objectives has been verified. Regular contacts are being maintained by telephone – e-mail to confirm the latest operating status of the units. Technical Tests Included: AVR dynamic characteristic and synchronization test; Load operation test; Reliability test; Certificate of Final Completion. | It has been confirmed by the manager of Taji Power Plant that the instruments are indicating what is being generated by the unit (approx. 50 MW) to the national grid system, Initially when the gas line was damaged by sabotage and later when four project workers were killed, the task became almost impossible, but with constant discussions, persuasion, motivation and monitoring both on the part of UNDP and Hitachi the work could continue. First unit No. 1 and 6 were energized with liquid firing and later when gas became available the units were energized on gas also. Unit No.4 was energized on gas firirng only. Daily real time monitoring through web cameras and VSAT was initiated to continue work with minimum delays. |
| IP Outcome 2. The generating capacity, availability and reliability of Units No.1 and 6 at Taji Gas Power Station increased. |
| IP Output 2.1 Set of selected, essential spare parts supplied to Taji GPS, are in stock for emergency repairs and routine maintenance - in order to improve the reliability of power generation. | Indicator 2.1.1 Provision of specified spare parts and relevant rectification of selected components coming from disassembled units. | Lack of spare parts and severely deteriorated plant. | Spare parts available for 2-3 years of repair. Ability of plant staff to operate and maintain the power plant after being trained. | Delivery of 175 Tons of spare parts and equipment. Twelve site engineers from Taji and Mosul trained as trainers in Japan; One Iraqi technical advisor trained in Japan, increasing national capacity for rehabilitation and commissioning; Forty un-skilled/semi-skilled workers from the TPS were provided on the job training. | Careful verifications and inspection visits were conducted under the guidance of UNDP engineers in close co-operation with Taji GPS engineering staff. This was achieved through three party meeting during and after the completion of rehabilitation works. The last meeting was held on 14th-15th. January 2008. The achievement of objectives has been verified. In addition comprehensive weekly reports with photographs were issued to document the activities undertaken. Post completion monitoring by telephone and e-mail confirm that the units are operating without interruption. | Timely arrangement for waiver of custom letters and monitoring the security situation while the cargo was on its way to the station by road was an uphill task, achieved through constant liaison with the ground staff. |
| IP Outcome 3. The capacity of staff and plant management to operate and maintain the units in accordance with international standards built. |  |  |  |  | IP Outcome 2 |
| IP Output 3.1 Trained plant engineers to operate and maintain the power plant for higher levels of performance and skill to train other junior technical personnel (engineers and technicians). | Indicator 3.1.1 Implementation of relevant training carried out both at site in Taji and at the manufacturer’s workshop. | Capacity needed to conduct repair | Iraqi engineers better able to operate and maintain the power plant to its best capabilities and standards. They will be able to train other junior engineers. | Twelve site engineers from Taji and Mosul trained as trainers in Japan; One Iraqi technical advisor trained in Japan, increasing national capacity for rehabilitation and commissioning; Forty un-skilled/semi-skilled workers from the TPS were provided on the job training. | Careful verifications and inspection visits were conducted under the guidance of UNDP engineers in close co-operation with Mosul GPS engineering staff. This was achieved through three party meeting during and after the completion of rehabilitation works. The last meeting was held on 14th-15th. January 2008. The achievement of objectives has been verified. In addition comprehensive weekly reports with photographs were issued to document the activities undertaken. Post completion monitoring by telephone and e-mail confirm that the units are operating without interruption. | Nomination of engineers from MoE was the first step of the training process. This was a lengthy process and could be achieved only by constant follow-up by UN Staff. Later arranging visas and a training programme to suit the requirements needed was only possible with the remarkable help of MoE and Hitachi. |